## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q3 2018 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 225% | 225% | 224.7% | 154% | 154% | 153.7% | 216% | 216% | 284.5% | 154% | 154% | 153.9% | 226%
.x.2 | % of promised (by that time) CPU available | 100% | 193% | 193% | 238% | 262% | 262% | 262.2% | 175% | 175% | 222.4% | 210% | 210% | 210.2% | 234.2%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 96% | 77% | 95% | 100% | 100% | 96% | 98% | 97% | 85% | 98% | 93% | 91.75%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 96% | 79% | 100% | 100% | 100% | 100% | 98% | 97% | 86% | 98% | 93% | 92.25%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 71% | 70% | 70.29% | 79% | 79% | 80.46% | 122% | 199% | 163.5% | 105% | 92% | 75.78% | 105.4%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 63% | 59% | 53.17% | 72% | 58% | 73.96% | 106% | 173% | 142.1% | 92% | 86% | 64.67% | 89.41%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2018
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2018-07-01 | 2018-08-01 | 2018-09-01 | Total |  | Site | 2018-07-01 | 2018-08-01 | 2018-09-01 | Total
Liverpool | Umd4 | umd4 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 20236332 | 16451824 | 20116264 | 56804420 |  | Lancaster | 24693490 | 23946734 | 26451878 | 75092102
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 11699030 | 16235095 | 15608721 | 43542846 |  | Liverpool | 12698041 | 17521985 | 17149377 | 47369403
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 49323391 | 48980496 | 46104850 | 144408737 |  | Manchester | 53974862 | 57461962 | 54673395 | 166110219
[7 empty] | Sheffield | 5016265 | 5929282 | 4134021 | 15079568 |  | Sheffield | 5309953 | 7669824 | 4688873 | 17668650
[7 empty] | Total CPU hrs | 81258753 | 81667415 | 81829835 | 244756003 |  | Total | 96676346 | 106600505 | 102963523 | 306240374
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2018/1/2018/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 48384 | 3074 | 20332 | 1368 | 238% | 224.7% | 36.76% | 32.11% | 56804420 | 21.86% | 2208 | 106831872 | 53.17% | 70.29%
Liverpool | 26664 | 1425 | 10169 | 927 | 262.2% | 153.7% | 20.26% | 14.88% | 43542846 | 16.76% | 2208 | 58874112 | 73.96% | 80.46%
Manchester | 46010 | 4544 | 20685 | 1597 | 222.4% | 284.5% | 34.96% | 47.46% | 144408737 | 55.58% | 2208 | 101590080 | 142.1% | 163.5%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 8.023% | 5.546% | 15079568 | 5.804% | 2208 | 23316480 | 64.67% | 75.78%
Totals | 131618 | 9574 | 56210 | 4237 | 234.2% | 226% | 100% | 100% | 259835571 | 100% | 2208 | 290612544 | 89.41% | 105.4%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3360 | 48384 | 3074 | NA | Lancaster
Liverpool | 2498 | 26634 | 1425 | NA | Liverpool
Manchester | 4297 | 46010 | 4544 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10955 | 131588 | 9574 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2018
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cernatschool | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hyperk.org | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | moedal | na48 | na62 | neiss | ops | pheno | planck | vo.skatelescope.eu | snoplus | solidexperiment.org | vo.sixt.cern.ch | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 |  | 0 | 1 | 0 | 1 | 0 |  | 1 | 1 |  |  | 1 |  |  | 1 |  | 16
Liverpool | 1 | 1 |  | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 35
Manchester | 1 | 1 |  | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 23
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 | 0 | 3 | 1 | 1 | 0 | 0 |  | 3 | 4 | 1 | 1 | 1 | 2 | 1 |  | 2 | 4 | 2 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 4 | 3 |  | 3 | 4 |  | 1 | 4 | 2 | 2 | 4 |  | 92
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1800 | 0 | 17 | 1 | 1818 | 0.9351% | 0.9901%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3970.24 | 0.57 | 179 | 8.47 | 4266.46 | 4.196% | 4.407%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q3 2018
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.25; GridPP Funded Month 2: 0.25; GridPP Funded Month 3: 0.25
| Mitchell Perry | Unfunded Month 1: 0.15; Unfunded Month 2: 0.15; Unfunded Month 3: 0.15
Total |  | 5.25 | 5.25 | 5.25 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Migration and Update to C7 of DPM headnode. Getting singularity working. Hardware expansion from University funds Site “DMZ’d” | Headnode migrated to virtual infrastructure and new OS Singularity works! More Nodes. Site now outside University border routers. |  |  | A lot of teething issues with the new DPM. None, just took a bit of time to get right. None, again just took some time to sort out. Caused some unforseen Ipv6 issues.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Electrical Problems caused a few of downtimes |  |  | Work taken to make things better (which took another downtime).
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Singularity Deployed DPM headnode moved Deployed new hardware |  |  | 30/9/18 31/8/18 31/8/18 |  | Able to run atlas container pilots. No longer worried about the DPM headware failing. More jobslots!
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Migrate DPM to DOME backend, start migrating pool nodes to C7 Purchase new kit with GRIDPP/IRIS grants Prepare cluster for IRIS Vos/users |  |  | 20th December 2018 |  | SE ready for new users and expansion More kit! Ready to provide resources when they land.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q3
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Liverpool | Talks and conferences WLCG/STFC devel SysAdmin New VO support HW purchase round Tickets CVES | GridPP41, GPP6 evolution “Skills” HTCondor ws, RAL “Integration” DUNE Collab, Edinb., “T2 view” (del. Oct 9) Testing/VC/Rel. Acc. Parser, HTCondorCE VAC V3 testing (DNS exceptions, firewall configs), C7 puppet builds, C7 task hung issue, new storage svr map3, new build system, C7 porting) DUNE cpu and disk, support, LZ Voms Bids underway HTTP/DPM restart (135374, 667,852,136667, 978) 137458 (misuse of space tokens by VO) 135369 (Cert w/out restart) CVE 2018 14634, mitigations & new kernel |  |  | N/a N/a N/a How to cross-test with other batch systems N/a N/a Still no resolution to this flakiness N/a
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Liverpool | The DPM HTTP restart issue (see 5 ticks in list above) is a pest. Due to a bug in Apache. |  |  | Automatic restart, but not 100%.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Adoption of Ipv6, documentation Definitive fix for Spectre/Meltdown on all CPUs |  |  | 1 Oct 2018 1 Oct 2018 |  | External partners unready External partners unready
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | HW Purchase (CPU, Disk) LSST changes (see af email, 22 Oct) VAC Superslot/Multicore tests Condor/Singularity, document baseline HTCondorCE Acc parsers release Find reason for VAC/C7 deadlock. Adoption of Ipv6, documentation Definitive fix for Spectre/Meltdown on all CPUs |  |  | 1 Jan 2019 1 Jan 2019 1 Jan 2019 1 Jan 2019 1 Jan 2019 1 Jan 2019 1 Jan 2019 1 Jan 2019 |  | New HW purchased and running jobs SLAC VOMS svr in use VAC running in MCORE mode C7 with singularity for ATLAS HTCondorCE site uses new release No VAC deadlock on C7 Depends on external partners Depends on external partners
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Ste working with STFC/WLCG Accounting on support for HTCondorCE parser. |  |  | 1 Sept 2018 |  | Release testing underway
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes

## Sheffield
GridPP Quarterly Report
Area | NorthGrid
Quarter | 2018Q3
Reported by | Elena Korolkova
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Sheffield | Operations | Configuring a new puppet machine. Tuning dpm headnode. Meeting with University network team to discuss ipv6 setup. Routine sysadmin work. |  |  | .
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Sheffield | University currently doesn't support ipv6. |  |  | ipv6 available is available from the end of September
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Configuring a new puppet machine. Tuning dpm headnode. Meeting with University network team to discuss ipv6 setup |  |  | 30 September 2018
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Sheffield | Preparation work for moving wn's to Centos7 in January 2019. Configure perfsonar to use ipv6 . |  |  | 2018-12-25
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Elena: atlas cloud support work
Other outputs and Knowledge |  |  | Date |  | Notes