## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q418 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 305.8% | 305.8% | 388.2% | 388.2% | 388.2% | 352.1% | 352.1% | 352.1% | 131.6% | 131.6% | 131.6% |  |  |  | 300.5% | 300.5% | 300.5%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 275.9% | 275.9% | 375.1% | 375.1% | 375.1% | 604.7% | 604.7% | 604.7% |  |  |  | 363.9% | 363.9% | 363.9%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 97% | 100% | 95% | 99% | 97% | 100% | 99% | 87% | 100% | 94% | 100% | 97% |  |  |  | 97.25% | 96% | 98%
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 97% | 100% | 98% | 100% | 100% | 100% | 99% | 91% | 100% | 94% | 100% | 97% |  |  |  | 97.5% | 97.75% | 98.75%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 77.99% | 101.6% | 95.92% | 87.21% | 80.35% | 82.23% | 75.55% | 32.66% | 84.96% | 63.14% | 135.8% | 146.4% |  |  |  | 76.82% | 87.92% | 102.6% | RHUL high
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 54.22% | 64.27% | 67.3% | 74.74% | 62.97% | 70.88% | 75.55% | 28.34% | 67.87% | 53.82% | 75.14% | 69.38% |  |  |  | 65.63% | 58.25% | 69.12%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q418
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2018 Oct | 2018 Nov | 2018 Dec | Total |  |  | 2018 Oct | 2018 Nov | 2018 Dec | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 40 Gb/s | dCache |  | UKI-LT2-Brunel | 17287815.2806 | 19906358.2876 | 14812927.595 | 52007101 |  | UKI-LT2-Brunel | 26175871.8352 | 28202873.6569 | 19746765.6073 | 74125511
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 27848357.5847 | 31763387.0807 | 35007593.0182 | 94619338 |  | UKI-LT2-IC-HEP | 35131686.6997 | 36161912.4395 | 38469252.8351 | 109762852
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 23201769.5756 | 22730131.0244 | 22052629.9288 | 67984531 |  | UKI-LT2-QMUL | 28439589.1041 | 28251736.9584 | 28409445.4281 | 85100771
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 28504760.5333 | 27212639.8659 | 22408575.5933 | 78125976 |  | UKI-LT2-RHUL | 33549505.6584 | 76550509.2402 | 54721988.5328 | 164822003
[8 empty] | UKI-LT2-UCL-HEP | 287236.2138 | 210035.1203 | 21265.2854 | 518537 |  | UKI-LT2-UCL-HEP | 340392.1489 | 327159.9602 | 31817.3534 | 699369
[8 empty] | Total | 97129939 | 101822551 | 94302991 | 293255482 |  | Total | 123637045 | 169494192 | 141379270 | 434510507
https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2018/10/2018/12/all/localinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1400 | 9632.812 | 457.8006 | 363.3% | 305.8% | 18.25% | 10.94% | 52007101 | 17.77% | 2208 | 77280000 | 67.3% | 95.92% | 70.16%
UKI-LT2-IC-HEP | 60456 | 5100 | 21915.766 | 1313.8219 | 275.9% | 388.2% | 31.52% | 39.84% | 94619338 | 32.32% | 2208 | 133486848 | 70.88% | 82.23% | 86.2%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 23.65% | 39.07% | 67984531 | 23.22% | 2208 | 100161504 | 67.87% | 84.96% | 79.89%
UKI-LT2-RHUL | 51000 | 1300 | 8434.349 | 987.6466 | 604.7% | 131.6% | 26.59% | 10.16% | 78125976 | 26.69% | 2208 | 112608000 | 69.38% | 146.4% | 47.4% | Very large wall-clock figures, being investigated
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 191819 | 12801 | 52714.598 | 4260.48 | 363.9% | 300.5% | 100% | 100% | 292736946 | 100% | 2208 | 423536352 | 69.12% | 102.6% | 67.49%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5765 | 68892 | 1377
UKI-LT2-IC-HEP | 5718 | 56664 | 4965
UKI-LT2-QMUL | 4064 | 204559 | 5031
UKI-LT2-RHUL | 4624 | 48121 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 378236 | 12833
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q418
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | alice | atlas | biomed | calice | camont | cepc | cernatschool.org | comet.j-parc.jp | cms | dteam | dune | dzero | enmr.eu | epic.vo.gridpp.ac.uk | fusion | geant4 | gridpp | hone | hyperk.org | icecube | ilc | ipv6.hepix.org | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | neiss.org.uk | ops | pheno | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.gear.cern.ch | vo.helio-vo.eu | vo.landslides.mossaic.org | skatelescope.eu | vo.londongrid.ac.uk |  | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 16
UKI-LT2-IC-HEP | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 21
UKI-LT2-QMUL | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 23
UKI-LT2-RHUL | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 17
Total | 0 | 4 | 4 | 2 | 0 | 1 | 3 | 1 | 4 | 4 | 4 | 0 | 1 | 1 | 0 | 0 | 4 | 0 | 3 | 1 | 4 | 0 | 4 | 3 | 3 | 4 | 1 | 0 | 4 | 4 | 4 | 1 | 0 | 0 | 4 | 0 |  | 0 | 0 | 0 | 2 | 0 |  | 1 | 1 | 77
Storage resource in use per VO (TB)
Site | supernemo.vo.eu-egee.org | t2k.org | biomed | ops | ilc | camont | mice | cms | totalep | atlas | dteam | zeus | babar | ngs.ac.uk | lhcb | geant4 | hone | hyperk | dzero | na48 | alice | epic.vo.gridpp.ac.uk | gridpp | pheno | cedar | gin | calice | geant | vo.londongrid.ac.uk | cdf | fusion | compchem | superbvo.org | snoplus.snolab.ca | comet | vo.gear.cern.ch | ukqcd.vo.gridpp.ac.uk | lz | lsst | cernatschool.org | solidexperiment.org | vo.moedal.org | skatelescope.eu | Other | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 0.278 |  | 0.411 |  |  |  | 10.601 | 972 |  | 36 | 0.017 | 0.002 |  |  |  |  | 1.491 | [5 empty] | 0.557 | 0.01 |  |  |  |  | 0.202 | [6 empty] | 0.018 |  | 0 |  |  | 0 |  |  |  | 1021.587 | 10.63% | 1.33%
UKI-LT2-IC-HEP |  | 29.08 | 0 |  | 0 |  | 0 | 2787.848 |  | 9.761 |  |  |  |  | 356.216 |  |  |  | 0 | [15 empty] | 36.652 |  |  | 357.668 |  |  | 193.874 |  |  | 72.322 | 3843.421 | 39.99% | 17.94%
UKI-LT2-QMUL |  | 164 | 0.929 |  |  | 0 |  | 3.3 |  | 3500 | 0.052 |  |  |  | 181 |  | 0.673 | 0.0068 |  |  |  | 0.016 | 0.069 | 0.017 |  |  |  |  | 0.0052 |  |  |  | 0.019 | 11 |  |  |  | 0 | 0.265 | 0.073 | 0 | 1.1 | 0.109 |  | 3862.634 | 40.19% | 4.617%
UKI-LT2-RHUL | 0 |  | 0 |  |  |  |  | 1.6 |  | 882 | 0.015 | 0.002 |  |  |  |  | 0.19 | [5 empty] | 0.006 | 0.018 | [6 empty] | 0.009 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 883.84 | 9.196% | 0.02715%
Total | 0.278 | 193.08 | 1.34 | 0 | 0 | 0 | 10.601 | 3764.748 | 0 | 4427.761 | 0.084 | 0.004 | 0 | 0 | 537.216 | 0 | 2.354 | 0.0068 | 0 | 0 | 0 | 0.016 | 0.632 | 0.045 | 0 | 0 | 0 | 0 | 0.2072 | 0 | 0.009 | 0 | 0.019 | 11 | 36.652 | 0.018 | 0 | 357.668 | 0.265 | 0.073 | 193.874 | 1.1 | 0.109 | 72.322 | 9611.482 | 100% | 9.174%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q418
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.5 | 0.5 | 0.5 | 0.15 | 0.15 | 0.15 | Have not been updated
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Antonio Perez Fernandez | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| B.Green/Tom | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.05 | 6.05 | 6.05 | 1.95 | 1.95 | 1.95

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q418
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | October: updated xroot redirector. Success November: update storage to dmlite 1.10. Success December: lost one disk server.
UKI-LT2-IC-HEP | Procuring new GridPP and IRIS hardware. Preparing for move to Slough.
UKI-LT2-QMUL | Initial planning of GridPP hardware spend with meeting with several vendors. Attended UKRI Cloud technical workshop at JISC London HQ. (notes:https://etherpad.net/p/UKRI-Cloud-Technical-Workshop-20181124). QMUL received an award from the UK IPv6 Council (Jim Bound IPv6 World Leader Award) due to >20% of QMUL Internet traffic using IPv6. GridPP staff were instrumental in making this happen at QMUL. The award was accepted on behalf of QMUL by Terry Froy and Chris Walker. Brought 2 new AMD compute nodes (HPE DL385, CPU=AMD EPYC 7401/ 256GB RAM) with capability to operate network ports at 10/40/50 and 100Gb/s. These will replace the existing R710 used for the StoRM frontend and allow us to scale WAN data transfers up to 100Gb/s. Continued development of our new deployment system. We now have a production CentOS7 batch system with a new CE, batchmaster and worknode passing ops and atlas tests and running production ATLAS jobs. Investigating use of containers (Kubernetes/ Singularity) and use of "user namespace" only for containers on workernodes. Investigating adding IPv6 to worknodes (we have it available for storage and forntend services)
UKI-LT2-RHUL | Some problems with PDUs down affected production in December. IPV6 awaiting solution to DNS
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes