## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q4 2018 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 225% | 225% | 224.7% | 154% | 154% | 153.7% | 216% | 285% | 284.5% | 154% | 154% | 153.9% | 226%
.x.2 | % of promised (by that time) CPU available | 100% | 193% | 238% | 238% | 262% | 262% | 262.2% | 175% | 222% | 222.4% | 210% | 210% | 210.2% | 234.2%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 77% | 87% | 100% | 100% | 100% | 98% | 97% | 100% | 98% | 93% | 93% | 95%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 96% | 79% | 88% | 100% | 100% | 100% | 98% | 97% | 100% | 98% | 93% | 93% | 95.25%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 70% | 70% | 92.89% | 79% | 80% | 86.8% | 199% | 164% | 167.6% | 92% | 76% | 109.9% | 119.1%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 59% | 53% | 76.48% | 58% | 74% | 78.19% | 173% | 142% | 144.8% | 86% | 65% | 93.54% | 102.1%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2018
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total |  | Site | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total
Liverpool | Umd4 | umd4 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 27801780 | 27601063 | 26300415 | 81703258 |  | Lancaster | 33099013 | 34992122 | 31143027 | 99234162
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 15299096 | 14241964 | 16493018 | 46034078 |  | Liverpool | 16899332 | 16326620 | 17876099 | 51102051
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 46484824 | 47851021 | 52740676 | 147076521 |  | Manchester | 54014055 | 56413636 | 59829744 | 170257435
[7 empty] | Sheffield | 7011203 | 6466571 | 8331318 | 21809092 |  | Sheffield | 8155877 | 7782463 | 9688784 | 25627124
[7 empty] | Total CPU hrs | 89585700 | 89694048 | 95534109 | 274813857 |  | Total | 112168277 | 115514841 | 118537654 | 346220772
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2018/1/2018/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 48384 | 3074 | 20332 | 1368 | 238% | 224.7% | 36.76% | 32.11% | 81703258 | 27.54% | 2208 | 106831872 | 76.48% | 92.89%
Liverpool | 26664 | 1425 | 10169 | 927 | 262.2% | 153.7% | 20.26% | 14.88% | 46034078 | 15.52% | 2208 | 58874112 | 78.19% | 86.8%
Manchester | 46010 | 4544 | 20685 | 1597 | 222.4% | 284.5% | 34.96% | 47.46% | 147076521 | 49.58% | 2208 | 101590080 | 144.8% | 167.6%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 8.023% | 5.546% | 21809092 | 7.352% | 2208 | 23316480 | 93.54% | 109.9%
Totals | 131618 | 9574 | 56210 | 4237 | 234.2% | 226% | 100% | 100% | 296622949 | 100% | 2208 | 290612544 | 102.1% | 119.1%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3360 | 48384 | 3074 | NA | Lancaster
Liverpool | 2498 | 26634 | 1425 | NA | Liverpool
Manchester | 4297 | 46010 | 4544 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10955 | 131588 | 9574 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2018
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cernatschool | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hyperk.org | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | moedal | na48 | na62 | neiss | ops | pheno | planck | vo.skatelescope.eu | snoplus | solidexperiment.org | vo.sixt.cern.ch | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 |  | 0 | 1 | 0 | 1 | 0 |  | 1 | 1 |  |  | 1 |  |  | 1 |  | 16
Liverpool | 1 | 1 |  | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 35
Manchester | 1 | 1 |  | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 23
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 | 0 | 3 | 1 | 1 | 0 | 0 |  | 3 | 4 | 1 | 1 | 1 | 2 | 1 |  | 2 | 4 | 2 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 4 | 3 |  | 3 | 4 |  | 1 | 4 | 2 | 2 | 4 |  | 92
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1800 | 0 | 17 | 1 | 1818 | 0.9351% | 0.9901%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3970.24 | 0.57 | 179 | 8.47 | 4266.46 | 4.196% | 4.407%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2018
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | bar: GridPP Funded Month 1 to GridPP Funded Month 3
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| R. Fay | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
| J. Bland | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.25; GridPP Funded Month 2: 0.25; GridPP Funded Month 3: 0.25
| Mitchell Perry | Unfunded Month 1: 0.15; Unfunded Month 2: 0.15; Unfunded Month 3: 0.15
Total |  | 5.25 | 5.25 | 5.25 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | DOME “activation” for DPM Purchase of new Kit | Dome’d. New kit purchased. |  |  | Some issues with some tests. Dome not as bedded in as we’d like. New racks are proving slow to install.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | CREAM CE is on its way out - need to replace it. |  |  | Engaged in HTCondorCE investigation.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | DPM Dome’d New kit purchased Prepare for IRIS VO/Users |  |  | 20/12/18 |  | DPM running all the mod cons. More kit Ready for new user groups.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Deploy New Kit Engage and get IRIS jobs running alongside Grid resources Deploy new CEs |  |  | 31st Jan 28th Feb 28th Feb |  | Increased capacity. Utilisation of new equipment More Ces
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q4
Reported by | Matt Doidge
Progress over last Quarter
Site |  | Successes |  |  | Problems/Issues
Liverpool | Deployment research Storage Sysadmin. | HTCondor-CE in production Fixes, test and document for APEL-client for HTCondor-CE Preprations in puppet for DPM conversion to DOME Revert VAC to SL6. C7 gives kernel lockup. Varied sysadmin (CVEs, kernel updates, etc. Bids for new HW order |  |  | Having problems with older HW, esp migration to C7. Need to document route to HTCondor-CE for other sites.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Liverpool | Older hardware is hard to get going with CentOS7. |  |  | Use for VAC, sl6.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Adoption of Ipv6, documentation HW Purchase (CPU, Disk) LSST changes (see af email, 22 Oct) VAC Superslot/Multicore tests Condor/Singularity, document baseline HTCondorCE Acc parsers release Find reason for VAC/C7 deadlock. Adoption of Ipv6, documentation |  |  | 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 31 Dec 2018 |  | External partners unready Bids out. Next step is to order. Complete Deferred Complete Complete Deferred Deferred
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Deal with CentOS7 on older hardware problems Remove all SL6 resources Set up new hardware Document route to HTCondor-CE Switch DOME on Remove BDII dependency for APEL client |  |  | 1 Apr 2019 1 Apr 2019 1 Apr 2019 1 Apr 2019 1 Apr 2019 1 Apr 2019 |  | No SL6 No SL6 New slots and storage running New doc to help sites DOME running APEL works without BDII
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Ste working with STFC/WLCG Accounting on support for HTCondorCE parser. |  |  | 1 Sept 2018 |  | Now in operation
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Other outputs and Knowledge |  |  | Date |  | Notes