## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q4 2018 | [5 empty] | Not OK
Reported by | Kashif Mohammad | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 156.2% | 156.2% | 116.6% | 178.3% | 178.3% | 178.3% | 140.2% | 140.2% | 140.2% | 191.4% | 191.4% | 183.6% | 170.1% | 170.1% | 170.1% | 189.2% | 189.2% | 189.2% | 169.1% | 169.1% | 158.1%
.x.2 | % of promised (by that time) CPU available | 100% | 248.4% | 248.4% | 248.4% | 218.9% | 218.9% | 218.9% | 308.6% | 308.6% | 308.6% | 240.4% | 240.4% | 240.4% | 239.5% | 239.5% | 239.5% | 206.5% | 206.5% | 206.5% | 240.6% | 240.6% | 240.6%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 96.51% | 96.51% | 40.15% | 91.15% | 91.15% | 100% | 99.79% | 99.79% | 99.11% | 95.39% | 95.39% | 100% | 99.33% | 99.33% | 99.35% | 90.91% | 90.91% | 96.18% | 95.51% | 95.51% | 89.13% | Bham decommisiioning …
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 96.51% | 96.51% | 51.15% | 97.36% | 97.36% | 100% | 99.79% | 99.79% | 99.11% | 95.39% | 95.39% | 100% | 99.33% | 99.33% | 99.35% | 91.22% | 91.22% | 96.18% | 96.6% | 96.6% | 90.97%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 48.92% | 33.96% | 73.75% | 33.52% | 53.21% | 54.11% | 97.18% | 95.23% | 94.71% | 65.14% | 82.41% | 75.24% | 56.58% | 67.23% | 87.6% | 69.21% | 73.48% | 64.39% | 58.26% | 66.55% | 77.89%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 35.3% | 34.92% | 34.92% | 25.07% | 24.53% | 24.53% | 80.27% | 79.4% | 79.4% | 61.62% | 60.95% | 60.95% | 53.86% | 53.28% | 53.28% | 56.33% | 55.72% | 55.72% | 51.57% | 51.01% | 51.01%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q4 2018
Reported by | Kashif Mohammad
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total |  | Site | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total
Birmingham | UMD4 | VAC |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | UMD4 | EMI 3+UMD4 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 8032814.2728 | 9358104.3037 | 10244455.9242 | 15577411 |  | Birmingham | 9496637.0742 | 11133833.6737 | 12273727.0736 | 32904197.8215
Cambridge | UMD 4/SL6 or C7 | UMD 4/SL6 or VAC/CS7 |  | 10Gb/s | 2*20Gb/s | DPM 1.10.3 |  | Bristol | 2625101.2537 | 5327636.6963 | 4941064.139 | 7984607 |  | Bristol | 4421798.5537 | 6758542.6019 | 6434686.5731 | 17615027.7287
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 5287462.4785 | 4122114.6117 | 4834539.1546 | 15563617 |  | Cambridge | 6218434.1912 | 6179291.362 | 6167251.125 | 18564976.6782
RALPP | UMD4 | UMD3 |  | 2X10Gb/s | 100Gb/s | Dcache 3.2.41 |  | Oxford | 14990536.0654 | 15939809.0135 | 17987346.4095 | 44989023 |  | Oxford | 16519896.5621 | 18511956.5827 | 20509389.9272 | 55541243.072
Sussex | UMD4/EMI3 | UMD4 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 22021832.6781 | 23878372.6976 | 25575543.4714 | 54463246 |  | RALPP | 27328391.4836 | 30055657.0514 | 32166953.7863 | 89551002.3213
[8 empty] | Sussex | 2368353.1155 | 1532209.6569 | 2971807.1725 | 6870138 |  | Sussex | 2673483.2161 | 1761172.0516 | 3504318.897 | 7938974.1647
[8 empty] | Total CPU hrs | 55326099.864 | 60158246.9797 | 66554756.2712 | 182039103.1149 |  | Total | 66658641.0809 | 74400453.3233 | 81056327.3822 | 222115421.7864
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | job efficiency
Birmingham | 20206 | 1000 | 8136 | 858 | 248.4% | 116.6% | 15.65% | 18.37% | 15577411 | 10.71% | 2208 | 44614848 | 34.92% | 73.75% | 47.34%
Bristol | 14744 | 560 | 6735 | 314 | 218.9% | 178.3% | 11.42% | 10.28% | 7984607 | 5.49% | 2208 | 32554752 | 24.53% | 54.11% | 45.33%
Cambridge | 8878 | 265 | 2877 | 189 | 308.6% | 140.2% | 6.874% | 4.867% | 15563617 | 10.7% | 2208 | 19602624 | 79.4% | 94.71% | 83.83%
Oxford | 33432 | 940 | 13905 | 512 | 240.4% | 183.6% | 25.89% | 17.26% | 44989023 | 30.93% | 2208 | 73817856 | 60.95% | 75.24% | 81%
RALPP | 46300 | 2610 | 19329 | 1534 | 239.5% | 170.1% | 35.85% | 47.93% | 54463246 | 37.45% | 2208 | 102230400 | 53.28% | 87.6% | 60.82%
Sussex | 5584 | 70 | 2704 | 37 | 206.5% | 189.2% | 4.324% | 1.286% | 6870138 | 4.723% | 2208 | 12329472 | 55.72% | 64.39% | 86.54%
Totals | 129144 | 5445 | 53686 | 3444 | 240.6% | 158.1% | 100% | 100% | 145448042 | 100% | 2208 | 285149952 | 51.01% | 77.89% | 65.48%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
[6 empty] | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
[10 empty] | Q4 | 2208
[5 empty] | Birmingham | 22433 | 980
[5 empty] | Bristol | 9607 | 0
[5 empty] | Cambridge | 5940 | 293
[5 empty] | Oxford | 26240 | 940
[5 empty] | RALPP | 42840 | 3079
[5 empty] | Sussex | 2006 | 83
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q4 2018
Reported by | Kashif Mohammad
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 14
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 23
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [7 empty] | 5
[47 empty] | 0 | 0
[47 empty] | 0 | 0
Total | 5 | 6 | 0 | 2 | 3 | 3 | 1 | 1 | 2 | 5 | 6 | 2 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 1 | 0 | 2 | 0 | 0 | 4 | 106
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 21.1% | 0%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 8.113% | 0.001822%
Cambridge | 0 | 185.7 | 0 | 0 | 0.096 | 0.027 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.206 | 0 |  | 0 | 0 | 0.448 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.35 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.831 | 4.01% | 1.94%
Oxford | 0 | 660 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 2.98 | 0.018 |  | 0.016 | 1.5 | 32.13 | 0 | 0 | 0.02285 | 698.5091 | 14.75% | 5.368%
RALPP | 0 | 642 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1353 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 326 |  | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0.7 | 8 | 0 | 0 | 0.65 | 2412.06 | 50.95% | 3.775%
Sussex |  | 50 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [10 empty] | 51.01 | 1.077% | 1.98%
Total | 999 | 1537.7 | 2 | 1 | 0.096 | 0.051 | 0 | 0 | 0 | 1738.11 | 0.311 | 0 | 0.049 | 0.73 | 0 | 0.129 | 0 | 0.2095 | 0.066 | 0 | 1.604 | 0 | 326.4538 | 0 | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063 | 0 | 0 | 1 | 3.35 | 2.98 | 0.018 | 0 | 0.046 | 2.2 | 40.13 | 0 | 0 | 0.67285 | 4734.5192 | 100% | 2.815%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q4 2018
Reported by | Kashif Mohammad
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| Luke Kreczko | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Cambridge
| John Hill | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Oxford
| Vip Davda | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| Kashif Mohammad | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| Leo Rojas | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 2 | 2 | 2 | 1.7 | 1.7 | 1.7
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q4 2018
Reported by | Kashif Mohammad
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Completed decommissioning of DPM. Prepared ATLAS EOS instance but holding off deployment until told to. Created a single SQUID to use for the VAC machines so there is no longer disk space + CPU taken up on each node for this. Have managed to make progress in getting IPv6 DNS entries from the university |  | Aircon failed in October and took some time to fix. Our avilability/reliability has suffered from the tests failing during DPM decommissioning. Still looking for ways to test against EOS or not have tests at all
Bristol | 1. 7-OS Site-BDII (on 7-OS VM host) replaced previous 6-OS Site-BDII (on SL5 VM host!) 2. 7-OS PerfSONAR BW built & ready on IPv6-enabled network, ticket in to site Networks to open PerfSONAR ports 3. Still hoping to experiment with xrootd-only SE with Sam Skipsey (have site login ready for him, waiting on his ssh keys) 4. Old LCG main switch finally replaced with 3 new switches :) |  | 1 Changing Site-BDII in GOC-DB not propagate: propagation of GOC-DB info to worldwide top-BDIIs been broken since May 2018 (ggus#138461 update#11). Had to reboot the old Site-BDII & raise tickets + LCG-Rollout complaints to get this fixed. But it was resolved & the old 6-OS Site-BDII retired. 2. Local Network staff not get around to open new 7-OS PerfSONAR site firewall ports before Christmas Holidays :-/ 3. Sam Skipsey not finding time to start with Bristol on xrootd-only SE :-/ 4. Local Networks cut off our monitoring of new LCG network switches :[ 5. vm00 the old (6-OS) vm-host keeps intermittently losing its public network. Brings whole LCG site down (hosts lcgarg & other VMs) 6. LHCb jobs fail on 7-OS WN @Bristol. CMS & local users can use 7-OS WN ok, but had to disable 7-OS WN till we debug the problem with LHCb. :[ 7. Site staff shortage not improving :[
Cambridge | Storage dual-stacked. Squid upgraded to 4.4. cvmfs upgraded to 2.5.2. VAC instabilities on CS7 appear to have gone away with upgrade to 7.6 |  | Still waiting for ATLAS and ops to decide if and how to move SAM tests to VAC. perfSonar host went bad (high load) just before Xmas (eventual "solution" was to reinstall from scratch).
Oxford | Moved majority of Compute Nodes to Centos7 ARCE. Progress in IPV6 as university IT services has enabled IPv6 Route advertisement on edge router. Looking to install a new IPv6 DHCP server
RALPP | All storage and data movers migrated to Dual Stack Moved most of the Worker nodes to C7
Sussex | We bough a couple of compute nodes from 2018 budget, they have to be added to the grid. |  | Physics is still recruiting a person to look after de site and perform the necessary updates 1. Moving away from SL6. 2. decomissioning and replacing cream CE
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: Upgrade to HTCondor 8.6 Due date: 12/31/2018 |  | 12/31/2018 |  | Partial upgrade to 8.8 (1 scheduler and two 7-OS WNs)
Bristol: New IPv6 perfsonar hosts |  | 2018-12-01 |  | BW ready but no site fw ports open
Bristol: New network gear installed & configured |  | 2018-10-01 |  | All hardware arrived & configured (including security!) & all machines migrated
RALPP: Deploy New Hardware |  | 2018-03-31 |  | Complete, New disk and CPU installed and allocated
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Make all Service Nodes Dual Stack |  | 2019-03-31
RALPP: Dual Sack the worker nodes |  | 2019-03-31
RALPP: Upgrade site-bdii to C7 |  | 2018-12-31 |  | On hold - awaiting clarity on the future of the BDII
RALPP: Join LHCONE |  | 2019-06-30
Bristol: Continue with upgrade to HTCondor 8.6 (htc00+01 managers next = failover pair - one at a time) |  | 03/31/2019 |  | SL7 container jobs (via jobrouter)
Bristol: Order New hardware to replace host vm00 |  | 2018-07-12 |  | Hardware arrived(not in production yet)
Bristol: Completion of 7-OS IPv6 perfsonar BW+LAT |  | 03/31/2019 |  | All test passing
Bristol: decide on grant spending for WNs - GPUs? |  | : 03/31/2019 |  | Spending Plan(even just rough)
Oxford: Buy CPU from GridPP Hardware grant |  | : 03/31/2019 |  | Spending Plan
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes