## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q119 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 305.8% | 371.3% | 388.2% | 388.2% | 606.6% | 352.1% | 352.1% | 352.1% | 131.6% | 131.6% | 131.6% |  |  |  | 300.5% | 300.5% | 374.8%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 275.9% | 258.6% | 375.1% | 375.1% | 375.1% | 604.7% | 604.7% | 604.7% |  |  |  | 363.9% | 363.9% | 356.7%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 95% | 83% | 97% | 100% | 98% | 87% | 100% | 94% | 100% | 97% | 100% |  |  |  | 96% | 98% | 93.75% | Brunel low
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 98% | 89% | 100% | 100% | 98% | 91% | 100% | 97% | 100% | 97% | 100% |  |  |  | 97.75% | 98.75% | 96% | Brunel low
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 101.6% | 95.92% | 98.51% | 80.35% | 82.23% | 87.91% | 32.66% | 84.96% | 83.4% | 135.8% | 146.4% | 80.77% |  |  |  | 87.92% | 102.6% | 86.86% | RHUL high
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 64.27% | 67.3% | 61.91% | 62.97% | 70.88% | 75.71% | 28.34% | 67.87% | 70.85% | 75.14% | 69.38% | 68.16% |  |  |  | 58.25% | 69.12% | 69.92%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q119
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2019 Jan | 2019 Feb | 2019 Mar | Total |  |  | 2019 Jan | 2019 Feb | 2019 Mar | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 100 Gb/s | dCache |  | UKI-LT2-Brunel | 9191803.5733 | 16728342.3915 | 20885662.5759 | 46805809 |  | UKI-LT2-Brunel | 15971226.0381 | 27634552.905 | 30868169.8323 | 74473949
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 31590489.9538 | 29573686.087 | 31503087.7622 | 92667264 |  | UKI-LT2-IC-HEP | 37268116.6814 | 34863635.3687 | 35465868.5469 | 107597621
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 16812924.3812 | 21171566.7865 | 31436239.1454 | 69420730 |  | UKI-LT2-QMUL | 27685143.7995 | 26157897.46 | 27875622.5341 | 81718664
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 24907067.4006 | 24090969.8501 | 26083567.2401 | 75081604 |  | UKI-LT2-RHUL | 28907745.5452 | 28279014.6973 | 31792470.4699 | 88979231
[8 empty] | Total | 82502285 | 91564565 | 109908557 | 283975407 |  | Total | 109832232 | 116935100 | 126002131 | 352769464
https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2018/10/2018/12/all/localinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1700 | 9632.812 | 457.8006 | 363.3% | 371.3% | 18.61% | 10.64% | 46805809 | 16.48% | 2160 | 75600000 | 61.91% | 98.51% | 62.85%
UKI-LT2-IC-HEP | 56664 | 7969 | 21915.766 | 1313.8219 | 258.6% | 606.6% | 30.14% | 49.9% | 92667264 | 32.63% | 2160 | 122394240 | 75.71% | 87.91% | 86.12%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 24.13% | 31.31% | 69420730 | 24.45% | 2160 | 97984080 | 70.85% | 83.4% | 84.95%
UKI-LT2-RHUL | 51000 | 1300 | 8434.349 | 987.6466 | 604.7% | 131.6% | 27.12% | 8.14% | 75081604 | 26.44% | 2160 | 110160000 | 68.16% | 80.77% | 84.38%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 188027 | 15970 | 52714.598 | 4260.48 | 356.7% | 374.8% | 100% | 100% | 283975407 | 100% | 2160 | 406138320 | 69.92% | 86.86% | 80.5%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5876 | 70218 | 1757
UKI-LT2-IC-HEP | 5718 | 56664 | 7969
UKI-LT2-QMUL | 3992 | 379018 | 5031
UKI-LT2-RHUL | 4624 | 48121 | 1460
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 554021 | 16217
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q119
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | atlas | biomed | calice | cepc | cernatschool.org | cms | comet.j-parc.jp | dteam | dune | enmr.eu | epic.vo.gridpp.ac.uk | gridpp | hone | hyperk.org | icecube | ilc | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | ops | Other | pheno | skatelescope.eu | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | vo.complex-systems.eu | vo.cta.in2p3.fr | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
UKI-LT2-IC-HEP | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 23
UKI-LT2-QMUL | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 23
UKI-LT2-RHUL | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 17
Total | 4 | 4 | 2 | 1 | 3 | 4 | 1 | 4 | 4 | 1 | 1 | 4 | 0 | 3 | 1 | 4 | 4 | 3 | 3 | 4 | 1 | 4 | 0 | 4 | 2 | 4 | 1 | 0 | 0 | 4 | 1 | 1 | 0 | 1 | 1 | 79
Storage resource in use per VO (TB)
Site | atlas | biomed | calice | cepc | cernatschool.org | cms | comet.j-parc.jp | dteam | dune | enmr.eu | epic.vo.gridpp.ac.uk | gridpp | hone | hyperk.org | icecube | ilc | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | ops | Other | pheno | skatelescope.eu | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | vo.complex-systems.eu | vo.cta.in2p3.fr | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 36 | 0.442 | 0 | 0 | 0 | 972 | 0 | 0.062 | 0 | 0 | 0 | 0.557 | 1.491 | 0 | 0 | 0 | 0 | 0 | 0 | 10.601 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0.278 | 0 | 0 | 0 | 0.202 | 0 | 0.002 | 1021.645 | 9.229% | 1.336%
UKI-LT2-IC-HEP | 0 | 0 | 0 | 0 | 0 | 3767.521 | 36.652 | 0 | 248.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.089 | 0 | 364.509 | 0 | 0 | 0 | 162.5 | 0 | 0 | 0 | 308.165 | 0 | 0 | 29.073 | 0 | 0 | 0 | 0 | 0 | 5305.342 | 47.92% | 21.67%
UKI-LT2-QMUL | 3500 | 0.929 | 0 | 0 | 0.073 | 3.3 | 0 | 0.052 | 0 | 0 | 0.016 | 0.069 | 0.673 | 0.0068 | 0 | 0 | 181 | 0.265 | 0 | 0 | 0 | 0 | 0 | 0.017 | 0.109 | 11 | 0 | 0.019 | 0 | 164 | 0 | 0 | 0.0052 | 1.1 | 0 | 3862.634 | 34.89% | 4.617%
UKI-LT2-RHUL | 879 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0.015 | 0 | 0 | 0 | 0.006 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 880.831 | 7.957% | 0.02623%
Total | 4415 | 1.371 | 0 | 0 | 0.073 | 4744.421 | 36.652 | 0.129 | 248.833 | 0 | 0.016 | 0.632 | 2.354 | 0.0068 | 0 | 0 | 569.089 | 0.265 | 364.509 | 10.601 | 0 | 0 | 162.5 | 0.045 | 0.109 | 11 | 308.165 | 0.019 | 0.278 | 193.073 | 0 | 0 | 0.2072 | 1.1 | 0.004 | 11070.452 | 100% | 12.12%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q119
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.5 | 0.5 | 0.5 | 0.15 | 0.15 | 0.15 | Have not been updated
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| P. Kyberd | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Antonio Perez Fernandez | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| B.Green/Tom | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 6.05 | 6.05 | 6.05 | 1.95 | 1.95 | 1.95

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q119
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | Jisc/Janet approved to upgrade the Brunel link to 80 Gbps, where 40 Gbps will be exclusively dedicated for the GridPP project. Brunel storage upgrade to DOME 1.12 (first in WLCG). Brunel storage in DOMA TPC stress testing. Brunel transfers 55% of data on IPv6.
UKI-LT2-IC-HEP | Preparing for move to Slough.
UKI-LT2-QMUL | Had a major clear out of old IT equipment. Have tendered, procured, installed, configured and put into production 24 new compute worker nodes. In addition we have procured a new 100Gb core network, 25/100Gb Top of rack switches, and new racks, PDUs and UPSs to replace aging infrastructure and future proof the cluster. Installed and brought online 2 new compute nodes, with capability to operate network ports at 10/40/50 and 100Gb/s. These have replaced aging R710s used for the StoRM frontend and will hopefully allow us to scale WAN data transfers up to 100Gb/s. Started discussions with central networks about provisioning of upgraded WAN network including a data transfer zone. We put into production over 2000 job slots for our CentOS7 batch system (1/2 our compute resources). Singularity has been enabled on this service. Provided advice to colleagues about switch, router and network issues related to development of a new TDAQ system for a new particle physics detector. Upgraded to the latest version of StoRM and enabled third part transfers for WebDav using StoRM and participate in wlcg data transfer stress tests.
UKI-LT2-RHUL | IPV6 awaiting solution to DNS Some problem with the implementation of Perfson2.
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes