## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q1 2019 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 225% | 225% | 224.7% | 154% | 154% | 183.4% | 285% | 285% | 284.5% | 154% | 154% | 153.9% | 232.5%
.x.2 | % of promised (by that time) CPU available | 100% | 238% | 238% | 239.2% | 262% | 262% | 280.1% | 222% | 222% | 222.4% | 210% | 210% | 210.2% | 237.8%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 77% | 87% | 79.8% | 100% | 100% | 99.5% | 97% | 100% | 100% | 93% | 93% | 96% | 93.83%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 79% | 88% | 82% | 100% | 100% | 99.5% | 97% | 100% | 100% | 93% | 93% | 97.5% | 94.75%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 70% | 93% | 65.48% | 80% | 87% | 75.32% | 164% | 168% | 152.7% | 110% | 110% | 77.62% | 98.54%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 53% | 76% | 54.76% | 74% | 78% | 66.13% | 142% | 145% | 136.5% | 65% | 94% | 67.32% | 86.29%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html
Now instead using:
http://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
http://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/Critical/SITES/UKI-NORTHGRID-SHEF-HEP?start_date=2019-01-01&end_date=2019-03-31

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2019
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total |  | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total
Liverpool | Umd4 | umd4 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 25908215 | 15420208 | 17485885 | 58814308 |  | Lancaster | 30959115 | 17813921 | 21555590 | 70328626
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 14462617 | 11301053 | 15822933 | 41586603 |  | Liverpool | 16266263 | 13427224 | 17671462 | 47364949
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 51113489 | 42012140 | 45498561 | 138624190 |  | Manchester | 57536988 | 47972376 | 49574025 | 155083389
[7 empty] | Sheffield | 4849439 | 5552898 | 5294431 | 15696768 |  | Sheffield | 5806475 | 6342281 | 5949260 | 18098016
[7 empty] | Total CPU hrs | 91484321 | 68733401 | 78807379 | 239025101 |  | Total | 110568841 | 85555802 | 94750337 | 290874980
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2018/1/2018/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 48640 | 3074 | 20332 | 1368 | 239.2% | 224.7% | 36.38% | 31.21% | 58814308 | 23.09% | 2208 | 107397120 | 54.76% | 65.48%
Liverpool | 28482 | 1700 | 10169 | 927 | 280.1% | 183.4% | 21.3% | 17.26% | 41586603 | 16.33% | 2208 | 62888256 | 66.13% | 75.32%
Manchester | 46010 | 4544 | 20685 | 1597 | 222.4% | 284.5% | 34.41% | 46.14% | 138624190 | 54.42% | 2208 | 101590080 | 136.5% | 152.7%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 7.899% | 5.391% | 15696768 | 6.162% | 2208 | 23316480 | 67.32% | 77.62%
Totals | 133692 | 9849 | 56210 | 4237 | 237.8% | 232.5% | 100% | 100% | 254721869 | 100% | 2208 | 295191936 | 86.29% | 98.54%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 3200 | 48640 | 3074 | NA | Lancaster
Liverpool | 2691 | 28482 | 1700 | NA | Liverpool
Manchester | 4297 | 55829 | 4544 | NA | Manchester
Sheffield | 800 | 10560 | 531 | NA | Sheffield
Totals | 10988 | 143511 | 9849 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2019
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cernatschool | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | geant4 | gridpp | hyperk.org | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | moedal | na48 | na62 | neiss | ops | pheno | planck | vo.skatelescope.eu | snoplus | solidexperiment.org | vo.cta.in2p3.fr | vo.sixt.cern.ch | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 |  |  | 0 | 1 | 1 |  | 0 | 1 | 0 | 1 |  | 1 | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 |  | 0 | 1 | 0 | 1 | 0 |  | 1 | 1 |  | 1 |  | 1 |  |  | 1 |  | 17
Liverpool | 1 | 1 |  | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 35
Manchester | 1 | 1 |  | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  | 23
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  |  | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 | 0 | 3 | 1 | 1 | 0 | 0 |  | 3 | 4 | 1 | 1 | 1 | 2 | 1 |  | 2 | 4 | 2 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 4 | 3 |  | 3 | 4 |  |  | 1 | 4 | 2 | 2 | 4 |  | 93
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1800 | 0 | 17 | 1 | 1818 | 0.9351% | 0.9901%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3970.24 | 0.57 | 179 | 8.47 | 4266.46 | 4.196% | 4.407%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q1 2019
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | R. Long | 1 | 1 | 1
| M. Doidge | 1 | 1 | 1
| P. Love |  |  |  | 0.3 | 0.3 | 0.3
Liverpool | S. Jones | 1 | 1 | 1
| R. Fay |  |  |  | 0.5 | 0.5 | 0.5
| J. Bland |  |  |  | 0.5 | 0.5 | 0.5
Manchester | A. Forti | 1 | 1 | 1
| R. Frank | 1 | 1 | 1
| A. McNab |  |  |  | 0.5 | 0.5 | 0.5
Sheffield | E. Korolkova | 0.25 | 0.25 | 0.25
| Mitchell Perry |  |  |  | 0.15 | 0.15 | 0.15
Total |  | 5.25 | 5.25 | 5.25 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | 0.5 | 0.5 | 0.5
Manchester | A. Forti |  |  |  | 1 | 1 | 1

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q2
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | DOME aftermath Commission new Kit Prepare for new infrastructure | Dome’d. New kit purchased. |  |  | Some issues with some tests. Dome not as bedded in as we’d like. New racks are proving slow to install.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | CREAM CE is on its way out - need to replace it. DPM Issues after DOME upgrade Down a warm body as Robin will be leaving. |  |  | Engaged in HTCondorCE investigation. Work closely with DPM devs and other sites. Extensive handover.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Commissioned new Kit – storage coming online in phases DPM Stabilised |  |  | 31/3/19 |  | Increased Capacity Less firefighting
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Improve IRIS utilisation Deploy new CEs Improve stability |  |  | 2019-06-30 |  | Improve Utilisation and uptime.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 18Q1
Reported by | Ste Jones
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Liverpool | Usual routine admin Information System HTCondor-CE baseline APEL Accounting | HW Purchase (disk, cpu) + install, maint… Test JSON-style info sys (WLCG related) Bring HTCondor-CE into production for large VOs, document and make install kit (WLCG related) Refined HTCondor-CE APEL interface. Passed to HTCondor team for integration. Will test once product is released. |  |  | None to speak of Need a JSON Schema for this work. None. Working with WLCG CREAM-migration task force. Awaiting product release to test change on UK T2 HTCondor-CE system.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Liverpool | Liverpool will be a “small T2”, with half FTE. This will reduce effort for baselines of new technologies. |  |  | None. Work with WLCG (CREAM Migration, APEL for HTCondorCE, UK baseline + documentation, BDII replacement, etc.) will be cut or curtailed.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Scrapped. Liverpool to become small site. Preparations underway now to simplify site to allow it to be maintained with 0.5 FTE. On the other hand, make time for some work already in progress, e.g. finalise HTCondor-CE APEL interface (with BDII bypass), JSON work for new Info System etc. There will be slower progress, though. Can’t give a date.) |  |  | 6/9/2019 |  | Site survives downsize…
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Unknown. A much greater proportioner of effort will be expended on routine admin, leaving less overall for novel or advanced research, documentation, or work with WLCG on (say) CREAM migration (e.g. ARC/HTCondorCE) or work with (say) Condor devs at Madison. We’ll have to see how it goes with new hours, and find out if there is anything left over for more interesting work.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG