## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q1 2019 | [5 empty] | Not OK
Reported by | Kashif Mohammad | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 156.2% | 116.6% | 116.6% | 178.3% | 178.3% | 178.3% | 140.2% | 140.2% | 140.2% | 191.4% | 183.6% | 183.6% | 170.1% | 170.1% | 170.1% | 189.2% | 189.2% | 189.2% | 169.1% | 158.1% | 158.1%
.x.2 | % of promised (by that time) CPU available | 100% | 248.4% | 248.4% | 248.4% | 218.9% | 218.9% | 218.9% | 308.6% | 308.6% | 308.6% | 240.4% | 240.4% | 240.4% | 239.5% | 239.5% | 239.5% | 206.5% | 206.5% | 206.5% | 240.6% | 240.6% | 240.6%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 96.51% | 40.15% | 70% | 91.15% | 100% | 99% | 99.79% | 99.11% | 99.11% | 95.39% | 100% | 99% | 99.33% | 99.35% | 95% | 90.91% | 96.18% | 95% | 95.51% | 89.13% | 92.85% | Bham decommisiioning …
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 96.51% | 51.15% | 70% | 97.36% | 100% | 99% | 99.79% | 99.11% | 99.11% | 95.39% | 100% | 95% | 99.33% | 99.35% | 95% | 91.22% | 96.18% | 95% | 96.6% | 90.97% | 92.19%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 33.96% | 73.75% | 77.18% | 53.21% | 54.11% | 59.1% | 95.23% | 94.71% | 103.3% | 82.41% | 75.24% | 85.72% | 67.23% | 87.6% | 91.54% | 73.48% | 64.39% | 70.37% | 66.55% | 77.89% | 83.98%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 34.92% | 34.92% | 67.71% | 24.53% | 24.53% | 44.99% | 79.4% | 79.4% | 79.08% | 60.95% | 60.95% | 78.74% | 53.28% | 53.28% | 65.53% | 55.72% | 55.72% | 59.17% | 51.01% | 51.01% | 67.61%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2019
Reported by | Kashif Mohammad
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total |  | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total
Birmingham | UMD4 | VAC |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | UMD4 | EMI 3+UMD4 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 10276542.9566 | 8537259.5885 | 10739975.9341 | 29553778.4792 |  | Birmingham | 11403375.1871 | 9655962.7124 | 12625889.8448 | 33685227.7443
Cambridge | UMD 4/SL6 or C7 | UMD 4/SL6 or VAC/CS7 |  | 10Gb/s | 2*20Gb/s | DPM 1.10.3 |  | Bristol | 4057684.2325 | 5537143.6152 | 4734384.3226 | 14329212.1703 |  | Bristol | 5599509.7879 | 6764598.7959 | 6456564.8049 | 18820673.3887
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 4762866.6004 | 5063652.5398 | 5337365.249 | 15163884.3892 |  | Cambridge | 6777791.4952 | 6235407.6405 | 6797045.7811 | 19810244.9168
RALPP | UMD4 | UMD3 |  | 2X10Gb/s | 100Gb/s | Dcache 3.2.41 |  | Oxford | 19877578.0412 | 16554545.1573 | 20430611.6694 | 56862734.8679 |  | Oxford | 22227079.7442 | 17493052.2954 | 22178671.3873 | 61898803.4269
Sussex | UMD4/EMI3 | UMD4 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 22726347.2338 | 17846502.6729 | 24965648.2595 | 65538498.1662 |  | RALPP | 32102497.3297 | 26717521.61 | 32729387.5582 | 91549406.4979
[8 empty] | Sussex | 2427684.9067 | 2125128.3189 | 2584524.5017 | 7137337.7273 |  | Sussex | 2765330.0292 | 2646718.7542 | 3075514.3685 | 8487563.1519
[8 empty] | Total CPU hrs | 64128703.9712 | 55664231.8926 | 68792509.9363 | 188585445.8001 |  | Total | 80875583.5733 | 69513261.8084 | 83863073.7448 | 234251919.1265
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | job efficiency
Birmingham | 20206 | 1000 | 8136 | 858 | 248.4% | 116.6% | 15.65% | 18.37% | 29553778.4792 | 15.67% | 2160 | 43644960 | 67.71% | 77.18% | 87.74%
Bristol | 14744 | 560 | 6735 | 314 | 218.9% | 178.3% | 11.42% | 10.28% | 14329212.1703 | 7.598% | 2160 | 31847040 | 44.99% | 59.1% | 76.14%
Cambridge | 8878 | 265 | 2877 | 189 | 308.6% | 140.2% | 6.874% | 4.867% | 15163884.3892 | 8.041% | 2160 | 19176480 | 79.08% | 103.3% | 76.55%
Oxford | 33432 | 940 | 13905 | 512 | 240.4% | 183.6% | 25.89% | 17.26% | 56862734.8679 | 30.15% | 2160 | 72213120 | 78.74% | 85.72% | 91.86%
RALPP | 46300 | 2610 | 19329 | 1534 | 239.5% | 170.1% | 35.85% | 47.93% | 65538498.1662 | 34.75% | 2160 | 100008000 | 65.53% | 91.54% | 71.59%
Sussex | 5584 | 70 | 2704 | 37 | 206.5% | 189.2% | 4.324% | 1.286% | 7137337.7273 | 3.785% | 2160 | 12061440 | 59.17% | 70.37% | 84.09%
Totals | 129144 | 5445 | 53686 | 3444 | 240.6% | 158.1% | 100% | 100% | 188585445.8001 | 100% | 2160 | 278951040 | 67.61% | 83.98% | 80.51%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
[6 empty] | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
[10 empty] | Q4 | 2208
[5 empty] | Birmingham | 22433 | 980
[5 empty] | Bristol | 9607 | 0
[5 empty] | Cambridge | 5940 | 293
[5 empty] | Oxford | 26240 | 940
[5 empty] | RALPP | 42840 | 3079
[5 empty] | Sussex | 2006 | 83
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2019
Reported by | Kashif Mohammad
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 14
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 23
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [7 empty] | 5
[47 empty] | 0 | 0
[47 empty] | 0 | 0
Total | 5 | 6 | 0 | 2 | 3 | 3 | 1 | 1 | 2 | 5 | 6 | 2 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 1 | 0 | 2 | 0 | 0 | 4 | 106
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 21.1% | 0%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 8.113% | 0.001822%
Cambridge | 0 | 185.7 | 0 | 0 | 0.096 | 0.027 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.206 | 0 |  | 0 | 0 | 0.448 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.35 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.831 | 4.01% | 1.94%
Oxford | 0 | 660 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 2.98 | 0.018 |  | 0.016 | 1.5 | 32.13 | 0 | 0 | 0.02285 | 698.5091 | 14.75% | 5.368%
RALPP | 0 | 642 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1353 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 326 |  | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0.7 | 8 | 0 | 0 | 0.65 | 2412.06 | 50.95% | 3.775%
Sussex |  | 50 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [10 empty] | 51.01 | 1.077% | 1.98%
Total | 999 | 1537.7 | 2 | 1 | 0.096 | 0.051 | 0 | 0 | 0 | 1738.11 | 0.311 | 0 | 0.049 | 0.73 | 0 | 0.129 | 0 | 0.2095 | 0.066 | 0 | 1.604 | 0 | 326.4538 | 0 | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063 | 0 | 0 | 1 | 3.35 | 2.98 | 0.018 | 0 | 0.046 | 2.2 | 40.13 | 0 | 0 | 0.67285 | 4734.5192 | 100% | 2.815%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2019
Reported by | Kashif Mohammad
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| Luke Kreczko | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Cambridge
| John Hill | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Oxford
| Vip Davda | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| Kashif Mohammad | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| Leo Rojas | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 2 | 2 | 2 | 1.7 | 1.7 | 1.7
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q1 2019
Reported by | Kashif Mohammad
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham
Bristol
Cambridge | GridPP5 Tranche2 CPUs installed. Reinstalled perfSonar after box went into a strange state just before Xmas. CentOS7.6 seems to have resolved hang seen with VAC factories. |  | Continuing war of attrition with old disk servers. Some issues with keeping CREAM CE operational (resolved in the next quarter!).
Oxford | Upgraded to DOME.
RALPP
Sussex
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: Upgrade to HTCondor 8.6 Due date: 12/31/2018 |  | 12/31/2018 |  | Partial upgrade to 8.8 (1 scheduler and two 7-OS WNs)
Bristol: New IPv6 perfsonar hosts |  | 2018-12-01 |  | BW ready but no site fw ports open
Bristol: New network gear installed & configured |  | 2018-10-01 |  | All hardware arrived & configured (including security!) & all machines migrated
RALPP: Deploy New Hardware |  | 2018-03-31 |  | Complete, New disk and CPU installed and allocated
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Make all Service Nodes Dual Stack |  | 2019-03-31
RALPP: Dual Sack the worker nodes |  | 2019-03-31
RALPP: Upgrade site-bdii to C7 |  | 2018-12-31 |  | On hold - awaiting clarity on the future of the BDII
RALPP: Join LHCONE |  | 2019-06-30
Bristol: Continue with upgrade to HTCondor 8.6 (htc00+01 managers next = failover pair - one at a time) |  | 03/31/2019 |  | SL7 container jobs (via jobrouter)
Bristol: Order New hardware to replace host vm00 |  | 2018-07-12 |  | Hardware arrived(not in production yet)
Bristol: Completion of 7-OS IPv6 perfsonar BW+LAT |  | 03/31/2019 |  | All test passing
Bristol: decide on grant spending for WNs - GPUs? |  | : 03/31/2019 |  | Spending Plan(even just rough)
Oxford: Buy CPU from GridPP Hardware grant |  | : 03/31/2019 |  | Spending Plan
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes