## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | ATLAS |  |  | Close to target
Year | 2018 |  |  | Not OK
Reported by | Roger Jones |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comment Q318
1.5.1 | Tier 1 -Required hardware deployed |  | Roger Jones | Requested share, dymanic
1.5.2 | Tier 1 - Job success rates from ATLAS dashboard |  | Roger Jones | 0.95 | 0.949 | 0.978 | 0.939 | 0.938 | 0.973 | 0.964 | 0.952
1.5.3 | Tier 1 - Data availability from ATLAS dashboard |  | Roger Jones | 0.98 | 0.968 | 0.915 | 0.948 | 0.95 | 0.954 | 0.94 | 0.952 | This just fails the metric because the echo service is included and has lower efficiency |  |  | Problems with Castor | CASTOR is now the weak link; we are working on decommissioing the CASTOR instance | CASTPR to ECHO transition blurs the two systems
1.5.4 | Tier 1 - Data acceptance from Tier-0/1/2 - ATLAS SAM tests |  | Roger Jones | 0.98 | 0.968 | 0.98 | 0.96 | 0.95 | 0.978 | 0.966 | 0.953 |  |  | New data source from ATLAS; pulled down by transfers to ECHO | Broker-off periods for PANDA queue merger | As above
1.5.5 | Tier 1 - Data loss |  | Roger Jones | 0.01 | [9 empty] | Significant loss from ECHO | Data loss from Castor | Data loss from Castor |  | Planned loss of logfiles
2.1.1 | Tier 2 - Requested disk space deployed |  | Roger Jones | Requested share, dynamic
2.1.2 | Tier 2 - Production job success rates |  | Roger Jones | 0.95 | 0.938 | 0.99 | 0.925 | 0.943 | 0.952 | 0.932 | 0.927 |  |  |  | Numbers pulled down fro ScotGrid by Durham having a sub 90% rate |  | Scotgrid pulle down by ECDF and London by Brunel, both well sub-90%
2.1.3 | Tier 2 - Data availability from the ATLAS dashboard |  | Roger Jones | 0.95 | 0.941 | 0.963 | 0.955 | 0.972 | 0.975 | 0.959 | 0.966 | [6 empty] | Pulled down by issues at Bruel and ECDF
2.1.4 | Tier 2 - Data acceptance |  | Roger Jones | 0.95 | 0.971 | 0.96 | 0.91 | 0.965 | 0.966 | 0.935 | 0.929 |  |  | This is pulled down by a low data acceptance in SouthGrid; (Oxford) |  |  | Again, numbers notiably pulle down by ECDF and Brunel | Pulled down by Brunel, ECDF - and some issues at Sheffield
2.1.5 | Tier 2 - Data loss |  | Roger Jones | 0.05 | [12 empty] | Significant data loiss at Glasgow, but mainly recovered
2.1.6 | Tier 2 - ATLAS Available slots |  | Roger Jones | Requested share, dynamic
2.1.7 | Tier 2 - Atlas job success in production |  | Roger Jones |  |  |  | 0.925 | 0.943 |  | 0.932 | 0.927
2.1.8 | Tier 2 - ATLAS job success rate in user analysis |  | Roger Jones | 0.95 | 0.922 | 0.92 | 0.926 | 0.956 | 0.961 | 0.959 | 0.959 | Problems at Lancaster (where misconfigured jobs requested too much RAM) and Oxford for short periods | This is artificailly low because of a large number of miscomnfigured user jobs with very high memory requiremetns sent to one site.Hammercloud confirmed the site was not at fault | Still lwo because of misconfigured jobs to lancs and RHUL
Note on B16: gronbech: site only metric from PANDA dashboard
Note on B18: gronbech: via the Steve Lloyd page folded with the available storage (Peter Love page)
Note on B19: gronbech: Cedric's page

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | ATLAS |  |  | Overdue
Year | 2018 |  |  | Not yet due
Reported by | Roger Jones |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A5.6 | Report to PMB on delivery during the year | Roger Jones | 2016-12-01 | 2016-12-01 | OC Docs for Nov + PG Review SS
A5.7 | Report to PMB on delivery during the year | Roger Jones | 2017-12-01 | 2018-02-02 | OC Docs for Nov + PG Review SS
A5.8 | Report to PMB on delivery during the year | Roger Jones | 2018-12-01
A5.9 | Report to PMB on delivery during the year | Roger Jones | 2019-12-01

## Manpower Q1 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q2 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q4 2017
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1 | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q1 2018
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1
Total |  |  | 1 | 1 | 0 | 0 | 0 | 0

## Manpower Q2 2018
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1
RAL | ATLAS | Tim Adye |  |  | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2018
GridPP Quarterly Report
Area | ATLAS
Quarter | 2018 Q3
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | 1 | 1
RAL | ATLAS | Tim Adye |  |  | 1
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q117
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst/ Tim Adye | Worked mainly on the echo installation; the remaining time was on ipv6 and Frontier issues. Tim then was * Decommissioning Castor disk and reorganising PanDA queues * Improving xrootd access and transfers from ECHO * WebDAV transfer tests between many ATLAS sites * Started helping with ATLAS UK Cloud support * ATLAS Distributed Analysis shifts (DAST) * ATLAS Release Tester (ART) development for ITk
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q217
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | - Echo was a very large percentage of his work (as it entered production this quarter). - Quite a bit of work on was done on IPv6 stuff at the Tier 1. - He contributed to DynaFed and testing storage on Microsoft Azure. - WLCG Workshop in Manchester (He gave presentation on both Object Stores and IPv6 [tutorial]) - He attended ATLAS Software week in Valencia and did related work on Object Stores for the Event Service - He has been contributing to the WLCG data steering group, especially with respect to storage accounting. - Also did some work to help setup LIGO on S3. |  | While it is not a problem, and genrally useful to ATLAS, the level of non-ATLAS specific effort is high and could become a problem if ATLAS problems arise.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q317
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | August was taken with holiday and paternity leave. Object store benchmarking for ATLAS; presentation and preparation for pre-GDB on object stores. Project management for Echo; project management training.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q417
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2017
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Echo Project management, ipv6 deployment, some work on Object Stores for ATLAS, large scale CVMFS+DynaFed
Operations | Good work on data recovery after Castor losses |  | Castor data loss, some more minor Echo problems. Alastair had a period of illneess
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q118
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2018
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Echo management, ipv6, castro incident respoinse |  | Moved to T1 mamager position towards the end of the quarter; replacement not made until Q2
Operations | Further good work on castor recovery and migration to echo
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q218
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2018
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q318
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2018
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tim Adye | * Studying ATLAS CPU use of the Tier-1 and arrange ADC/Condor tweaks to improve our fair-share. We now have consistently ~100% fair-share. * Finished decommissioning Castor disk and plan reorganising PanDA queues. * Setup new Castor tape stager as test DDM endpoint and perform large-scale tape performance test for ATLAS "tape carousel" project. * Started work on developing xrootd+https third-party copy access for Echo. * Chairs ATLAS UK Cloud support meetings and help UK Cloud Squad. * ATLAS Distributed Analysis shifts (DAST).
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
CAP | 2011-
DPHEP Management group | 2012-
Other outputs and Knowledge | Date | Notes