## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q218 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 99% | 91% | 92% | 99% | 82% | 99% | 96% | 99% | [9 empty] | 99% | 99% | 90.67% | ECDF low availability due to non-updated site packages which affected tests but not work payloads. Durhams low availablity due to non-updated packages misflagged by a test.
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 100% | 91% | 92% | 99% | 82% | 99% | 96% | 99% | [9 empty] | 99% | 99% | 90.67%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 82% | 86% | 89.47% | 44% | 40% | 60.94% | 75% | 72% | 79.14% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 69% | 68% | 84.45%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 82% | 86% | 89.51% | 42% | 38% | 57.72% | 51% | 50% | 64.24% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 52% | 59% | 73.35%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q218
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 4Gb/s | 4Gb/s | DPM |  | Site | 2018-04-01 | 2018-05-01 | 2018-06-01 | Total |  | Site | 2018-04-01 | 2018-05-01 | 2018-06-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 29504152 | 31241649 | 28324208 | 89070009 |  | DURHAM | 29486542 | 31202818 | 28340472 | 89029832
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 3266534 | 3479671 | 5859000 | 12605205 |  | ECDF | 3479760 | 3741094 | 6088614 | 13309468
[8 empty] | GLASGOW | 26471675 | 31214399 | 31599562 | 89285636 |  | GLASGOW | 33841288 | 39091563 | 37063366 | 109996217
[8 empty] | ECDF-CS [1,2] | 1684000 | 1398000 | 1850000 | 4932000 |  | ECDF-CS [1,2] | 2342000 | 2647000 | 2545000 | 7534000
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 60926361 | 67333719 | 67632770 | 195892850 |  | Total | 69149590 | 76682475 | 74037452 | 219869517
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 89070009 | 46.64% | 2184 | 99503040 | 89.51% | 89.47%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 12605205 | 6.601% | 2184 | 21840000 | 57.72% | 60.94%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 89285636 | 46.76% | 2184 | 138996312 | 64.24% | 79.14%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 190960850 | 100% | 2184 | 260339352 | 73.35% | 84.45%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q218
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q218
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | T. Li | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | D Crooks | 1 | 1 | 0 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 3 | 3 | 2 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q218
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Shared Fail2Ban idea is working as a PoC; the ideal was presented by Paul Clark at the WLCG SoC meeting at CERN and was greeted with much praise. Local to Durham, there has been development work to HEPForge to migrate it to phabricator. Continued work with JISC and University IT (CIS) has moved the 10GB/s Network connection forwards and an end is in sight! |  | One of the disk servers has had a wobble (Disk02) and has been taken offline; there is no known data loss, this system will be evaluated and either retired or reinstated depending on the results of testing.
ECDF | Increase of our Eddie ringfence allocation to >1,000 cores. Rolled out initial prometheus/grafana site monitoring ahead of CHEP to support ongoing studies. Hired James Perry for data management prototype work |  | Increased pressure to reduce rackspace at Advanced Computing Facility
GLASGOW | A building warrant has been issued for the construction of the new Data Centre which will allow construction to commence. All worker nodes were successfully upgraded to UMD-4 in this report period as well as 50% of VAC nodes being upgraded to VAC 3.0.1. This allows extended support to a wider range of smaller VOs. A test sytem with Containerised WN using the autopilot has been setup, with inital results given in a poster at CHEP 2018. |  | Staff loss (David Crooks) means some projects which have been ongoing are now on hold and may need to be cancelled.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Operational continuity concerns with upcoming machine room server move. Out of warranty network switch. ACF Power outage during August |  | Regular meetings with University Research Services to formulate smooth machine room change. Request for new switch equipment pending Preparing for power outage to reduce potential impact
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction in Mid 2018
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy development MISP/Bro integration |  | 2018-06-30 |  | On hold due to Staff movement.
Glasgow: Migrate to UMD-4 on all WNs |  | 2018-06-30 |  | All worker nodes migrated to UMD-4
ECDF: XCache performance study |  | 2018-06-30 |  | Performance study is done, and results are reported at CHEP 2018
ECDF: Deploy RDF Storage for smaller VOs |  | 2018-06-30 |  | New RDF storage registered with GridPP DIRAC instance
ECDF: Improved monitoring |  | 2018-06-30 |  | New Jobs and site portal for monitoring site performance
ECDF: Automated Audit |  | 2018-06-30 |  | Auto-generated wiki summary of site hardware/layout
Durham: Researching and Developing an OpenShift Origin Cluster to investigate it's viability in the GRID environment. |  | 2018-06-30 |  | On hold due to other projects taking up time.
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-06-30 |  | Brought forward, initial test/proof of concept was discussed at the WLCG SoC.
Durham: 10Gb/s Network Connectivity *Optimistic Date* |  | 2018-06-30 |  | Brought Forward.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-06-30 |  | Brought Forward.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Researching and Developing an OpenShift Origin Cluster to investigate it's viability in the GRID environment. |  | 2018-09-30 |  | Bringing forward but probably no serious work forwards during this quarter due to other projects.
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-09-30 |  | Requires a more substantial development path to make the system more robust. See GitHub (https://github.com/bulgemonkey/Shared-Fail2Ban) for development.
Durham: 10Gb/s Network Connectivity *Optimistic Date* |  | 2018-07-07 |  | Should have the new connectivity activated on the 7th July.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-09-30 |  | Will have working Reverse IPv6 DNS
Durham: Testing Site Firewall Idea |  | 2018-09-30 |  | Will have a working firewall for the grid.
Glasgow: Evaluate feasabily of migrating off of DPM as a storage technology |  | 2018-09-30 |  | Selected a technology and developed plans.
Glasgow: Deploy Prometheus as a production monitoring system, decommision Graphite. |  | 2018-09-30 |  | Prometheus endpoint set up.
Glasgow: Migrate Puppet WN configuration to Ansible |  | 2018-09-30 |  | Configure new WN via ansible rather than puppet.
ECDF: RUCIO cache study |  | 2018-09-30 |  | Deploy the RUCIO cache server and integrate it to ATLAS workflow. Study the RUCIO Name2Name plugin.
ECDF: Improve Middleware Monitoring |  | 2018-09-30 |  | Finish exporter to monitor middleware performance/stability via prometheus
ECDF: Job scheduling analytics |  | 2018-09-30 |  | Build upon scheduling analytics and simulation studies created for CHEP contribution
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via Ganga/DIRAC
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
David Crooks,GridPP Security Officer, RAL |  | 2018-05-28 |  | David has left ot become the GridPP security officer.
Dissemination events |  | Date |  | Notes
WLCG Soc, Paul Clark |  | 2018-06-29 |  | Paul presented the proof of concept and idea for Durhams Shared Fail2Ban system.
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
WLCG Traceability WG [was Traceability & Isolation] |  | Present |  | David Crooks
WLCG SOC Working Group |  | Present |  | co-lead by David Crooks
EGI Software Vulnerability Group |  | Present |  | David Crooks
UK NGI Security Team |  | Present |  | David Crooks
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A