## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q318 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW | [11 empty] | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 99% | 91% | 97% | 99% | 82% | 92% | 96% | 99% | 99% | [9 empty] | 99% | 100% | 96%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 91% | 97% | 99% | 82% | 92% | 96% | 99% | 99% | [9 empty] | 99% | 100% | 96%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 86% | 89% | 89.02% | 40% | 61% | 127.1% | 72% | 79% | 78.67% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 68% | 84% | 90.53%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 86% | 90% | 89.12% | 38% | 58% | 122.9% | 50% | 64% | 61.29% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 59% | 73% | 77.1%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q318
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | Site | 2018-07-01 | 2018-08-01 | 2018-09-01 | Total |  | Site | 2018-07-01 | 2018-08-01 | 2018-09-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 31079692 | 30961892 | 27609281 | 89650865 |  | DURHAM | 31108748 | 30908627 | 27538276 | 89555651
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 9423614 | 9091336 | 8631426 | 27146376 |  | ECDF | 9706827 | 9452962 | 8914757 | 28074546
[8 empty] | GLASGOW | 27534761 | 30293334 | 28295417 | 86123512 |  | GLASGOW | 35529959 | 38077161 | 36943766 | 110550886
[8 empty] | ECDF-CS [1,2] | 2729000 | 3191000 | 2659000 | 8579000 |  | ECDF-CS [1,2] | 3107000 | 3664000 | 3327000 | 10098000
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 70767067 | 73537562 | 67195124 | 211499753 |  | Total | 79452534 | 82102750 | 76723799 | 238279083
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 89650865 | 44.18% | 2208 | 100596480 | 89.12% | 89.02%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 27146376 | 13.38% | 2208 | 22080000 | 122.9% | 127.1%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 86123512 | 42.44% | 2208 | 140523744 | 61.29% | 78.67%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 202920753 | 100% | 2208 | 263200224 | 77.1% | 90.53%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q318
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q318
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | T. Li | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | J. Perry (EPCC) | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 2.2 | 2.2 | 2.2 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q318
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Moved to DMLite. Gained 10GB/s WAN Link. |  | IPv6 Networking Issues; Issue with route out of the University/JISC, this was repaired as soon as it was discovered. DPM Pool Disk Failure; Drained disk, reported file loss to PhenoGrid and ATLAS. DPM Authentication issues; upgraded to DMLite. Free-IPA LDAP Issue; Underlying certificates were renewed manually.
ECDF | RDF problems are fixed. ATLAS RDF queue is set online. DUNE VO is enabled. |  | Enabling IPv6 caused problems to the site, will dicuss with the system admin for dual-stacking the whole storage. Ongoing issues with getting RDF storage to be used by ATLAS. Currently have ~175Tb of storage in use of >600Tb space.
GLASGOW | Work began on provisioning hardware for and design of a new cluster to be created and migrated to the KDC. Ansible roles created for repeated tasks, and structures put in place for using these instead of ad-hoc commands. |  | Enabling IPv6 continues to be an issue, aim still to meet end of year deadline for PerfSonar & Storage. Loss of staff has meant a slow down in completing some tasks, such as reinstallation of PerfSonar.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Operational continuity concerns with upcoming machine room server move. Out of warranty network switch. |  | Regular meetings with University Research Services to formulate smooth machine room change. Request for new switch equipment pending
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction, completeion scheduled July 2019
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Researching and Developing an OpenShift Origin Cluster to investigate it's viability in the GRID environment. |  | 2018-09-30 |  | On Hold
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-09-30 |  | Proof of Concept was success full.
Durham: 10Gb/s Network Connectivity *Optimistic Date* |  | 2018-07-07 |  | Great Success! We have 10Gbs WAN Link!
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-09-30 |  | University IT are discussing with JaNET/JISC.
Durham: Testing Site Firewall Idea |  | 2018-09-30 |  | Still ongoing testing, Transparent mode didn't give enough throughput. Static NAT to be tested.
Glasgow: Evaluate feasabily of migrating off of DPM as a storage technology |  | 2018-09-30 |  | Ongoing work to set up new CEPH testbed
Glasgow: Deploy Prometheus as a production monitoring system, decommision Graphite. |  | 2018-09-30 |  | Ongoing small scale testing with pool of WNs succesful, need now to scale out
Glasgow: Migrate Puppet WN configuration to Ansible |  | 2018-09-30 |  | Initial testing complete, highlighted limitiations in current ansible set up which need to be thought through to progress.
ECDF: RUCIO cache study |  | 2018-09-30 |  | On hold for ATLAS as the use case is not clear. Will continue study with the rucio test instance in Edinburgh.
ECDF: Improve Middleware Monitoring |  | 2018-09-30 |  | Have improved node/grafana monitoring systems to incorporate automatic alerting of pending issues.
ECDF: Job scheduling analytics |  | 2018-09-30 |  | Have interactive grafana dashboard showing jobs/cpu-usage across the site vs VO and job type.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Testing Site Firewall Idea - Static NAT |  | 2018-12-31 |  | Working Firewall
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-12-31 |  | Will have working IPv6 Reverse DNS
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-12-31 |  | Shared Fail2Ban will be written in Python.
Durham: Test CentOS7 Worker Nodes |  | 2018-12-31 |  | *Some* Worker nodes in test for CentOS7.
Glasgow: Deploy Prometheus as a production monitoring system, decommision Graphite. |  | 2018-12-31 |  | Scale up small test, and include in new cluster deployment
Glasgow: Set up Ceph testbed |  | 2018-12-31 |  | Test system which can be used for load testing, operation testing and integration with Grid Systems
Glasgow: Initial new cluster design created for Data Centre migration |  | 2018-12-31 |  | Design of new cluster to be migrated to KDC
ECDF: Data caching study |  | 2018-12-31 |  | Test rucio cache with the test rucio instance in Edinburgh; Optimize the opptunistic cache based on ATLAS data access analytics; Study sub-file cache.
ECDF: Server room movement |  | 2018-11-30 |  | Shall move kit within the ACF server room with minimal interuption to services
ECDF: Initial Object-store/EOS study |  | 2018-12-31 |  | Initial study into lightweight EOS install at a Tier2 and potential technologies to integrate Grid software with object stores.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via Ganga/DIRAC
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
DUNE |  | Ongoing |  | Agreed to host the DUNE UK computing workshop in Edinburgh (October 8th and 9th) Provided effort into DUNE Rucio Prototype Evaluation
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
Technology Choices, GridPP41 |  | 2018-08-30 |  | Presented on Technology Choices for GridPP6 at the GridPP41 collaboration meeting.
File Catalogue/Information Forward look, GridPP41 |  | 2018-08-30 |  | Presented on File Catalogue/Information as part of storage forward look for GridPP6 at GridPP41
A data caching model for Tier-2 WLCG computing centres using XCache |  | 2018-07-09 |  | Presented at CHEP 2018 Conference, Sofia, Bulgaria
Many hands make light work: Experiences from a shared resource WLCG Tier-2 computing site |  | 2018-07-09 |  | Presented at CHEP 2018 Conference, Sofia, Bulgaria
Using ZFS to manage Grid storage and improve middleware resilience |  | 2018-07-09 |  | Presented at CHEP 2018 Conference, Sofia, Bulgaria
Monitoring LHCb Trigger developments using nightly integration tests and a new interactive web UI |  | 2018-07-09 |  | Presented at CHEP 2018 Conference, Sofia, Bulgaria
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Member of WLCG DOMA-Access WG |  | Present |  | Teng Li
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A