## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q418 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 91% | 97% | 100% | 82% | 92% | 53% | 99% | 99% | 97% | [9 empty] | 99% | 100% | 83.33% | Delay in updating lcg-CA causing tests to fail but didn't impact running jobs
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 91% | 97% | 100% | 82% | 92% | 53% | 99% | 99% | 97% | [9 empty] | 99% | 100% | 83.33%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 86% | 89% | 89.1% | 40% | 61% | 119.8% | 72% | 79% | 74.05% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 68% | 84% | 85.57%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 86% | 90% | 89.39% | 38% | 58% | 107% | 50% | 64% | 57.14% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 59% | 73% | 73.65%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q418
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | Site | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total |  | Site | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 29261997 | 26654840 | 34006970 | 89923807 |  | DURHAM | 29137657 | 26629289 | 33867331 | 89634277
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 8239140 | 7328160 | 8057443 | 23624743 |  | ECDF | 8914666 | 8531340 | 9007797 | 26453803
[8 empty] | GLASGOW | 26030548 | 28718193 | 25551084 | 80299825 |  | GLASGOW | 34634626 | 34799187 | 34626325 | 104060138
[8 empty] | ECDF-CS [1,2] | 2222000 | 1535000 | 0 | 3757000 |  | ECDF-CS [1,2] | 3082000 | 1997000 | 0 | 5079000
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 65753685 | 64236193 | 67615497 | 197605375 |  | Total | 75768949 | 71956816 | 77501453 | 225227218
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 89923807 | 46.39% | 2208 | 100596480 | 89.39% | 89.1%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 23624743 | 12.19% | 2208 | 22080000 | 107% | 119.8%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 80299825 | 41.42% | 2208 | 140523744 | 57.14% | 74.05%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 193848375 | 100% | 2208 | 263200224 | 73.65% | 85.57%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q418
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q418
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
Edinburgh | R. Currie | 0.25 | 0.25 | 0.25 | 0 | 0 | 0
Edinburgh | T. Li | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | J. Perry (EPCC) | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 2.45 | 2.45 | 2.45 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q418
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Repaired a faulty disk server (disk02) which is ready to be brought back online. Brought new rack and nodes online. Restructured production networking. Replaced various disk server failed drives. |  | Some older nodes are starting to fail, attempting to locate spares. Disk Server LACP/Bonding Issues, Bonding refuses to work correctly on a single host. CentOS7 migration is going slower than expected.
ECDF | Migrated servers within ACF data center. Re-balanced storage to cope with loss of physical servers. Have new switch in place and all traffic appears OK. Re-factored Tier3 servers in JCMB to act as new RUCIO/storage development environment and test bed. |  | Loss of expertise due to Andy leaving. Reduced disk servers potentially exposes us to lhigh load per server. Experiencing potential load related issues with RDF storage which needs investigation. Ongoing scalability issues with university openstack cluster impacting our roadmap to migrate our WN.
GLASGOW | New staffing with the arrival of Emanuale Simili. Initial IPv6 deployment within main cluster environment succesful, reverse DNS testes and found to be working. Data Centre construction on track with only 1 week slippage in program, July 2019 still completion data. Design of new cluster in progress with main design complete. |  | IPv6 problems associated with ingress bandwidth, needs interaction with Central IT to help complete Aged disk estate beginning to fail in line with deprecation plans.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Operational continuity concerns with upcoming machine room server move. Senior admin with most experience has left. |  | Regular meetings with University Research Services to formulate smooth machine room change. Meetings to pass on knowledge/contacts for future work. Job advert being placed to look for replacement.
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction, completeion scheduled July 2019
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Testing Site Firewall Idea - Static NAT |  | 2018-12-31 |  | No work done on this.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-12-31 |  | Still Waiting University IT, discussion started with JISC/JaNET.
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-12-31 |  | Progress has been made on converting the basic funcationality to Python, some issues were found with SELinux Contexts that were resolved.
Durham: Test CentOS7 Worker Nodes |  | 2018-12-31 |  | Node successfully built after significant work to modify our Puppet Build Process
Glasgow: Deploy Prometheus as a production monitoring system, decommision Graphite. |  | 2018-12-31 |  | Ongoing, not yet complete
Glasgow: Set up Ceph testbed |  | 2018-12-31 |  | Testbed exists, still evaluating.
Glasgow: Initial new cluster design created for Data Centre migration |  | 2018-12-31 |  | Design complete, centred around 3 new Hypervisors, HTCondor, ARC-CE. Still awaiting decision on Storage solution
ECDF: Data caching study |  | 2018-12-31 |  | Simulated all GridPP sites and reported in ALTAS week.
ECDF: Server room movement |  | 2018-11-30 |  | Servers now behind a new switch which has warranty. Reduced number of physical servers means less manpower required to maintain them.
ECDF: Initial Object-store/EOS study |  | 2018-12-31 |  | This is ongoing but the initial results are that EOS is unlike DPM in quite a few regards which requires paying attention as to how it's deployed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy Prometheus as a production monitoring system, decommision Graphite. |  | 2018-03-31 |  | New system functional
Glasgow: Complete PerfSonar Migration to CentOS7 |  | 2018-03-31 |  | Working CentOS7 PerfSonar
Durham: Testing Site Firewall Idea - Static NAT |  | 2018-03-31 |  | Working Firewall with Static NAT.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-03-31 |  | Working Reverse IPv6 DNS.
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-03-31 |  | Working Shared Fail2Ban Module using the default Python engine.
Durham: Test CentOS7 Worker Nodes |  | 2018-03-31 |  | CentOS7 Nodes and work ready to rollout cluster wide.
Durham: New Disk Server Online |  | 2018-03-31 |  | More storage space available via DPM.
Durham: Refirbished Disk Server Online |  | 2018-03-31 |  | More storage space available via DPM.
ECDF: IPV6 main storage |  | 2018-03-31 |  | Going to bite the bullet and go IPv6 across the main ATLAS storage asap in 2019. Preferabbly after DPM 1.11 to go DOME+IPv6
ECDF: Bring up new production CE |  | 2018-03-31 |  | Bringing up 2nd newer CE which is on our own servers which removes our dependence on vmware servers provided by uni.
ECDF: Interview for new Admin |  | 2018-03-31 |  | Hopefully interview for replacement for missing admin post.
ECDF: Data caching study |  | 2018-03-31 |  | Study sub-file cache performance of XCache.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via Ganga/DIRAC
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
DUNE |  | Ongoing |  | Agreed to host the DUNE UK computing workshop in Edinburgh (October 8th and 9th) Provided effort into DUNE Rucio Prototype Evaluation
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
ATLAS Software Quality Coordinator |  | Present |  | Andrew Washbrook
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Member of WLCG DOMA-Access WG |  | Present |  | Teng Li
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A