## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q119 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW | [11 empty] | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 97% | 100% | 98% | 92% | 53% | 91% | 99% | 97% | 97% | [9 empty] | 100% | 83% | 95.33%
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 97% | 100% | 98% | 92% | 53% | 91% | 99% | 97% | 97% | [9 empty] | 100% | 83% | 95.33% | ECDF availability was impacted by power outages at ACF facility. Certain VOs impacted more than others when site came back.
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 89% | 89% | 78.57% | 61% | 120% | 117.2% | 79% | 74% | 59.47% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 84% | 86% | 71.61%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 90% | 89% | 78.59% | 58% | 107% | 104.6% | 64% | 57% | 48.81% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 73% | 74% | 64.88% | CPU utilisation at Glasgow impacted by power outage and associated 5 day downtime.
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q119
Reported by | Gareth Roy
(ECDF-CS has been 0 for Q1 2019 due to networking failure in Q4 2018 and pending replacement hardware being required to address issue)
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total |  | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 33910803 | 23536955 | 19889750 | 77337508 |  | DURHAM | 33817500 | 23651353 | 19850121 | 77318974
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 7780597 | 6296645 | 8526408 | 22603650 |  | ECDF | 9007824 | 7233783 | 9081927 | 25323534
[8 empty] | GLASGOW | 24925186 | 22995754 | 19183737 | 67104677 |  | GLASGOW | 30444303 | 28415621 | 22890028 | 81749952
[8 empty] | ECDF-CS [1,2] | 0 | 0 | 0 | 0 |  | ECDF-CS [1,2] | 0 | 0 | 0 | 0
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 66616586 | 52829354 | 47599895 | 167045835 |  | Total | 73269627 | 59300757 | 51822076 | 184392460
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 77337508 | 46.3% | 2160 | 98409600 | 78.59% | 78.57%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 22603650 | 13.53% | 2160 | 21600000 | 104.6% | 117.2%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 67104677 | 40.17% | 2160 | 137468880 | 48.81% | 59.47%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 167045835 | 100% | 2160 | 257478480 | 64.88% | 71.61%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q119
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q119
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | R. Currie | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | T. Li | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | J. Perry (EPCC) | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | E. SImili | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 4 | 4 | 4 | 0.2 | 0.2 | 0.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q119
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Developing and updating our CentOS7 Puppet Deplyment for our CentOS7 Tests. We have rolled out a test Shared Fail2Ban System with highly successful results within the DURHAM site. We have added more nodes and a new dpm disk server. |  | We tested our Firewall with Static NAT (After a transparent firewall test). This ws a successful test but a poor outcome, with performance being lower than the expected 10Gb/s. As such we have dropped this firewall idea. We've had a few issues with DPM, mainly due to the way it is packaged, adding a dome adaptor into the configuration even though we do not use dome. This is causing DPM to fail to operate correctly once it updates.
ECDF | We dual stacked main DPM storage. DPM storage monitoring was enabled. We built an XCache monitoring system based on ELK stack. Retired SL6 queue at site in favor of expanding our cloud scheduler footprint. We finished interviewing the new postdoc. |  | ARC ce has been unstable due to the machine is not fully controllable by us due to unknown reasons. Infrastructure which is running on HV we don't have direct control over exposes us to problems and amplifies issues.
GLASGOW | New Proxmos hypervisor set up and configured to allow build out of new Cluster components. New provisioning systems setup along with DNS, DHCP, NAT and other nework infrastructure. CEPH Hardware commissioned and ready for development work. Initial pool of WN hardware added to test system to allow deployment of CentOS7 WN. |  | Still issues with bandwidth related to IPv6 Power outage and associated problems led to 5 days lost activity, impacting used CPU time.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Operational continuity concerns with upcoming machine room server move. Senior admin with most experience has left. |  | Regular meetings with University Research Services to formulate smooth machine room change. Adding additional documentation as experience/expertise has been regenerated.
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction, completeion scheduled July 2019
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Deploy Prometheus as a production monitoring system, decommision Graphite. |  | 2018-03-31 |  | Ongoing, new hypervisor built. Delayed due to Hardware procurement
Glasgow: Complete PerfSonar Migration to CentOS7 |  | 2018-03-31 |  | Completed
Durham: Testing Site Firewall Idea - Static NAT |  | 2018-03-31 |  | Tested, no improvement on throughput. We highly suggest not using Ubiquti Edge Router Infinity for Firewalling. There is no ASIC for packet inspection and as such anything other than simple routing is software.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-03-31 |  | *ha* No changes yet.
Durham: Research, Develop and eventually deploy a shared Fail2Ban System |  | 2018-03-31 |  | System is developed, working towards a more robust documentation, packaging and sharing method.
Durham: Test CentOS7 Worker Nodes |  | 2018-03-31 |  | Tested and working towards implementing/rolling out CentOS 7 over all systems.
Durham: New Disk Server Online |  | 2018-03-31 |  | Disk07 is online.
Durham: Refirbished Disk Server Online |  | 2018-03-31 |  | No progress
ECDF: IPV6 main storage |  | 2018-03-31 |  | main storage is now dual stacked
ECDF: Bring up new production CE |  | 2018-03-31 |  | Still in progress
ECDF: Interview for new Admin |  | 2018-03-31 |  | Interviewing was done. The candidate is waiting for the visa process.
ECDF: Data caching study |  | 2018-03-31 |  | Some results are gathered and reported at GridPP42. Helping Birmingham based on that
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Plan for Data Centre Migration |  | 2018-06-30 |  | Detailed plan with milestones
Glasgow: Test instance of HTCondor-CE |  | 2018-06-30 |  | Sucessfully running jobs (Atlas)
Glasgow: Test instance of CEPH storage |  | 2018-06-30 |  | Succssfully transfered test data
Durham: Deploy CentOS7 Worker Nodes, CEs, UIs |  | 2018-06-30 |  | We will have all of our worker nodes running CentOS 7, as well as our local VO UIs and our ARC CEs.
Durham: Refirbished Disk Server Online |  | 2018-06-30 |  | Bring Disk02 online.
Durham: Improve Test Development and better document a shared Fail2Ban System |  | 2018-06-30 |  | We will have a shard Fail2Ban platform ready to distribute to ScotGRID sites.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2018-06-30 |  | Lets see if we can get anywhere with this. *sigh*
ECDF: Bring up the new CE |  | 2018-06-30 |  | Bring up a new ARC-CE instance as a replacement for ce8. Retire ce8. Evaluate HTCondor as a replacement technology.
ECDF: XCache monitoring service |  | 2018-06-30 |  | Try to integrate Birmingham's XCache instance into the service and study performance
ECDF: Hire new postdoc |  | 2018-06-30 |  | Get prepared for the new postdoc starting
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via Ganga/DIRAC
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
DUNE |  | Ongoing |  | Agreed to host the DUNE UK computing workshop in Edinburgh (October 8th and 9th) Provided effort into DUNE Rucio Prototype Evaluation
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Member of WLCG DOMA-Access WG |  | Present |  | Teng Li
Member of LHCb RTA |  | Present |  | Robert Currie
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A