## Summary
Ref. | Risk Description | Owner | Inherent Risk |  |  | Residual Risk
|  |  | Likelihood | Impact | Total | Likelihood | Impact | Total
1 | Castor Storage System Problems | AD | 4 | 3 | 12 | 7 | 3 | 21
2 | Tier-1 Tape service replacement | AD | 6 | 5 | 30 | 5 | 5 | 25
3 | Outage of UK T1 | AD | 4 | 6 | 24 | 1 | 5 | 5
4 | Failure of T1 to meet SLA or MoU | AD | 7 | 5 | 35 | 4 | 5 | 20
5 | Significant loss of custodial data at the T1 | AD | 6 | 8 | 48 | 5.5 | 5 | 27.5
6 | Loss or damage to hardware at T1 >£2M | AD | 0.5 | 10 | 5 | 0.5 | 10 | 5
7 | Disaster at T1 leads to prolonged outage | AD | 0.5 | 8 | 4 | 0.5 | 7 | 3.5
8 | Recruitment retention problems at RAL | DK | 9 | 6 | 54 | 8 | 5 | 40
9 | Failure to procur, deploy or operate hardware | AD,GR | 6 | 7 | 42 | 4 | 6.5 | 26
10 | Insufficient Network Bandwidth | PC | 6 | 5 | 30 | 5 | 5 | 25
11 | Over contention for resources | DB | 6 | 6 | 36 | 5 | 6 | 30
12 | Increased non-LHC use | DB | 5 | 5 | 25 | 3 | 5 | 15
13 | Capital vs Resource at the Tier-1 | DB | 8 | 6 | 48 | 5 | 5 | 25
14 | Technology Mismatch | DC | 2 | 5 | 10 | 1 | 5 | 5
15 | Loss of experienced personnel at T2s | SL | 7 | 5 | 35 | 6 | 4.5 | 27
16 | Insufficient funding at T2s for h/w | SL | 2 | 4 | 8 | 2 | 3 | 6
17 | Tier-2s are not fit for purpose | SL | 4 | 6 | 24 | 1 | 6 | 6
18 | Expt. s/w runs poorly on the grid | PG | 7 | 6 | 42 | 5 | 5 | 25
19 | Security problem affecting reputation | DK | 7 | 8 | 56 | 4 | 7 | 28
20 | Loss of GridPP service due to security | DK | 7 | 5 | 35 | 5 | 5 | 25
21 | Insufficient VO/user support effort | PG | 7 | 5 | 35 | 7 | 5 | 35
22 | Mismatch between budget and hardware costs | DB | 9 | 7 | 63 | 6 | 7 | 42
23 | Core service funding insuffcient | DB | 5 | 4 | 20 | 4 | 2 | 8
24 | Breakdown of NGI/EGI infrastructure | JC | 3 | 3 | 9 | 3 | 3 | 9
25 | Insufficient travel funds | DK | 4 | 2.5 | 10 | 3 | 2.5 | 7.5
26 | GridPP resources prove insufficient for actual requirements. | PG | 10 | 7 | 70 | 6 | 4 | 24
27 | Critical middleware no longer supported | DC | 5 | 6 | 30 | 4 | 6 | 24
28 | Unplanned infrastructure costs | PG | 2.5 | 3 | 7.5 | 2 | 2 | 4
29 | Loss of EGI.eu | DB | 4 | 3 | 12 | 3 | 2 | 6
30 | Financial Uncertainty | DB | 5 | 6 | 30 | 5 | 6 | 30
31 | Conflicting opinions amongst GridPP stakeholders | DB | 3 | 5 | 15 | 3 | 5 | 15
32 | Failure of achieving further intergration within PPAN community | JC | 4 | 6 | 24 | 4 | 6 | 24

## GRIDPP5 Risk Register
[7 empty] | Total risk is product of Likelihood and Impact | [6 empty] | Project Title: GridPP5
[7 empty] | 25 - 50 | medium | [5 empty] | Project Manager: Gareth Roy
[7 empty] | 0 - 25 | low
[7 empty] | 50 - 100 | high
[14 empty] | 2019-04-23 |  | T1 | T2 | Project | Operational | Reputational | Financial
Ref. | Risk Description | Short Name | Work-package | Potential impact on project | Owner | Inherent Risk |  |  | Existing Controls | Current and proposed mitigation | Residual Risk |  |  | Action Required | Change since last review
[6 empty] | Likelihood | Impact | Total |  |  | Likelihood | Impact | Total
1 | CASTOR storage system may suffer from degraded availability or inadequate performance | Castor Storage System Problems | 1 | Experiments would be unable to keep up with data rate from CERN or other sites. Service may be unable to handle planned level of reprocessing or analysis. | AD | 4 | 3 | 12 | Reliability good but some indication of performance related problems at high transaction rates. extensive testing infrastructure. Close liaison with CERN. Pro-active monitoring. Change control system. Limit number of major upgrades. Close liaison with experiments. Resilient architecture. | Continue to extend testing. Pro-active approach to advanced testing of new use cases. Increase priority of development of alternative solution. Impact will decline as CEPH project progresses. | 7 | 3 | 21 |  | Major users migrated. Migration of remaining users progressing well. As CEPH is now successful CASTOR has significantly less storage associated with is so liklehood of failure reduced. | x |  |  | x | x
2 | Replacement Tier-1 Tape service to replace CASTOR may not be in place before CASTOR support ends. | Tier-1 Tape service replacement | 1 | 1. CASTOR support from CERN will end with it's refocus on EOS as a storage solution. This will mean and end to software updates for the CASTOR Tape service. 2. At present no alternative has been identified so project runs a risk of hitting a software/security issue which will not be patched when support ends 3. Lack of development effort in GridPP6 may slow implementation of Tier-1 service | AD | 6 | 5 | 30 | Software development expertise held within Tier-1 that can be used to continue CASTOR support, ongoing effort in developing and deploying a new Tier-1 Tape service. | Identify and develop a new Tier-1 tape service. | 5 | 5 | 25 |  | Added at this review | x |  |  | x | x | x
3 | Outage of the UK T1 for 1 week or more (cooling failure, network failure etc) | Outage of UK T1 | 1 | Tier-1 would not be able to operate and would be unable to meet MoU commitments. Knock on effect on UK Tier-2s. | AD | 4 | 6 | 24 | Well tested disaster management system will initiate prompt remedial action. Staff prepared to work overtime. Resilient network connectivity and cooling system. UPS. Environment monitoring and callout system. | Continue to progress a secondary disaster recovery site in the ATLAS centre able to provide a limited number of critical services. Tier-2s could work with other Tier-1s if required. Some fall back services are provided by the Tier-2s. | 1 | 5 | 5 | Extend a number of critical services to have a presence in more than one building. |  | x |  |  | x | x
4 | Failure of T1 to meet WLCG MoU service level commitments for availability/responsivness | Failure of T1 to meet SLA or MoU | 1 | Due to falling staff levels at the Tier-1 it becomes increasingly difficult to respond in a timely manner. In the event of a major failure (rather than a slight technical failure) experiments would be unable to carry out their full program of work at the Tier-1. We may suffer reputational damage. | AD | 7 | 5 | 35 | Production team and callout system. Disaster management system. Resilient, segmented infrastructure. Performance metrics. Change control system. Well established hardware procurement system with reserve capacity to handle short term procurement delays. | Much of the work of the team is directed towards ensuring MoU commitments are met. Production team will continue to enhance the services ability to respond rapidly and effectively to problems. Increase further the emphasis on change management and testing. Improve ability to carry out transparent interventions, by architecture, virtualisation and instancing improvements. | 4 | 5 | 20 |  | 4a h/w b service level | x |  |  | x | x
5 | Significant loss of custodial data at the T1 | Significant loss of custodial data at the T1 | 1 | Reputational damage. Although copies are usually held elsewhere in the world copying back to RAL may be operationally problematic or even in extreme cases impossible. | AD | 6 | 8 | 48 | Metadata catalogue backups and live off site copy. Checksums. Media recovery procedures. | Extensive disaster recovery testing. Routine data dipsticking/validation. Regular media repacking. | 5.5 | 5 | 27.5 |  | slight rise due to oracle risk on Castor tape. | x |  |  | x | x
6 | Substantial loss of or damage to hardware at the T1 (Fire, flood, theft, flooring failure, cooling failure …) hardware damage exceeding £2m | Loss or damage to hardware at T1 >£2M | 1 | Could not meet MoU commitments. Corrective action would be impossible within existing funding and when funded may take many months to carry out. | AD | 0.5 | 10 | 5 | Building access control system and physical protection. Environment monitoring, automated shutdown and callout system. Fire alarm and fire suppression system. Cooling system resilience. Disaster management system. | Ensure close liaison with site services to pre-empt weaknesses when they are identified in the infrastructure. Develop a secondary disaster recovery site in the ATLAS centre. | 0.5 | 10 | 5 |  |  | x |  |  | x | x | x
7 | Significant disaster at the Tier-1, leading to prolonged outage (fire, flood, JANET unavailable for long period, etc.) | Disaster at T1 leads to prolonged outage | 1 | Very long term outage of the Tier-1: UK unable to meet its commitments to wLCG over substantial period | AD | 0.5 | 8 | 4 | Environment monitoring and callout system to stop problems becoming critical. Other wLCG Tier-1s take over services. | Resilient site network paths and infrastructure. Attempt to associate UK Tier-2s with other Tier-1s now a possibility owing to improved network infrastructure. | 0.5 | 7 | 3.5 |  |  | x |  |  | x | x | x
8 | Failure to retain or recruit key technical staff at RAL | Recruitment retention problems at RAL | 1,3 | Inability to meet GridPP deliverables and milestones because of lack of staff | DK | 9 | 6 | 54 | Ensure that STFC management are aware of problems when/if they occur | Well documented processes & procedures for key systems are used to share essential knowledge. This allows technical staff to have the minimum knowledge required to ensure critical systems stay online and at a minimum level of operation, in the case of a loss of expertise. Staff given appropriate ownership of key systems, recognition within STFC and opportunities to share key personal successes within the GridPP community (at collaboration and other meetings). Use of apprenticeships and internship where appropriate to help fill the recruitment pipeline. | 8 | 5 | 40 |  |  | x |  |  | x
9 | Failure to procur, deploy or operate hardware at GridPP sites | Failure to procur, deploy or operate hardware | 1,2 | Problems with procurement such as late delivery or other supplier related issues. Large batches of h/w could fail acceptance testing or develop faults during production use. Significant reduction in capacity could adversly affect GridPP's abilitiy to meet the WLCG MoU commitments. | AD,GR | 6 | 7 | 42 | 1. Monitoring of available disk space/cpu utilisation. 2. Procurements take account of experiment requests. 3.Track hardware failures and observe trends. 4. Documented clear recovery procedures. 5. Throughly test new hardware prior to deployment. 6. Changes in site procurement policy 7. PMB oversight of procurement at GridPP sites. | If jobs do not require site specific data then redirect them to other sites. If data is required then replicate it elsewhere and run jobs. Run a fast procurement to increase capacity - if not a short term effect. Close liason with instituional procurements teams. | 4 | 6.5 | 26 |  | Modified at this review to explicitely include procurement. | x | x |  | x
10 | Insufficient Network bandwidth delivered | Insufficient Network Bandwidth | 1,2 | Lack of bandwidth would prevent data flowing from the Tier 0, & 1 and onto the Tier 2s at a rate sufficient to process the data at required speeds. | PC | 6 | 5 | 30 | The Tier1 has a failover link for the LHCOPN. Tier-2s are liaising with JANET to upgrade links at major sites. | Exploit second OPN link if nesseccary, Tier-2s are generally well connected and GridPP has good communications links with JANET/JISC. Actual measured throughput should deliver as expected. | 5 | 5 | 25 | Third link to CERN installed, current bandwidth is suffcient. Firewall bypassed for storage but may hamper traffic from WNs. | RAL site improved, New FW, IPv6 deployed, 100gbps,however OPN may require further upgrades | x | x | x | x
11 | Over contention for Resources | Over contention for resources | 1,2 | Resources are so heaviliy used that conflicts arise between major VOs. | DB | 6 | 6 | 36 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Purchase more hardware and/or improve profiling and procurement.Reduce non-LHC experiment resources. Agree programme priorities through PMB and STFC. | 5 | 6 | 30 |  |  |  | x | x | x | x
12 | Unexpected resource requirements by non-LHC VOs | Increased non-LHC use | 1,2 | Mandated non-LHC VOs have increased usage requirement that cause conflict with LHC usage. | DB | 5 | 5 | 25 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Look at supporting non-LHC VOs from other funding opportunities such as IRIS fundining. | 3 | 5 | 15 |  |  |  | x | x | x | x
13 | Difficulty with STFC budgets due to Capital vs Resource limitations | Capital vs Resource at the Tier-1 | 1,2 | The Split of funding between Capital and Resource, can cause problems due to the changing classification of computer equipment | DB | 8 | 6 | 48 | Quarterly review of Tier 1 spending situation. Salaries are always classed as resource, but the boundary for equipment purchases makes predicting the capital requirement difficult. | Increase communications with STFC to ensure plan is appropriate. | 5 | 5 | 25 | Classifying tape media as capital has made predicting Captial/Resource split easier. |  | x | x | x | x |  | x
14 | Technology Shifts - WLCG expts exploit new technology not supported at GridPP sites. | Technology Mismatch | 1,2 | New developments in technology (eg multi core CPUs) cause mismatch between experiment processing requirements and available hardware. | DC | 2 | 5 | 10 | New technology directions are closely monitored by involvement in research work groups on Cloud computing, Virtualization, and HEPIX. Changes are expected by the end of the project. GridPP technology group meets regularly. | Work packages invest some small fraction of effort directly on new technologies with a view to bringing them mainstream when both mature enough and appropriate to the overall project. WLCG TEGs and WLCG TDR update. | 1 | 5 | 5 |  |  |  | x | x | x
15 | Loss of experienced personnel or insufficient manpower at T2s | Loss of experienced personnel at T2s | 2 | Sites may not be able to diagnose and fix problems as quickly. Ability to react to changing situations or to upgrade will be compromised. | SL | 7 | 5 | 35 | GridPP5 staffing levels now known. Multiple Tier-2s provide resilience to the project. | Two people at main sites. Grid Operations team spreads knowledge and expertise across sites. New models of working adopted to cope with falling staff levels at smaller sites. | 6 | 4.5 | 27 |  |  |  | x |  | x
16 | Insufficient funding to meet hardware commitments at T2s | Insufficient funding at T2s for h/w | 2 | Less hardware available to meet international obligations and user expectations. | SL | 2 | 4 | 8 | Funding models are different at different sites. Not all sites would be affected the same way and some sites may be able to add resources to compensate. | Encourage opportune use of more central resources. Encourage experiments to prioritise and make more efficient use of resources. | 2 | 3 | 6 |  |  |  | x |  |  |  | x
17 | Middleware or software at T2 sites cannot deal with the challenges of on-demand user analysis | Tier-2s are not fit for purpose | 2,3 | User analysis compromised. | SL | 4 | 6 | 24 | The same middleware and software is used at T1 and T2 sites across the world. wLCG will work with experiments to solve problems. | Establishment of data management group with manpower to deal with storage, movement and replication | 1 | 6 | 6 |  |  |  | x |  | x
18 | Experiment software runs inefficiently on the grid, to the detriment of UK physicists | Expt. s/w runs poorly on the grid | 3 | Workload would not be able to fully exploit the resources available. Expts would need to invest effort in improved computing model. | PG | 7 | 6 | 42 | Experiments have reviewed computing models in preparation for run 2. Special arrangements are made for certain customers. | Experiment support posts and the grid support team will be available to all sites. Good dialogue with special customers required to ensure appropriate planning. | 5 | 5 | 25 | Recent ineffciencies with CMS code at the Tier-1 in particular. Team has been setup to investigate, DC to lead. |  |  |  | x | x
19 | Reputation risk due to a serious security problem | Security problem affecting reputation | 3 | Security problems may bring down the whole of GridPP or even wLCG, given that all Sites run very similar software. A major outage is likely to attract significant outside interest and GridPP is likely to suffer damage to its reputation. Threats rising and ability to deal with is decreasing and impact on operations is rising | DK | 7 | 8 | 56 | Act on many fronts in parallel to handle vulnerabilities to avoid incidents, to contain and handle incidents quickly when they do happen and define and enforce appropriate policies to control actions of participants. | We lead the Joint Security Policy Group of wLCG/EGI, the security vulnerability group of EGI . Established experienced security team in place. Many staff have recently recieved security training. | 4 | 7 | 28 | Recent widely publicised incidents are a cause for concern, even though our resources run different OS's. We are a big target. Continued good practice and close vigilance is required. |  |  |  | x |  | x
20 | Non-availability of T1 &2 service or compromised data due to security vulnerability | Loss of GridPP service due to security | 3 | Extended service downtime, loss of data, inability to process and analyse data. | DK | 7 | 5 | 35 | Well organised operational security incident handling led by the GridPP Security Officer in collaboration with the Tier 1 and Tier 2 system managers. Vulnerabilities in the middleware are handled today by EGI to prevent incidents happening | The GridPP security effort is essential to reduce the risks from known security vulnerabilities, to handle incidents when they do occur, to train system managers, to define and encourage security best practice, e.g. timely system patching, and to continuously monitor the status. Many staff have recently recieved security training. | 5 | 5 | 25 | Service have to be taken down to perform critical updates. Recent BIOS bugs are hard to fix. Systems admin effort is decreasing so outages may be longer. |  |  |  | x | x
21 | Insufficient effort to support the VOs or the users | Insufficient VO/user support effort | 3 | New user groups (VOs) or users of the main LHC VOs are not able to make use of the Grid to do their research. | PG | 7 | 5 | 35 | Dedicated experiment support post at the Tier-1 and Tier-2 s for LHC Vos however an increase in non LHC VOS could stretch resources. Extensive Web documentation. User Coordinator can liaise with the experimental users. | Tier-1 resource meeting with the User Coordinator provides a forum to discuss new user requirements. GridPP-Support mailing list setup to coordinate help to new users. | 7 | 5 | 35 | increased number of VOs now supported, but effort available is limited. |  |  |  | x | x | x
22 | Mismatch between budget and hardware costs | Mismatch between budget and hardware costs | 4 | Project would not be able to deliver the pledged resources resulting in (a) political damage and eventually (b) disadvantage to the UK experiments as the level of resource falls | DB | 9 | 7 | 63 | Monitor UK purchases for last 10 years and extrapolate | Cross check with CERN predictions but there is a residual exchange rate uncertainty on top of the technological uncertainty. | 6 | 7 | 42 | Still very high, post BREXIT exchange rate fluxtuations etc. Monitor the situation closely. | Slight reduction thanks to STFC capital allocation. |  |  | x |  |  | x
23 | Funding for central services that GridPP relys on insufficiently funded. | Core service funding insuffcient | 4 | Resources within the NGI on which GridPP is planning to rely are not available. For example, the Certificate Authority is not funded or has inadequate effort to meet GridPP needs. | DB | 5 | 4 | 20 | Close collaboration with STFC to ensure GridPP is aware of progress and any issues. | Call on GridPP contingency to fund extra posts to cover the core staff. | 4 | 2 | 8 |  |  |  |  | x |  |  | x
24 | Breakdown of core operations structures - for example in the NGI/EGI infrastructure | Breakdown of NGI/EGI infrastructure | 4 | Without a central ticketing (GGUS) interface or Grid Operations database the ability to follow up on problems, inform of upcoming downtimes and general communications between sites and users is interrupted. | JC | 3 | 3 | 9 | Core services are hosted on high-availability hardware. The GOCDB has a failover capability to another region. | NGI structure in place and the existing central instances serve as a backup. After the transition the UK instances will be placed on high resilience equipment and procedures put in place for rapid deployment of new services. | 3 | 3 | 9 |  |  |  |  | x | x |  | x
25 | Insufficient travel funds for effective engagement and contribution to wLCG and for internal operation of GridPP. | Insufficient travel funds | 4 | GridPP would experience difficulty in keeping up with developments in operations, in updating staff skills (through attendance at technical meetings) and in keeping up to date with experiment requirements. | DK | 4 | 2.5 | 10 | Careful management of resources and prioritisation to ensure sufficient travel funds are available | Increase the use of phone and video conferencing for attending meetings (though noting such facilities are not always available and they are frequently less optimal than attendance in person). | 3 | 2.5 | 7.5 |  | note exchange rate problems makes the likelihod higher |  |  | x | x |  | x
26 | GridPP resources prove insufficient for actual requirements. | GridPP resources prove insufficient for actual requirements. | 4 | Inability of UK to meet experiment requirements and UK disadvantaged in LHC data analysis. | PG | 10 | 7 | 70 | Regular tuning of experiment requirements against resources through User Board. WLCG constrained by flat cash for run II. | Long range and short range planning through User Board and Ops-Team using LHC schedule. Seek additional funding to cover requirements outside the scope of the original proposal. | 6 | 4 | 24 | LHC Global requirements have increased significantly above expectations.Aim to meet 100% of uplift. |  |  |  | x |  | x
27 | Critical middleware no longer supported | Critical middleware no longer supported | 4 | The significant Grid middleware code base needs to be properly maintained and supported throughout the project. The development community is now reduced to a skeleton staff and maintenance problems can arise especially with data management components. | DC | 5 | 6 | 30 | Existing GGUS mechanisms enable bug reporting by sysadmins to a small number of expert developers. Data support staff enable appropriate deployment choices, workarounds and bug fixes to be made. | Culture of fully-tested code and minimal change established. Maintenance of expertise and support staff in recognised critical areas. Reductions in functionality, if necessary. Community based support model in process of being established. | 4 | 6 | 24 | Some issues with loss of Globus support. However the problem and solution is share with WLCG. | LFC gridftp being phased out, questions about DPM future. CASTOR support declining. |  |  | x | x
28 | Unplanned infrastructure costs | Unplanned infrastructure costs | 4 | If extra costs arise at the T1 or T2, there is the possibility that funds will not be sufficient to buy the required hardware. Risks failing to meet WLCG pledge, and reputation risk. | PG | 2.5 | 3 | 7.5 | Tier-2 costs spread across sites - if one site cannot meet the price GridPP is paying, then other sites can increase their share. Increasing risk of electricity costs or networking costs. | GridPP contingency available for extra costs at the Tier-1 or systematic increases at the Tier-2s. | 2 | 2 | 4 |  |  |  |  | x |  |  | x
29 | EGI does not continue or the UK does not continue to be a member. | Loss of EGI.eu | 4 | Access to services run by EGI, Loss of co funding for services run within the UK. Loss of access to future funding oportunities, such as Horizon 2020. | DB | 4 | 3 | 12 | Essential posts are part of the GridPP5. Possible BREXIT implications. | Call on GridPP contingency to fund necessary posts. Reallocate work to other staff if possible. | 3 | 2 | 6 |  | sligjht increase |  |  | x | x |  | x
30 | Financial Uncertainty | Financial Uncertainty | 4 | Uncertainties can make staff retention difficult. Lack of long term funding would result in inadequate resources and service being provided to serve the needs of the UK Particle Physics Community. | DB | 5 | 6 | 30 | GridPP5 funding approved but still longer term uncertainities with Government funding. | Raise issues with GridPP Oversight Committee and directly with STFC | 5 | 6 | 30 |  |  |  |  | x |  |  | x
31 | Conflicting opinions amongst GridPP stakeholders | Conflicting opinions amongst GridPP stakeholders | 4 | Disatisfaction amoungst users or site administrators could result in reduced utilisation of the resources and adversly affect the quality of research carried out. | DB | 3 | 5 | 15 | 1. Weekly PMB meetings. PMB minutes widely circulated to members of the community. Operations and sites meetings held weekly, with good coomunication between the PMB and the OPS team via cross membership. Collaboration meetings held regularly. | More F2F meetings, More CB meetings, Sites visits. | 3 | 5 | 15 |  |  |  |  | x | x | x
32 | Failure of achieving further intergration within PPAN community | Failure of achieving further intergration within PPAN community | 4 | GridPP does not benefit from shared infrastructure cost savings. Reputational damage, and lack of endorsement that the GridPP infrastructure service is relevant to a wider community. | JC | 4 | 6 | 24 | Invest effort in engagement with a wide range of new communities. Requires investment in time, which was not funded. | Small steps have been made, now working with several new communities. Perhaps not progressing as fast as we would like. | 4 | 6 | 24 |  | IRIS, progress. |  |  | x |  | x
Note on B14: Peter Gronbech: Outage caused by the problem
Note on B25: gronbech: ALICE s/w incompatibilities causes extra cost
Note on B38: gronbech: Consider deleting

## Risk OC Format
| RISK REGISTER |  |  |  | Total risk is product of Likelihood and Impact | [7 empty] | Project Title: | GridPP5
[5 empty] | 0 - 25 | Low | [6 empty] | Project Manager: | Peter Gronbech
[5 empty] | 25 - 50 | Medium
[5 empty] | 50 - 100 | High | [6 empty] | Last Update: | 2019-04-23
[5 empty] | 0 | Retired
Ref. | Risk Description | Potential impact on project | Owner | Inherent Risk |  |  | Existing Controls | Current/Proposed mitigation | Residual Risk |  |  | Risk Exposure |  |  | Action Required
|  |  |  | Likelihood | Impact | Total |  |  | Likelihood | Impact | Total | Change | description | Cost (£k)
1 | CASTOR storage system may suffer from degraded availability or inadequate performance | Experiments would be unable to keep up with data rate from CERN or other sites. Service may be unable to handle planned level of reprocessing or analysis. | AD | 4 | 3 | 12 | Reliability good but some indication of performance related problems at high transaction rates. extensive testing infrastructure. Close liaison with CERN. Pro-active monitoring. Change control system. Limit number of major upgrades. Close liaison with experiments. Resilient architecture. | Continue to extend testing. Pro-active approach to advanced testing of new use cases. Increase priority of development of alternative solution. Impact will decline as CEPH project progresses. | 7 | 3 | 21 | p
2 | Replacement Tier-1 Tape service to replace CASTOR may not be in place before CASTOR support ends. | 1. CASTOR support from CERN will end with it's refocus on EOS as a storage solution. This will mean and end to software updates for the CASTOR Tape service. 2. At present no alternative has been identified so project runs a risk of hitting a software/security issue which will not be patched when support ends 3. Lack of development effort in GridPP6 may slow implementation of Tier-1 service | AD | 6 | 5 | 30 | Software development expertise held within Tier-1 that can be used to continue CASTOR support, ongoing effort in developing and deploying a new Tier-1 Tape service. | Identify and develop a new Tier-1 tape service. | 5 | 5 | 25 | q |  |  | 0
3 | Outage of the UK T1 for 1 week or more (cooling failure, network failure etc) | Tier-1 would not be able to operate and would be unable to meet MoU commitments. Knock on effect on UK Tier-2s. | AD | 4 | 6 | 24 | Well tested disaster management system will initiate prompt remedial action. Staff prepared to work overtime. Resilient network connectivity and cooling system. UPS. Environment monitoring and callout system. | Continue to progress a secondary disaster recovery site in the ATLAS centre able to provide a limited number of critical services. Tier-2s could work with other Tier-1s if required. Some fall back services are provided by the Tier-2s. | 1 | 5 | 5 | q |  |  | Extend a number of critical services to have a presence in more than one building.
4 | Failure of T1 to meet WLCG MoU service level commitments for availability/responsivness | Due to falling staff levels at the Tier-1 it becomes increasingly difficult to respond in a timely manner. In the event of a major failure (rather than a slight technical failure) experiments would be unable to carry out their full program of work at the Tier-1. We may suffer reputational damage. | AD | 7 | 5 | 35 | Production team and callout system. Disaster management system. Resilient, segmented infrastructure. Performance metrics. Change control system. Well established hardware procurement system with reserve capacity to handle short term procurement delays. | Much of the work of the team is directed towards ensuring MoU commitments are met. Production team will continue to enhance the services ability to respond rapidly and effectively to problems. Increase further the emphasis on change management and testing. Improve ability to carry out transparent interventions, by architecture, virtualisation and instancing improvements. | 4 | 5 | 20 | q |  |  | 0
5 | Significant loss of custodial data at the T1 | Reputational damage. Although copies are usually held elsewhere in the world copying back to RAL may be operationally problematic or even in extreme cases impossible. | AD | 6 | 8 | 48 | Metadata catalogue backups and live off site copy. Checksums. Media recovery procedures. | Extensive disaster recovery testing. Routine data dipsticking/validation. Regular media repacking. | 5.5 | 5 | 27.5 | q |  |  | 0
6 | Substantial loss of or damage to hardware at the T1 (Fire, flood, theft, flooring failure, cooling failure …) hardware damage exceeding £2m | Could not meet MoU commitments. Corrective action would be impossible within existing funding and when funded may take many months to carry out. | AD | 0.5 | 10 | 5 | Building access control system and physical protection. Environment monitoring, automated shutdown and callout system. Fire alarm and fire suppression system. Cooling system resilience. Disaster management system. | Ensure close liaison with site services to pre-empt weaknesses when they are identified in the infrastructure. Develop a secondary disaster recovery site in the ATLAS centre. | 0.5 | 10 | 5 | tu |  |  | 0
7 | Significant disaster at the Tier-1, leading to prolonged outage (fire, flood, JANET unavailable for long period, etc.) | Very long term outage of the Tier-1: UK unable to meet its commitments to wLCG over substantial period | AD | 0.5 | 8 | 4 | Environment monitoring and callout system to stop problems becoming critical. Other wLCG Tier-1s take over services. | Resilient site network paths and infrastructure. Attempt to associate UK Tier-2s with other Tier-1s now a possibility owing to improved network infrastructure. | 0.5 | 7 | 3.5 | q |  |  | 0
8 | Failure to retain or recruit key technical staff at RAL | Inability to meet GridPP deliverables and milestones because of lack of staff | DK | 9 | 6 | 54 | Ensure that STFC management are aware of problems when/if they occur | Well documented processes & procedures for key systems are used to share essential knowledge. This allows technical staff to have the minimum knowledge required to ensure critical systems stay online and at a minimum level of operation, in the case of a loss of expertise. Staff given appropriate ownership of key systems, recognition within STFC and opportunities to share key personal successes within the GridPP community (at collaboration and other meetings). Use of apprenticeships and internship where appropriate to help fill the recruitment pipeline. | 8 | 5 | 40 | q |  |  | 0
9 | Failure to procur, deploy or operate hardware at GridPP sites | Problems with procurement such as late delivery or other supplier related issues. Large batches of h/w could fail acceptance testing or develop faults during production use. Significant reduction in capacity could adversly affect GridPP's abilitiy to meet the WLCG MoU commitments. | AD,GR | 6 | 7 | 42 | 1. Monitoring of available disk space/cpu utilisation. 2. Procurements take account of experiment requests. 3.Track hardware failures and observe trends. 4. Documented clear recovery procedures. 5. Throughly test new hardware prior to deployment. 6. Changes in site procurement policy 7. PMB oversight of procurement at GridPP sites. | If jobs do not require site specific data then redirect them to other sites. If data is required then replicate it elsewhere and run jobs. Run a fast procurement to increase capacity - if not a short term effect. Close liason with instituional procurements teams. | 4 | 6.5 | 26 | q |  |  | 0
10 | Insufficient Network bandwidth delivered | Lack of bandwidth would prevent data flowing from the Tier 0, & 1 and onto the Tier 2s at a rate sufficient to process the data at required speeds. | PC | 6 | 5 | 30 | The Tier1 has a failover link for the LHCOPN. Tier-2s are liaising with JANET to upgrade links at major sites. | Exploit second OPN link if nesseccary, Tier-2s are generally well connected and GridPP has good communications links with JANET/JISC. Actual measured throughput should deliver as expected. | 5 | 5 | 25 | q |  |  | Third link to CERN installed, current bandwidth is suffcient. Firewall bypassed for storage but may hamper traffic from WNs.
11 | Over contention for Resources | Resources are so heaviliy used that conflicts arise between major VOs. | DB | 6 | 6 | 36 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Purchase more hardware and/or improve profiling and procurement.Reduce non-LHC experiment resources. Agree programme priorities through PMB and STFC. | 5 | 6 | 30 | q |  |  | 0
12 | Unexpected resource requirements by non-LHC VOs | Mandated non-LHC VOs have increased usage requirement that cause conflict with LHC usage. | DB | 5 | 5 | 25 | Quarterly review of resources and priorities at Resource Meetings. Weekly review of storage resources at Castor meetings. Ability to redefine intra-experiment CPU fairshares at short notice. | Look at supporting non-LHC VOs from other funding opportunities such as IRIS fundining. | 3 | 5 | 15 | q |  |  | 0
13 | Difficulty with STFC budgets due to Capital vs Resource limitations | The Split of funding between Capital and Resource, can cause problems due to the changing classification of computer equipment | DB | 8 | 6 | 48 | Quarterly review of Tier 1 spending situation. Salaries are always classed as resource, but the boundary for equipment purchases makes predicting the capital requirement difficult. | Increase communications with STFC to ensure plan is appropriate. | 5 | 5 | 25 | q |  |  | Classifying tape media as capital has made predicting Captial/Resource split easier.
14 | Technology Shifts - WLCG expts exploit new technology not supported at GridPP sites. | New developments in technology (eg multi core CPUs) cause mismatch between experiment processing requirements and available hardware. | DC | 2 | 5 | 10 | New technology directions are closely monitored by involvement in research work groups on Cloud computing, Virtualization, and HEPIX. Changes are expected by the end of the project. GridPP technology group meets regularly. | Work packages invest some small fraction of effort directly on new technologies with a view to bringing them mainstream when both mature enough and appropriate to the overall project. WLCG TEGs and WLCG TDR update. | 1 | 5 | 5 | q |  |  | 0
15 | Loss of experienced personnel or insufficient manpower at T2s | Sites may not be able to diagnose and fix problems as quickly. Ability to react to changing situations or to upgrade will be compromised. | SL | 7 | 5 | 35 | GridPP5 staffing levels now known. Multiple Tier-2s provide resilience to the project. | Two people at main sites. Grid Operations team spreads knowledge and expertise across sites. New models of working adopted to cope with falling staff levels at smaller sites. | 6 | 4.5 | 27 | q |  |  | 0
16 | Insufficient funding to meet hardware commitments at T2s | Less hardware available to meet international obligations and user expectations. | SL | 2 | 4 | 8 | Funding models are different at different sites. Not all sites would be affected the same way and some sites may be able to add resources to compensate. | Encourage opportune use of more central resources. Encourage experiments to prioritise and make more efficient use of resources. | 2 | 3 | 6 | q |  |  | 0
17 | Middleware or software at T2 sites cannot deal with the challenges of on-demand user analysis | User analysis compromised. | SL | 4 | 6 | 24 | The same middleware and software is used at T1 and T2 sites across the world. wLCG will work with experiments to solve problems. | Establishment of data management group with manpower to deal with storage, movement and replication | 1 | 6 | 6 | q |  |  | 0
18 | Experiment software runs inefficiently on the grid, to the detriment of UK physicists | Workload would not be able to fully exploit the resources available. Expts would need to invest effort in improved computing model. | PG | 7 | 6 | 42 | Experiments have reviewed computing models in preparation for run 2. Special arrangements are made for certain customers. | Experiment support posts and the grid support team will be available to all sites. Good dialogue with special customers required to ensure appropriate planning. | 5 | 5 | 25 | q |  |  | Recent ineffciencies with CMS code at the Tier-1 in particular. Team has been setup to investigate, DC to lead.
19 | Reputation risk due to a serious security problem | Security problems may bring down the whole of GridPP or even wLCG, given that all Sites run very similar software. A major outage is likely to attract significant outside interest and GridPP is likely to suffer damage to its reputation. Threats rising and ability to deal with is decreasing and impact on operations is rising | DK | 7 | 8 | 56 | Act on many fronts in parallel to handle vulnerabilities to avoid incidents, to contain and handle incidents quickly when they do happen and define and enforce appropriate policies to control actions of participants. | We lead the Joint Security Policy Group of wLCG/EGI, the security vulnerability group of EGI . Established experienced security team in place. Many staff have recently recieved security training. | 4 | 7 | 28 | q |  |  | Recent widely publicised incidents are a cause for concern, even though our resources run different OS's. We are a big target. Continued good practice and close vigilance is required.
20 | Non-availability of T1 &2 service or compromised data due to security vulnerability | Extended service downtime, loss of data, inability to process and analyse data. | DK | 7 | 5 | 35 | Well organised operational security incident handling led by the GridPP Security Officer in collaboration with the Tier 1 and Tier 2 system managers. Vulnerabilities in the middleware are handled today by EGI to prevent incidents happening | The GridPP security effort is essential to reduce the risks from known security vulnerabilities, to handle incidents when they do occur, to train system managers, to define and encourage security best practice, e.g. timely system patching, and to continuously monitor the status. Many staff have recently recieved security training. | 5 | 5 | 25 | q |  |  | Service have to be taken down to perform critical updates. Recent BIOS bugs are hard to fix. Systems admin effort is decreasing so outages may be longer.
21 | Insufficient effort to support the VOs or the users | New user groups (VOs) or users of the main LHC VOs are not able to make use of the Grid to do their research. | PG | 7 | 5 | 35 | Dedicated experiment support post at the Tier-1 and Tier-2 s for LHC Vos however an increase in non LHC VOS could stretch resources. Extensive Web documentation. User Coordinator can liaise with the experimental users. | Tier-1 resource meeting with the User Coordinator provides a forum to discuss new user requirements. GridPP-Support mailing list setup to coordinate help to new users. | 7 | 5 | 35 | tu |  |  | increased number of VOs now supported, but effort available is limited.
22 | Mismatch between budget and hardware costs | Project would not be able to deliver the pledged resources resulting in (a) political damage and eventually (b) disadvantage to the UK experiments as the level of resource falls | DB | 9 | 7 | 63 | Monitor UK purchases for last 10 years and extrapolate | Cross check with CERN predictions but there is a residual exchange rate uncertainty on top of the technological uncertainty. | 6 | 7 | 42 | q |  |  | Still very high, post BREXIT exchange rate fluxtuations etc. Monitor the situation closely.
23 | Funding for central services that GridPP relys on insufficiently funded. | Resources within the NGI on which GridPP is planning to rely are not available. For example, the Certificate Authority is not funded or has inadequate effort to meet GridPP needs. | DB | 5 | 4 | 20 | Close collaboration with STFC to ensure GridPP is aware of progress and any issues. | Call on GridPP contingency to fund extra posts to cover the core staff. | 4 | 2 | 8 | q |  |  | 0
24 | Breakdown of core operations structures - for example in the NGI/EGI infrastructure | Without a central ticketing (GGUS) interface or Grid Operations database the ability to follow up on problems, inform of upcoming downtimes and general communications between sites and users is interrupted. | JC | 3 | 3 | 9 | Core services are hosted on high-availability hardware. The GOCDB has a failover capability to another region. | NGI structure in place and the existing central instances serve as a backup. After the transition the UK instances will be placed on high resilience equipment and procedures put in place for rapid deployment of new services. | 3 | 3 | 9 | tu |  |  | 0
25 | Insufficient travel funds for effective engagement and contribution to wLCG and for internal operation of GridPP. | GridPP would experience difficulty in keeping up with developments in operations, in updating staff skills (through attendance at technical meetings) and in keeping up to date with experiment requirements. | DK | 4 | 2.5 | 10 | Careful management of resources and prioritisation to ensure sufficient travel funds are available | Increase the use of phone and video conferencing for attending meetings (though noting such facilities are not always available and they are frequently less optimal than attendance in person). | 3 | 2.5 | 7.5 | q |  |  | 0
26 | GridPP resources prove insufficient for actual requirements. | Inability of UK to meet experiment requirements and UK disadvantaged in LHC data analysis. | PG | 10 | 7 | 70 | Regular tuning of experiment requirements against resources through User Board. WLCG constrained by flat cash for run II. | Long range and short range planning through User Board and Ops-Team using LHC schedule. Seek additional funding to cover requirements outside the scope of the original proposal. | 6 | 4 | 24 | q |  |  | LHC Global requirements have increased significantly above expectations.Aim to meet 100% of uplift.
27 | Critical middleware no longer supported | The significant Grid middleware code base needs to be properly maintained and supported throughout the project. The development community is now reduced to a skeleton staff and maintenance problems can arise especially with data management components. | DC | 5 | 6 | 30 | Existing GGUS mechanisms enable bug reporting by sysadmins to a small number of expert developers. Data support staff enable appropriate deployment choices, workarounds and bug fixes to be made. | Culture of fully-tested code and minimal change established. Maintenance of expertise and support staff in recognised critical areas. Reductions in functionality, if necessary. Community based support model in process of being established. | 4 | 6 | 24 | q |  |  | Some issues with loss of Globus support. However the problem and solution is share with WLCG.
28 | Unplanned infrastructure costs | If extra costs arise at the T1 or T2, there is the possibility that funds will not be sufficient to buy the required hardware. Risks failing to meet WLCG pledge, and reputation risk. | PG | 2.5 | 3 | 7.5 | Tier-2 costs spread across sites - if one site cannot meet the price GridPP is paying, then other sites can increase their share. Increasing risk of electricity costs or networking costs. | GridPP contingency available for extra costs at the Tier-1 or systematic increases at the Tier-2s. | 2 | 2 | 4 | q |  |  | 0
29 | EGI does not continue or the UK does not continue to be a member. | Access to services run by EGI, Loss of co funding for services run within the UK. Loss of access to future funding oportunities, such as Horizon 2020. | DB | 4 | 3 | 12 | Essential posts are part of the GridPP5. Possible BREXIT implications. | Call on GridPP contingency to fund necessary posts. Reallocate work to other staff if possible. | 3 | 2 | 6 | q |  |  | 0
30 | Financial Uncertainty | Uncertainties can make staff retention difficult. Lack of long term funding would result in inadequate resources and service being provided to serve the needs of the UK Particle Physics Community. | DB | 5 | 6 | 30 | GridPP5 funding approved but still longer term uncertainities with Government funding. | Raise issues with GridPP Oversight Committee and directly with STFC | 5 | 6 | 30 | tu |  |  | 0
31 | Conflicting opinions amongst GridPP stakeholders | Disatisfaction amoungst users or site administrators could result in reduced utilisation of the resources and adversly affect the quality of research carried out. | DB | 3 | 5 | 15 | 1. Weekly PMB meetings. PMB minutes widely circulated to members of the community. Operations and sites meetings held weekly, with good coomunication between the PMB and the OPS team via cross membership. Collaboration meetings held regularly. | More F2F meetings, More CB meetings, Sites visits. | 3 | 5 | 15 | tu |  |  | 0
32 | Failure of achieving further intergration within PPAN community | GridPP does not benefit from shared infrastructure cost savings. Reputational damage, and lack of endorsement that the GridPP infrastructure service is relevant to a wider community. | JC | 4 | 6 | 24 | Invest effort in engagement with a wide range of new communities. Requires investment in time, which was not funded. | Small steps have been made, now working with several new communities. Perhaps not progressing as fast as we would like. | 4 | 6 | 24 | tu |  |  | 0
Notes:
Likelihood scale of 1 to 10, where 1 is low
Impact scale of 1 to 10, where 1 is low
Note on B15: gronbech: connected to Risk 18 – one is an operational risk (risk 19) and the other financial risk (Risk 18).
Note on B26: gronbech: ALICE s/w incompatibilities causes extra cost
Note on B39: gronbech: Consider deleting