## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q2 2019 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 116.6% | 116.6% | 140.4% | 178.3% | 178.3% | 186% | 140.2% | 140.2% | 144% | 183.6% | 183.6% | 172.8% | 170.1% | 170.1% | 171.7% | 189.2% | 189.2% | 179.5% | 158.1% | 158.1% | 165%
.x.2 | % of promised (by that time) CPU available | 100% | 248.4% | 248.4% | 274% | 218.9% | 218.9% | 215.6% | 308.6% | 308.6% | 176.3% | 240.4% | 240.4% | 215.1% | 239.5% | 239.5% | 213.2% | 206.5% | 206.5% | 181.9% | 240.6% | 240.6% | 216.7%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 40.15% | 70% | 42% | 100% | 99% | 100% | 99.11% | 99.11% | 100% | 100% | 99% | 100% | 99.35% | 95% | 93% | 96.18% | 95% | 99% | 89.13% | 92.85% | 89% | Bham decommisiioning …
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 51.15% | 70% | 42% | 100% | 99% | 100% | 99.11% | 99.11% | 100% | 100% | 95% | 100% | 99.35% | 95% | 93% | 96.18% | 95% | 99% | 90.97% | 92.19% | 89%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 73.75% | 77.18% | 68.96% | 54.11% | 59.1% | 59.01% | 94.71% | 103.3% | 111.9% | 75.24% | 85.72% | 75.25% | 87.6% | 91.54% | 97.41% | 64.39% | 70.37% | 67.37% | 77.89% | 83.98% | 82.34%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 34.92% | 67.71% | 59.55% | 24.53% | 44.99% | 36.53% | 79.4% | 79.08% | 84.12% | 60.95% | 78.74% | 67.48% | 53.28% | 65.53% | 73.4% | 55.72% | 59.17% | 60.15% | 51.01% | 67.61% | 65.7%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2019
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total |  | Site | 2019-01-01 | 2019-02-01 | 2019-03-01 | Total
Birmingham | UMD4 | VAC |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | UMD4 | EMI 3+UMD4 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 10066927.3301 | 8274342.1353 | 7937186.3961 | 26278455.8615 |  | Birmingham | 11670481.1434 | 9726201.0045 | 9037425.5053 | 30434107.6532
Cambridge | UMD 4/SL6 or C7 | UMD 4/SL6 or VAC/CS7 |  | 10Gb/s | 2*20Gb/s | DPM 1.10.3 |  | Bristol | 4617976.3133 | 5829908.4092 | 1316074.7439 | 11763959.4664 |  | Bristol | 7663655.7409 | 9385461.0306 | 1951195.4866 | 19000312.2581
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 5693875.1973 | 5586405.1026 | 5030961.9747 | 16311242.2746 |  | Cambridge | 7382027.8307 | 7580640.2229 | 6728680.1021 | 21691348.1557
RALPP | UMD4 | UMD3 |  | 2X10Gb/s | 100Gb/s | Dcache 3.2.41 |  | Oxford | 19819539.2912 | 17428167.6935 | 17031430.0321 | 54279137.0168 |  | Oxford | 21728562.9275 | 18898879.6479 | 19903107.2689 | 60530549.8443
Sussex | UMD4/EMI3 | UMD4 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 23517193.8513 | 24727050.5098 | 25977301.408 | 74221545.7691 |  | RALPP | 33497714.8305 | 31500793.8508 | 33496716.9327 | 98495225.614
[8 empty] | Sussex | 2954436.5628 | 2160939.8438 | 2220650.1534 | 7336026.56 |  | Sussex | 3191856.3177 | 2599315.185 | 2424421.4397 | 8215592.9424
[8 empty] | Total CPU hrs | 66669948.546 | 64006813.6942 | 59513604.7082 | 190190366.9484 |  | Total | 85134298.7907 | 79691290.9417 | 73541546.7353 | 238367136.4677
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2019) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | job efficiency
Birmingham | 20206 | 1000 | 7375 | 712 | 274% | 140.4% | 15.24% | 18.37% | 26278455.8615 | 13.82% | 2184 | 44129904 | 59.55% | 68.96% | 86.35%
Bristol | 14744 | 560 | 6839 | 301 | 215.6% | 186% | 11.12% | 10.28% | 11763959.4664 | 6.185% | 2184 | 32200896 | 36.53% | 59.01% | 61.91%
Cambridge | 8878 | 265 | 5035 | 184 | 176.3% | 144% | 6.698% | 4.867% | 16311242.2746 | 8.576% | 2184 | 19389552 | 84.12% | 111.9% | 75.2%
Oxford | 36832 | 940 | 17126 | 544 | 215.1% | 172.8% | 27.79% | 17.26% | 54279137.0168 | 28.54% | 2184 | 80441088 | 67.48% | 75.25% | 89.67%
RALPP | 46300 | 2610 | 21712 | 1520 | 213.2% | 171.7% | 34.93% | 47.93% | 74221545.7691 | 39.02% | 2184 | 101119200 | 73.4% | 97.41% | 75.36%
Sussex | 5584 | 70 | 3069 | 39 | 181.9% | 179.5% | 4.213% | 1.286% | 7336026.56 | 3.857% | 2184 | 12195456 | 60.15% | 67.37% | 89.29%
Totals | 132544 | 5445 | 61156 | 3300 | 216.7% | 165% | 100% | 100% | 190190366.9484 | 100% | 2184 | 289476096 | 65.7% | 82.34% | 79.79%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
[6 empty] | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
[10 empty] | Q4 | 2208
[5 empty] | Birmingham | 22433 | 980
[5 empty] | Bristol | 9607 | 0
[5 empty] | Cambridge | 5940 | 293
[5 empty] | Oxford | 26240 | 940
[5 empty] | RALPP | 42840 | 3079
[5 empty] | Sussex | 2006 | 83
Note on D30: gronbech: Sussex may have promised 2000 by email.?
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2019
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 14
Cambridge | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 23
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [7 empty] | 5
[47 empty] | 0 | 0
[47 empty] | 0 | 0
Total | 5 | 6 | 0 | 2 | 3 | 3 | 1 | 1 | 2 | 5 | 6 | 2 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 5 | 1 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 1 | 0 | 2 | 0 | 0 | 4 | 106
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 21.02% | 0%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 8.081% | 0.001822%
Cambridge | 0 | 185.7 | 0 | 0 | 0.096 | 0.027 | 0 | 0 | 0 | 0 | 0.004 |  | 0 | 0 | 0 | 0 | 0 | 0.206 | 0 |  | 0 | 0 | 0.448 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.35 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 189.831 | 3.994% | 1.94%
Oxford | 0 | 677 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 2.98 | 0.018 |  | 0.016 | 1.5 | 33.6 | 0 | 0 | 0.02285 | 716.9792 | 15.08% | 5.435%
RALPP | 0 | 642 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1353 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 326 |  | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0.7 | 8 | 0 | 0 | 0.65 | 2412.06 | 50.75% | 3.775%
Sussex |  | 50 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [10 empty] | 51.01 | 1.073% | 1.98%
Total | 999 | 1554.7 | 2 | 1 | 0.096 | 0.051 | 0 | 0 | 0 | 1738.11 | 0.311 | 0 | 0.049 | 0.73 | 0 | 0.129 | 0 | 0.2095 | 0.066 | 0 | 1.604 | 0 | 326.4538 | 0 | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063 | 0 | 0 | 1 | 3.35 | 2.98 | 0.018 | 0 | 0.046 | 2.2 | 41.6 | 0 | 0 | 0.67285 | 4752.9892 | 100% | 2.835%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q2 2019
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| Luke Kreczko | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Cambridge
| John Hill | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Oxford
| Vip Davda | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| Kashif Mohammad | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.8
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| Leo Rojas | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 2 | 2 | 2.3 | 1.7 | 1.7 | 1.7
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q2 2019
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | We are testing XCache for Atlas in order run with a small amount of storage. Everything is set up but waiting on final config settings on the ATLAS side. |  | Reaching the limit for air con in the server room so have started moving Tier3 machines to a different building to allow more Tier 2 usage of the space.
Bristol | vm00 replacement (vm03) in production, upgraded HDFS from 2.7 to 3.0.0, partial upgrade (schedulers, mangers & some worker nodes) to HTCondor 8.8 |  | Perfsonar: UoB IT support is very slow, transfer problems due to Imperial network change (blocked by firewall) [fixed]
Cambridge
Oxford | Retired SL6 queue and moved all worker nodes to CentOS7. Decommisioned the ovirt infrastructure. Migrated several VM's from this to our Vsphere setup. (bdii, Argus, AliceVObox…) Migrated Oxford VOMS server to Vmware vSphere. Added new Worker nodes. Dell 6400's (3 chassis 10 servers). Completed DPM to DOME migration |  | Kashif's last day was 28th June.
RALPP
Sussex
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: Upgrade to HTCondor 8.8 Due date: 31/31/2018 |  | 2019-12-31 |  | Partial upgrade to 8.8 (1 scheduler and two 7-OS WNs)
Bristol: New IPv6 perfsonar hosts |  | 31/06/2019 |  | BW & LAT ready but some issues with IPv6 and getting ports open
Bristol: Order New hardware to replace host vm00 |  | 2019-03-31 |  | Ordered & arrived
RALPP: Deploy New Hardware |  | 2018-03-31 |  | Complete, New disk and CPU installed and allocated
Oxford: Buy CPU from GridPP Hardware grant |  | 03/31/2019 |  | Purchased and installed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Make all Service Nodes Dual Stack |  | 2019-03-31
RALPP: Dual Sack the worker nodes |  | 2019-03-31
RALPP: Upgrade site-bdii to C7 |  | 2018-12-31 |  | On hold - awaiting clarity on the future of the BDII
RALPP: Join LHCONE |  | 2019-06-30
Bristol: Continue with upgrade to HTCondor 8.8 (CE, and debug issues) |  | 31/09/2019 |  | SL7 container jobs (via jobrouter)
Bristol: Completion of 7-OS IPv6 perfsonar BW+LAT |  | 31/09/2019 |  | All test passing
Bristol: decide on grant spending for WNs - GPUs? |  | 31/09/2019 |  | Ordered & arrived
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes