## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q219 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 305.8% | 371.3% | 371.3% | 388.2% | 606.6% | 606.6% | 352.1% | 352.1% | 352.1% | 131.6% | 131.6% | 131.6% |  |  |  | 300.5% | 374.8% | 374.8%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 275.9% | 258.6% | 258.6% | 375.1% | 375.1% | 375.1% | 604.7% | 604.7% | 592.8% |  |  |  | 363.9% | 356.7% | 354.8%
.x.3 | Average Nagios (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 95% | 83% | 63% | 100% | 98% | 99% | 100% | 94% | 100% | 97% | 100% | 99% |  |  |  | 98% | 93.75% | 90.25% | Brunel very low
.x.4 | Average Nagios (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 98% | 89% | 63% | 100% | 98% | 99% | 100% | 97% | 100% | 97% | 100% | 99% |  |  |  | 98.75% | 96% | 90.25% | Brunel very low
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 95.92% | 98.51% | 123.1% | 82.23% | 87.91% | 71.14% | 84.96% | 83.4% | 113.5% | 146.4% | 80.77% | 83% |  |  |  | 102.6% | 86.86% | 94.31% | Brunel + QMUL > 100%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 67.3% | 61.91% | 82.07% | 70.88% | 75.71% | 62.35% | 67.87% | 70.85% | 146.5% | 69.38% | 68.16% | 67.73% |  |  |  | 69.12% | 69.92% | 87.89% | QMUL > 100%
.x.3/.4
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q219
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2019 Apr | 2019 May | 2019 Jun | Total |  |  | 2019 Apr | 2019 May | 2019 Jun | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 100 Gb/s | dCache |  | UKI-LT2-Brunel | 19195862.415 | 18930685.7553 | 24606542.8183 | 62733091 |  | UKI-LT2-Brunel | 27635880.8346 | 30951067.99 | 35502472.9981 | 94089422
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 29323479.2127 | 28378707.4144 | 19463222.0458 | 77165409 |  | UKI-LT2-IC-HEP | 33424304.4237 | 33430012.9294 | 21186102.2823 | 88040420
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 47286371.9912 | 42634360.6967 | 55233975.7977 | 145154708 |  | UKI-LT2-QMUL | 40474560.9825 | 32988049.7942 | 38994978.6904 | 112457589
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 27256344.879 | 23982166.7286 | 22718030.2137 | 73956542 |  | UKI-LT2-RHUL | 32761725.0517 | 28271191.2538 | 29602719.098 | 90635635
[8 empty] | Total | 123062058 | 113925921 | 122021771 | 359009750 |  | Total | 134296471 | 125640322 | 125286273 | 385223066
https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2019/4/2019/6/all/localinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1700 | 9632.812 | 457.8006 | 363.3% | 371.3% | 18.71% | 10.64% | 62733091 | 17.47% | 2184 | 76440000 | 82.07% | 123.1% | 66.67%
UKI-LT2-IC-HEP | 56664 | 7969 | 21915.766 | 1313.8219 | 258.6% | 606.6% | 30.3% | 49.9% | 77165409 | 21.49% | 2184 | 123754176 | 62.35% | 71.14% | 87.65%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 24.25% | 31.31% | 145154708 | 40.43% | 2184 | 99072792 | 146.5% | 113.5% | 129.1%
UKI-LT2-RHUL | 50000 | 1300 | 8434.349 | 987.6466 | 592.8% | 131.6% | 26.73% | 8.14% | 73956542 | 20.6% | 2184 | 109200000 | 67.73% | 83% | 81.6%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 187027 | 15970 | 52714.598 | 4260.48 | 354.8% | 374.8% | 100% | 100% | 359009750 | 100% | 2184 | 408466968 | 87.89% | 94.31% | 93.2%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5362 | 64076 | 1757
UKI-LT2-IC-HEP | 5718 | 59582 | 7969
UKI-LT2-QMUL | 12320 | 149341 | 5031 | CPU capacity reporting is broken (need to get rid of SL6 and Cream CEs to fix it)
UKI-LT2-RHUL | 4624 | 48121 | 1400
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 321120 | 16157
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q219
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | atlas | biomed | calice | cepc | cernatschool.org | cms | comet.j-parc.jp | dteam | dune | enmr.eu | epic.vo.gridpp.ac.uk | gridpp | hone | hyperk.org | icecube | ilc | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | ops | Other | pheno | skatelescope.eu | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | vo.complex-systems.eu | vo.cta.in2p3.fr | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
UKI-LT2-IC-HEP | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 23
UKI-LT2-QMUL | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 23
UKI-LT2-RHUL | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 17
Total | 4 | 4 | 2 | 1 | 3 | 4 | 1 | 4 | 4 | 1 | 1 | 4 | 0 | 3 | 1 | 4 | 4 | 3 | 3 | 4 | 1 | 4 | 0 | 4 | 2 | 4 | 1 | 0 | 0 | 4 | 1 | 1 | 0 | 1 | 1 | 79
Storage resource in use per VO (TB)
Site | atlas | biomed | calice | cepc | cernatschool.org | cms | comet.j-parc.jp | dteam | dune | enmr.eu | epic.vo.gridpp.ac.uk | gridpp | hone | hyperk.org | icecube | ilc | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | ops | Other | pheno | skatelescope.eu | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | vo.complex-systems.eu | vo.cta.in2p3.fr | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 15.66 | 0.33 | 0 | 0 | 0 | 1180 | 0 | 1.31 | 0 | 0 | 0 | 0.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.234 | 0 | 0 | 0 | 0.202 | 0 | 0.002 | 1198.214 | 10.21% | 0.2132%
UKI-LT2-IC-HEP | 0 | 0 | 0 | 0 | 0 | 3649.898 | 36.652 | 0 | 248.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407.128 | 0 | 397.454 | 0 | 0 | 0 | 143.205 | 0 | 0 | 0 | 392.246 | 0 | 0 | 40.389 | 0 | 0 | 0 | 0 | 0 | 5315.805 | 45.29% | 23.68%
UKI-LT2-QMUL | 3812 | 0.98 | 0 | 0 | 0.076 | 3.4 | 0 | 1.3 | 0 | 0 | 0.016 | 0.071 | 0.7 | 0.718 | 0 | 0 | 215.8 | 0.277 | 0 | 0 | 0 | 0 | 0 | 0.023 | 0.145 | 11.166 | 0 | 0.019 | 0 | 248.77 | 0 | 0 | 0.0052 | 1.442 | 0 | 4296.9082 | 36.61% | 6.184%
UKI-LT2-RHUL | 925.304 | 0 | 0 | 0 | 0 | 1.604 | 0 | 0.016 | 0 | 0 | 0 | 0.006 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 927.142 | 7.899% | 0.02524%
Total | 4752.964 | 1.31 | 0 | 0 | 0.076 | 4834.902 | 36.652 | 2.626 | 248.833 | 0 | 0.016 | 0.553 | 0.89 | 0.718 | 0 | 0 | 622.928 | 0.277 | 397.454 | 0 | 0 | 0 | 143.205 | 0.043 | 0.145 | 11.166 | 392.246 | 0.019 | 0.234 | 289.159 | 0 | 0 | 0.2072 | 1.442 | 0.004 | 11738.0692 | 100% | 13.01%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q219
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | 0.5 | 0.5 | 0.5 | 0.15 | 0.15 | 0.15 | Have not been updated
| Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
| P. Hobson |  |  |  | 0.1 | 0.1 | 0.1
| P. Kyberd |  |  |  | 0.05 | 0.05 | 0.05
UKI-LT2-IC-HEP | Simon Fayer | 1 | 1 | 1
| Daniela Bauer | 1 | 1 | 1
| Ray Beuselinck |  |  |  | 1 | 1 | 1
| Duncan Rand | 0.5 | 0.5 | 0.5
| David Colling |  |  |  | 0.1 | 0.1 | 0.1
UKI-LT2-QMUL | Terry Froy | 1 | 1 | 1
| Dan Traynor | 1 | 1 | 1
| local site assistance |  |  |  | 0.1 | 0.1 | 0.1
UKI-LT2-RHUL | Antonio Perez Fernandez | 0.5 | 0.5 | 0.5
| B.Green/Tom |  |  |  | 0.2 | 0.2 | 0.2
UKI-LT2-UCL-HEP | Ben Waugh |  |  |  | 0.05 | 0.05 | 0.05
Total |  | 6.05 | 6.05 | 6.05 | 1.95 | 1.95 | 1.95

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q219
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | Link upgrade was delivered in June. Brunel networks scheduled to deliver it in September. 95% or more of transfers to Brunel going on IPv6. CMS are now using permanently above 1.1 PB at Brunel
UKI-LT2-IC-HEP | Moved site to Slough.
UKI-LT2-QMUL | Have now deployed 4500 CentOS7 job slots, remaining 1500 slots will move when 2tk have finished their existing SL6 production run which they wish to keep on consistent software. Have developed a arc6 CE service to replace the cream CEs. Only the accounting remains to be done. Have helped Sussex grid site and their new sysadmin with Grid onboarding and move to CentOS 7. Have become the SE for Cambridge and Sussex grid sites (on top of IC and UCL) as they migrate to a storageless model. Had meeting with Central IT networks, central research IT and Janet to start on 100Gb/s network upgrade Purchased 3 lightweight nodes (4core/8HT 32 GB ram) for new monitoring box, Lustre management and test node (e.g. perfsonar@25/50Gb/s). These nodes were also purchased from different vendors from normal to aid in future tenders. Have had meetings with several vendors about next procurement of storage and compute. have drafted a tender for the storage which is with procurement. We have modified the configuration of one of the storage nodes(HA Lustre OSS/OST setup, providing 1.6PB) which was proving unreliable. New configuration is much more stable. Had a talk accepted for CHEP2019 on GPU usage and gave a talk tat the GridPP technical meeting about GPU usage. Updated cluster DHCPv4/DHCPv6 service to Kea 1.6.0beta2 (better API support for automated provisioning). Preliminary work on RHEL/CentOS 8.x deployment has begun - the intention is to have fully-functional CentOS 8.x test worker nodes in order to debug and validate SL6/CentOS7 workloads running under Singularity on CentOS 8 or some other LXC-based container solution. Continuing evaluation and familiarization with OpenStack on CentOS. Evaluation of later Linux LTS kernels for potential production use on compute nodes in order to maximize performance on newer CPU architectures (i.e. AMD EPYC).
UKI-LT2-RHUL | - Added two new squids for better redundancy - VAC nodes decommissioned to make space in racks for GridPP5.2 purchase - Delivery of 12 kHS06 (GridPP5.2) from Dell but not yet commissioning due to incorrect CPUs - Drained two old storage nodes (40 TB total) to prepare for DPM upgrade in August - General unreliability of DPM, CREAM and Torque/Maui batch systems required frequent intervention
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes