## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q219 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 98% | 45% | 53% | 91% | 44% | 97% | 97% | 99% | [9 empty] | 100% | 83% | 62.67% | At ECDF there hole in the accounting is due to a combination of the old CE at the site failing as well as problems with reporting/accounting from the new CE not being discovered until teh site was already a few weeks into production.
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 100% | 98% | 48% | 53% | 91% | 44% | 97% | 97% | 99% | [9 empty] | 100% | 83% | 63.67%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 89% | 79% | 72.37% | 120% | 117% | 54.17% | 74% | 59% | 66.61% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 84% | 86% | 72.7%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 89% | 79% | 72.95% | 107% | 105% | 50.85% | 57% | 49% | 55.54% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 73% | 74% | 61.8%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q219
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | Site | 2019-04-01 | 2019-05-01 | 2019-06-01 | Total |  | Site | 2019-04-01 | 2019-05-01 | 2019-06-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 20927530 | 17620088 | 34039200 | 72586818 |  | DURHAM | 20883739 | 17560115 | 33562626 | 72006480
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 8343924 | 2579665 | 181312 | 11104901 |  | ECDF | 8730283 | 2857766 | 242301 | 11830350
[8 empty] | GLASGOW | 31463757 | 22266730 | 23474633 | 77205120 |  | GLASGOW | 35375609 | 26492640 | 30720008 | 92588257
[8 empty] | ECDF-CS [1,2] | 2374070 | 3959651 | 5941866 | 12275587 |  | ECDF-CS [1,2] | 2484000 | 4143000 | 6217000 | 12844000
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 63109281 | 46426134 | 63637011 | 173172426 |  | Total | 67473631 | 51053521 | 70741935 | 189269087
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 72586818 | 45.11% | 2184 | 99503040 | 72.95% | 72.37%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 11104901 | 6.902% | 2184 | 21840000 | 50.85% | 54.17%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 77205120 | 47.98% | 2184 | 138996312 | 55.54% | 66.61%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 160896839 | 100% | 2184 | 260339352 | 61.8% | 72.7%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q219
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q219
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | R. Currie | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | T. Li | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | J. Perry (EPCC) | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | E. SImili | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 4 | 4 | 4 | 0.2 | 0.2 | 0.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q219
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
DURHAM | Our CentOS 7 Migration was a success albeit with some minor issues on change over; along with several nodes that decided not to play nice. Migrated to Puppet 5.5 / Foreman 20. Paul managed to deploy Fail2Ban via our Puppet setup, including some SELinux Modules for CentOS7. He has managed to deploy the setup over 6 systems within the Grid and our Local Group. CIS have finally bodged their DNS servers into IPv6 and can begine to provide IPv6 rDNS. |  | We have discovered CIS haven't actually setup IPv6 properly and as such we discovered that DHCPv6 is broken. As Durham have not yet implemented IPv6, we will be a test bed for their deployment ideas. CentOS 7 Migrated for ARC was a nightmare, mystery services were appearing, this resolved itself after a few rebuilds. Puppet broke as PuppetLabs removed the old Puppet binaries we relied on, so we migrated to a newer version, only for them to return the old binaries.
ECDF | Replaced the old ce, and migrated all workflow to it. Fixed several longstanding site issues to do with reliability/availability. Replaced old bdii service. Deployed LSST UI machine for users to submit jobs to the grid. Now migrated off deprecated vmware services hosted by IS in favor of kvm VMs managed on our own HV. |  | All major issues at the site in the last quater have been CE related. It is believed that these stem from site specific problems combined with a change in the ATLAS job submission system which amplified the issues already being observed. Problems with the new CE deployed at the site led to a hole in the reporting/monitoring metrics or about 2-3 weeks. Longstanding CE problems at the site have previously been poorly understood or documented which cost time in investigating the source of the problem(s). Combined with loss of expertise this required regenerating lost-knowledge. Instability of the old CE caused an initial downtime of the site for a considerable amount of time.
GLASGOW | Migration plans to the DC are underway and preferential access should be gained Aug 2019. New minimal cluster set up with new Argus, ARC6, HTCondor Batch and CentOS7 WN. Test CEPH storage systems setup, working on Grid interface and load testing. |  | Due to air conditioning problems in one of our server rooms, we ran at reduced capacity across the end of May and into June.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: Potential issues with already deployed services which were poorly documented (mainly ARGUS now). Or, failure of MW services due to poor monitoring. |  | Regular meetings with University Research Services to formulate smooth machine room change. Adding additional documentation/monitoring as experience/expertise around existing services is regenerated.
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction, completeion scheduled July 2019
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Plan for Data Centre Migration |  | 2019-06-30 |  | Completed and used to gain preferential acces to the Data Centre Aug-2019
Glasgow: Test instance of HTCondor-CE |  | 2019-06-30 |  | Due to difficulties in getting HTConodor-CE working we moved to installing new ARC6 CE
Glasgow: Test instance of CEPH storage |  | 2019-06-30 |  | Test instance setup and currently load testing
Durham: Deploy CentOS7 Worker Nodes, CEs, UIs |  | 2019-06-30 |  | Completed. All nodes are running CentOS 7.6, All CEs are running CentOS 7.6 and all UIs are running CentOS 7.6.
Durham: Refirbished Disk Server Online |  | 2019-06-30 |  | The "nearly as wobbly as the conservative party" disk server is back online and is determined to strive for greatness until post-brexit.
Durham: Improve Test Development and better document a shared Fail2Ban System |  | 2019-06-30 |  | Written a poor-mans puppet script for deployment at Durham. Now deployed over 6 systems.
Durham: Reverse DNS for IPv6 *Optimistic Date* |  | 2019-06-30 |  | CIS have bodged this in and we have working rDNSv6.
ECDF: Bring up the new CE |  | 2019-06-30 |  | New CE ce1.gridpp.ecdf.ed.ac.uk was deployed and functioning
ECDF: XCache monitoring service |  | 2019-06-30 |  | Software development was done. Hardware deloyment is ongoing.
ECDF: Hire new postdoc |  | 2019-06-30 |  | Hired new postdoc. Waiting for visa process and will start in early Septemper.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Inital Migration of Equipment to DC (VAC and new core services) |  | 2019-10-01 |  | VAC running from the new DC
Glasgow: New Cluster completed |  | 2019-10-01 |  | New CentOS 7 cluster running production work for ATLAS
Glasgow: Grid Interfaces completed and tested for CEPH |  | 2019-10-01 |  | Xrootd endpoints configured and system load tested by experiments (ATLAS)
Durham: Shared Fail2Ban Imporvements |  | 2019-10-01 |  | Shared F2B testing between more sites and A basic local deployment guide.
Durham: Remove all reliance on the sourge that is commercial closed source hypervisor vmware. |  | 2019-10-01 |  | ProxMox Vhosts Environment
Durham: In a vein attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  | 2019-10-01 |  | A 'Cloud' deployment and environment for our monitoring platforms.
Durham: Dual Stack Storage |  | 2019-10-01 |  | Our storage will be dual stacked.
ECDF: Delopy XCache monitoring service |  | 2019-10-01 |  | Finish the hardware deployment and advitise to GridPP
ECDF: Deploy Rucio development instance |  | 2019-10-01 |  | Deploy a dev instance of Rucio to share with UK Rucio people
ECDF: Deploy new landing page for site and blog to share experiences |  | 2019-10-01 |  | Publicly viewable blog at site sharing experiences of useful/interesting technical information.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via Ganga/DIRAC
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
DUNE |  | Ongoing |  | Provided effort into DUNE Rucio Prototype Evaluation
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Member of WLCG DOMA-Access WG |  | Present |  | Teng Li
Member of LHCb RTA |  | Present |  | Robert Currie
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A