## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | LondonGrid Tier 2 | [5 empty] | Close to target
Quarter | Q319 | [5 empty] | Not OK
Reported by | Duncan Rand | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | UKI-LT2-Brunel |  |  | UKI-LT2-IC-HEP |  |  | UKI-LT2-QMUL |  |  | UKI-LT2-RHUL |  |  | UKI-LT2-UCL-HEP |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 371.3% | 371.3% | 371.3% | 606.6% | 606.6% | 606.6% | 352.1% | 352.1% | 352.1% | 131.6% | 131.6% | 131.6% |  |  |  | 374.8% | 374.8% | 374.8%
.x.2 | % of promised (by that time) CPU available | 100% | 363.3% | 363.3% | 363.3% | 258.6% | 258.6% | 258.6% | 375.1% | 375.1% | 375.1% | 604.7% | 592.8% | 682.9% |  |  |  | 356.7% | 354.8% | 369.2%
.x.3 | Average Nagios (Argo page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 83% | 63% | 99.6% | 98% | 99% | 89.1% | 94% | 100% | 82.7% | 100% | 99% | 91.9% |  |  |  | 93.75% | 90.25% | 90.83%
.x.4 | Average Nagios (Argo page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 89% | 63% | 99.6% | 98% | 99% | 89.3% | 97% | 100% | 82.8% | 100% | 99% | 97.5% |  |  |  | 96% | 90.25% | 92.3%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 98.51% | 123.1% | 113.9% | 87.91% | 71.14% | 93.37% | 83.4% | 113.5% | 109.4% | 80.77% | 83% | 50.22% |  |  |  | 86.86% | 94.31% | 88.05% | Brunel + QMUL > 100%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 61.91% | 82.07% | 81.39% | 75.71% | 62.35% | 83.91% | 70.85% | 146.5% | 166.2% | 68.16% | 67.73% | 41.59% |  |  |  | 69.92% | 87.89% | 90.11% | QMUL > 100%
.x.3/.4
.x.5 | https://argo.egi.eu/egi/report-ar-dates-2/Critical/SITES/UKI-LT2-RHUL?start_date=2019-07-01&end_date=2019-09-30

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q319
Reported by | Duncan Rand
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
UKI-LT2-Brunel | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | DPM |  |  | 2019 Jul | 2019 Aug | 2019 Sep | Total |  |  | 2019 Jul | 2019 Aug | 2019 Sep | Total
UKI-LT2-IC-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 100 Gb/s | dCache |  | UKI-LT2-Brunel | 21861149.7596 | 21547520.6209 | 19487423.3965 | 62896094 |  | UKI-LT2-Brunel | 31698647.0486 | 29748309.3267 | 26607065.8806 | 88054022
UKI-LT2-QMUL | EMI-3 | EMI-3 |  | 10 Gb/s | 20 Gb/s | Storm |  | UKI-LT2-IC-HEP | 30911193.7168 | 37869044.5161 | 36207183.312 | 104987422 |  | UKI-LT2-IC-HEP | 35085224.3318 | 41366530.6304 | 40370191.3289 | 116821946
UKI-LT2-RHUL | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-QMUL | 58005097.2958 | 59374032.5972 | 49078829.9969 | 166457960 |  | UKI-LT2-QMUL | 38562662.2895 | 36600804.4316 | 34459966.2715 | 109623433
UKI-LT2-UCL-HEP | EMI-3 | EMI-3 |  | 10 Gb/s | 10 Gb/s | DPM |  | UKI-LT2-RHUL | 21290160.7169 | 16108052.1508 | 15501055.2558 | 52899268 |  | UKI-LT2-RHUL | 25148353.1454 | 20190854.0386 | 18532828.5762 | 63872036
[8 empty] | Total | 132067601 | 134898650 | 120274492 | 387240743 |  | Total | 130494887 | 127906498 | 119970052 | 378371437
https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2019/7/2019/9/all/localinfrajobs/
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2015*) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | Site efficiency
UKI-LT2-Brunel | 35000 | 1700 | 9632.812 | 457.8006 | 363.3% | 371.3% | 17.98% | 10.64% | 62896094 | 16.24% | 2208 | 77280000 | 81.39% | 113.9% | 71.43%
UKI-LT2-IC-HEP | 56664 | 7969 | 21915.766 | 1313.8219 | 258.6% | 606.6% | 29.11% | 49.9% | 104987422 | 27.11% | 2208 | 125114112 | 83.91% | 93.37% | 89.87%
UKI-LT2-QMUL | 45363 | 5001 | 12094.921 | 1420.211 | 375.1% | 352.1% | 23.31% | 31.31% | 166457960 | 42.99% | 2208 | 100161504 | 166.2% | 109.4% | 151.8%
UKI-LT2-RHUL | 57600 | 1300 | 8434.349 | 987.6466 | 682.9% | 131.6% | 29.6% | 8.14% | 52899268 | 13.66% | 2208 | 127180800 | 41.59% | 50.22% | 82.82%
UKI-LT2-UCL-HEP |  |  | 636.75 | 81
Totals | 194627 | 15970 | 52714.598 | 4260.48 | 369.2% | 374.8% | 100% | 100% | 387240744 | 100% | 2208 | 429736416 | 90.11% | 88.05% | 102.3%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | rebus | [8 empty] | Q3 | 2208
| cpu cores | HS06 | TB | [6 empty] | Q4 | 2208
UKI-LT2-Brunel | 5298 | 62344 | 1762
UKI-LT2-IC-HEP | 5718 | 59582 | 7969
UKI-LT2-QMUL | 12320 | 318474 | 5095 | CPU capacity reporting is broken (need to get rid of SL6 and Cream CEs to fix it)
UKI-LT2-RHUL | 4624 | 48121 | 1390
UKI-LT2-UCL-HEP | 0 | 0 | 0
Totals |  | 488521 | 16216
Colour coding is green for within 10% and orange within 20% and red for more than 20%
http://gstat-wlcg.cern.ch/apps/capacities/sites/ shows HS06
* https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q319
Reported by | Duncan Rand
Vos Supported
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Supported VOs
Site | atlas | biomed | calice | cepc | cernatschool.org | cms | comet.j-parc.jp | dteam | dune | enmr.eu | epic.vo.gridpp.ac.uk | gridpp | hone | hyperk.org | icecube | ilc | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | ops | Other | pheno | skatelescope.eu | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | vo.complex-systems.eu | vo.cta.in2p3.fr | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total
UKI-LT2-Brunel | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16
UKI-LT2-IC-HEP | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 23
UKI-LT2-QMUL | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 23
UKI-LT2-RHUL | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 17
Total | 4 | 4 | 2 | 1 | 3 | 4 | 1 | 4 | 4 | 1 | 1 | 4 | 0 | 3 | 1 | 4 | 4 | 3 | 3 | 4 | 1 | 4 | 0 | 4 | 2 | 4 | 1 | 0 | 0 | 4 | 1 | 1 | 0 | 1 | 1 | 79
Storage resource in use per VO (TB)
Site | atlas | biomed | calice | cepc | cernatschool.org | cms | comet.j-parc.jp | dteam | dune | enmr.eu | epic.vo.gridpp.ac.uk | gridpp | hone | hyperk.org | icecube | ilc | lhcb | lsst | lz | mice | na62.vo.gridpp.ac.uk | ops | Other | pheno | skatelescope.eu | snoplus.snolab.ca | solidexperiment.org | superbvo.org | supernemo.vo.eu-egee.org | t2k.org | vo.complex-systems.eu | vo.cta.in2p3.fr | vo.londongrid.ac.uk | vo.moedal.org | zeus | Total | Site Percentage of T2 Disk used | Site percentage non LHC
UKI-LT2-Brunel | 15.66 | 0.33 | 0 | 0 | 0 | 1080 | 0 | 4.16 | 0 | 0 | 0 | 0.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.007 | 0 | 0 | 0 | 0 | 0.234 | 0 | 0 | 0 | 0.202 | 0 | 0.002 | 1101.071 | 9.775% | 0.4914%
UKI-LT2-IC-HEP | 0 | 0 | 0 | 0 | 0 | 3495.401 | 36.652 | 0 | 248.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.88 | 0 | 528.769 | 0 | 0 | 0 | 145.987 | 0 | 0 | 0 | 360.17 | 0 | 0 | 47.165 | 0 | 0 | 0 | 0 | 0 | 5231.857 | 46.44% | 26.14%
UKI-LT2-QMUL | 3500 | 0.936 | 0 | 0 | 0.073 | 3.3 | 0 | 1.3 | 0 | 0 | 0.016 | 0.069 | 0.673 | 0.686 | 0 | 0 | 189 | 0.265 | 0 | 0 | 0 | 0 | 0 | 0.023 | 0.156 | 11 | 0 | 0.019 | 0 | 232 | 0 | 0 | 0.0052 | 1.4 | 0 | 3940.9212 | 34.98% | 6.309%
UKI-LT2-RHUL | 989 | 0 | 0 | 0 | 0 | 1.57 | 0 | 0.016 | 0 | 0 | 0 | 0.006 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.002 | 990.804 | 8.796% | 0.02362%
Total | 4504.66 | 1.266 | 0 | 0 | 0.073 | 4580.271 | 36.652 | 5.476 | 248.833 | 0 | 0.016 | 0.551 | 0.863 | 0.686 | 0 | 0 | 557.88 | 0.265 | 528.769 | 0 | 0 | 0 | 145.987 | 0.05 | 0.156 | 11 | 360.17 | 0.019 | 0.234 | 279.165 | 0 | 0 | 0.2072 | 1.4 | 0.004 | 11264.6532 | 100% | 14.4%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | LondonGrid Tier 2
Quarter | Q319
Reported by | Duncan Rand
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
UKI-LT2-Brunel | Raul Lopes | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| Ivan Reid | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| P. Kyberd | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-IC-HEP | Simon Fayer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Daniela Bauer | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Ray Beuselinck | bar: Unfunded Month 1 to Unfunded Month 3
| Duncan Rand | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| David Colling | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-QMUL | Terry Froy | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Dan Traynor | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| local site assistance | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
UKI-LT2-RHUL | Antonio Perez Fernandez | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| B.Green/Tom | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
UKI-LT2-UCL-HEP | Ben Waugh | Unfunded Month 1: 0.05; Unfunded Month 2: 0.05; Unfunded Month 3: 0.05
Total |  | 5.5 | 5.5 | 5.5 | 1.85 | 1.85 | 1.85

## Narrative
GridPP Quarterly Report
Area | LondonGrid Tier 2
Quarter | Q319
Reported by | Duncan Rand
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
UKI-LT2-Brunel | - Connection to Janet being upgraded to 40 Gbps. - 400 TB of new storage ordered. - Testing HTCondor-CE. - Testing BeeGFS to serve VM space and NFS in general.
UKI-LT2-IC-HEP | Moved site to Slough.
UKI-LT2-QMUL | Have deployed arc6 CE into production and started to decommission cream CEs. Deployed new monitoring solution, zabbix, on new hardware running on centOS8 Upgraded slurm to 19.05.major release. Prepared new Lustre deployment (Lustre 2.12 LTS) including new iml server for monitoring Lustre. Conducted tendering and awarded contact for new Lustre storage. Reorganised racks to make space for new storage, networking and future compute purchases .
UKI-LT2-RHUL | - IPV6 awaiting solution to DNS. - cream2 decommission. - htc01 (HTCondor-CE) in production. - Centos6 to Centos7 migration on going. - DPM/DOME upgraded in August.
UKI-LT2-UCL-HEP
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Other outputs and Knowledge |  | Date |  | Notes