## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q3 2019 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 116.6% | 140.4% | 140.4% | 178.3% | 186% | 186% | 140.2% | 144% | 144% | 183.6% | 172.8% | 172.8% | 170.1% | 171.7% | 171.7% | 189.2% | 179.5% | 179.5% | 158.1% | 165% | 165%
.x.2 | % of promised (by that time) CPU available | 100% | 248.4% | 274% | 274% | 218.9% | 215.6% | 215.6% | 308.6% | 176.3% | 176.3% | 240.4% | 215.1% | 215.1% | 239.5% | 213.2% | 213.2% | 206.5% | 181.9% | 181.9% | 240.6% | 216.7% | 216.7%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 70% | 42% | 42% | 99% | 100% | 100% | 99.11% | 100% | 100% | 99% | 100% | 100% | 95% | 93% | 93% | 95% | 99% | 99% | 92.85% | 89% | 89% | Bham decommisiioning …
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 70% | 42% | 42% | 99% | 100% | 100% | 99.11% | 100% | 100% | 95% | 100% | 100% | 95% | 93% | 93% | 95% | 99% | 99% | 92.19% | 89% | 89%
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 77.18% | 68.96% | 59.2% | 59.1% | 59.01% | 58.68% | 103.3% | 111.9% | 112.5% | 85.72% | 75.25% | 83.99% | 91.54% | 97.41% | 100.8% | 70.37% | 67.37% | 35.18% | 83.98% | 82.34% | 83.12%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 67.71% | 59.55% | 48.88% | 44.99% | 36.53% | 42.5% | 79.08% | 84.12% | 78.62% | 78.74% | 67.48% | 77.49% | 65.53% | 73.4% | 80.41% | 59.17% | 60.15% | 25.96% | 67.61% | 65.7% | 68.16%
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2019
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2019-07-01 | 2019-08-01 | 2019-09-01 | Total |  | Site | 2019-07-01 | 2019-08-01 | 2019-09-01 | Total
Birmingham | UMD4 | VAC |  | 10Gb/s | 10Gb/s | DPM 1.8 | [5 empty] | 0 | [5 empty] | 0
Bristol | UMD4 | EMI 3+UMD4 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 6394268.7616 | 7620342.6378 | 7557531.4365 | 21572142.8359 |  | Birmingham | 7538297.6841 | 8870904.853 | 9716172.3978 | 26125374.9349
Cambridge | UMD 4/C7 | VAC/CS7 |  | 10Gb/s | 2*20Gb/s | No SE |  | Bristol | 1827194.2254 | 7236685.0887 | 4622800.5526 | 13686679.8667 |  | Bristol | 2939146.7932 | 8417903.5172 | 7539816.806 | 18896867.1164
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 5632204.398 | 5370678.41 | 4240338.5736 | 15243221.3816 |  | Cambridge | 7336674.445 | 7417043.1329 | 7063586.1236 | 21817303.7015
RALPP | UMD4 | UMD3 |  | 2X10Gb/s | 100Gb/s | Dcache 3.2.41 |  | Oxford | 21755209.4918 | 19465821.4091 | 21110394.2228 | 62331425.1237 |  | Oxford | 23809108.9431 | 20601912.3379 | 23151516.5632 | 67562537.8442
Sussex | UMD4/EMI3 | UMD4 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 25054059.3002 | 29133200.2773 | 27119748.109 | 81307007.6865 |  | RALPP | 34005347.5224 | 34129813.5134 | 33772386.9692 | 101907548.005
[8 empty] | Sussex | 2012927.4027 | 1153177.4183 | 0 | 3166104.821 |  | Sussex | 2465276.3848 | 1824674.8031 | 0 | 4289951.1879
[8 empty] | Total CPU hrs | 62675863.5797 | 69979905.2412 | 64650812.8945 | 197306581.7154 |  | Total | 78093851.7726 | 81262252.1575 | 81243478.8598 | 240599582.7899
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2019) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | job efficiency
Birmingham | 20206 | 1000 | 7375 | 712 | 274% | 140.4% | 15.24% | 18.37% | 21572142.8359 | 10.93% | 2184 | 44129904 | 48.88% | 59.2% | 82.57%
Bristol | 14744 | 560 | 6839 | 301 | 215.6% | 186% | 11.12% | 10.28% | 13686679.8667 | 6.937% | 2184 | 32200896 | 42.5% | 58.68% | 72.43%
Cambridge | 8878 | 265 | 5035 | 184 | 176.3% | 144% | 6.698% | 4.867% | 15243221.3816 | 7.726% | 2184 | 19389552 | 78.62% | 112.5% | 69.87%
Oxford | 36832 | 940 | 17126 | 544 | 215.1% | 172.8% | 27.79% | 17.26% | 62331425.1237 | 31.59% | 2184 | 80441088 | 77.49% | 83.99% | 92.26%
RALPP | 46300 | 2610 | 21712 | 1520 | 213.2% | 171.7% | 34.93% | 47.93% | 81307007.6865 | 41.21% | 2184 | 101119200 | 80.41% | 100.8% | 79.79%
Sussex | 5584 | 70 | 3069 | 39 | 181.9% | 179.5% | 4.213% | 1.286% | 3166104.821 | 1.605% | 2184 | 12195456 | 25.96% | 35.18% | 73.8%
Totals | 132544 | 5445 | 61156 | 3300 | 216.7% | 165% | 100% | 100% | 197306581.7154 | 100% | 2184 | 289476096 | 68.16% | 83.12% | 82.01%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
[6 empty] | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
[10 empty] | Q4 | 2208
[5 empty] | Birmingham | 22433 | 980
[5 empty] | Bristol | 9607 | 0
[5 empty] | Cambridge | 5940 | 293
[5 empty] | Oxford | 26240 | 940
[5 empty] | RALPP | 42840 | 3079
[5 empty] | Sussex | 2006 | 83
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2019
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 14
Cambridge | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 23
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 0 | 0 | 1 | 30
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [7 empty] | 5
[47 empty] | 0 | 0
[47 empty] | 0 | 0
Total | 4 | 6 | 0 | 2 | 2 | 2 | 1 | 1 | 2 | 4 | 6 | 2 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 4 | 1 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 1 | 0 | 2 | 0 | 0 | 4 | 101
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 21.89% | 0%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 8.418% | 0.001822%
Cambridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Oxford | 0 | 677 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 2.98 | 0.018 |  | 0.016 | 1.5 | 33.6 | 0 | 0 | 0.02285 | 716.9791 | 15.71% | 5.435%
RALPP | 0 | 642 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1353 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 326 |  | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0.7 | 8 | 0 | 0 | 0.65 | 2412.06 | 52.86% | 3.775%
Sussex |  | 50 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [10 empty] | 51.01 | 1.118% | 1.98%
Total | 999 | 1369 | 2 | 1 | 0 | 0.024 | 0 | 0 | 0 | 1738.11 | 0.307 | 0 | 0.049 | 0.73 | 0 | 0.129 | 0 | 0.0035 | 0.066 | 0 | 1.604 | 0 | 326.0058 | 0 | 41 | 35 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063 | 0 | 0 | 1 | 0 | 2.98 | 0.018 | 0 | 0.046 | 2.2 | 41.6 | 0 | 0 | 0.67285 | 4563.1582 | 100% | 2.872%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q3 2019
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| Luke Kreczko | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Cambridge
| John Hill | 0 | 0 | 0 | 0 | 0 | 0
Oxford
| Vip Davda | GridPP Funded Month 1: 0.7; GridPP Funded Month 2: 0.7; GridPP Funded Month 3: 0.7
Kashif Mohammad
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| Leo Rojas | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 1.7 | 1.7 | 1.7 | 1.2 | 1.2 | 1.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q3 2019
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Completed the setup for XCache for Atlas use. This is now running in production with no problems. Finished shifting the majority of Tier3 kit out of the server room which has improved the temperature significantly. |  | The server running the ALICE EOS instance is struggling with memory and occasionaly going into swap. In the process of purchasing a significantly better server to run EOS on.
Bristol | . Grant hardware money spent ON TIME including 2 GPU Dev nodes - still have enough funding for 1 more WN but IT Services (who must be involved, argh!) not responding (BOO!) . IPMI config working via puppet :) |  | . Less progress than hoped on HTCondor 8.8 cluster upgrade due to low manpower & expertise :[ . 7-OS Perfsonar all working except "Unable to find any tests with data" and getting no response from UK PerfSonar support to debug! . Moving to next version of provisioning (stacki) for new UEFI WN beset with bugginess of new raw stacki releases :[
Cambridge | xCache operational on single 40TB disk server. Decommission remaining DPM pool nodes and SE, so site now "diskless". Decommission ARGUS server and site BDII. All remaining systems (VAC factories, perfSonar host, Squid, UI) are running CentOS 7. |  | John Hill retired on 30/9/19 and no replacement cover available for site.
Oxford | NTR |  | Recruiting a replacement for Kashif. Hope to interview in November.
RALPP
Sussex
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: Upgrade to HTCondor 8.8 Due date: 31/31/2018 |  | 2019-12-31 |  | Partial upgrade to 8.8 (1 scheduler and two 7-OS WNs)
Bristol: New IPv6 perfsonar hosts |  | 31/06/2019 |  | BW & LAT ready but some issues with IPv6 and getting ports open
Bristol: Order New hardware to replace host vm00 |  | 2019-03-31 |  | Ordered & arrived
RALPP: Deploy New Hardware |  | 2018-03-31 |  | Complete, New disk and CPU installed and allocated
Oxford: Buy CPU from GridPP Hardware grant |  | 03/31/2019 |  | Purchased and installed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Make all Service Nodes Dual Stack |  | 2019-03-31
RALPP: Dual Sack the worker nodes |  | 2019-03-31
RALPP: Upgrade site-bdii to C7 |  | 2018-12-31 |  | On hold - awaiting clarity on the future of the BDII
RALPP: Join LHCONE |  | 2019-06-30
Bristol: More Progress on upgrade to HTCondor 8.8 (CE, and debug issues) |  | 2019-12-31 |  | SL7 container jobs (via jobrouter)
Bristol: Work on replacement of dmlite SE with xrootd-only SE, with kind+generous help from Sam Skipsey |  | 2019-12-31 |  | Probably not "retire dmlite SE, xrootd-only SE in production", but approaching that (possibly) asymptotically (!)
Bristol: Plans for replacement of 7-OS IPv6 perfsonar BW+LAT with GridPP provided hardware |  | 2019-12-31 |  | Firmer info on when the GridPP hardware may arrive (13/12/2019 is probably too soon to expect it to have arrived!)
Bristol: Get new WN into production |  | 2019-12-31 |  | At least a few new WN running jobs & providing HDFS storage (given bugginess of raw new stacki versions)
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes