## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Tier 2 | [5 empty] | Close to target
Quarter | Q4 2019 | [5 empty] | Not OK
Reported by | Matt Doidge | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Lancaster |  |  | Liverpool |  |  | Manchester |  |  | Sheffield |  |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 329% | 329% | 328.9% | 171% | 171% | 170.9% | 427% | 427% | 427.1% | 154% | 154% | 153.9% | 317.1%
.x.2 | % of promised (by that time) CPU available | 100% | 239% | 239% | 239.2% | 179% | 179% | 178.6% | 270% | 270% | 269.9% | 210% | 210% | 210.2% | 237%
.x.3 | Average SAM (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 91% | 92% | 99.9% | 99% | 99% | 99% | 81% | 100% | 100% | 100% | 100% | 100% | 99.72%
.x.4 | Average SAM (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 91% | 92% | 99.9% | 99% | 99% | 99% | 83% | 100% | 100% | 100% | 100% | 100% | 99.72%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 110% | 86% | 111.1% | 134% | 129% | 141.6% | 131% | 134% | 155.5% | 95% | 39% | 0% | 125.1%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 92% | 107% | 83.69% | 105% | 144% | 122% | 119% | 151% | 124.8% | 81% | 45% | 0% | 99.52%
Used the link provided by Pete instead of the SLL page:
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/nagios_plots.html |  |  | http://argo.egi.eu/lavoisier/site_reports?accept=html
.x.5 | http://pprc.qmul.ac.uk/~lloyd/gridpp/uktest.html |  |  | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html
Now instead using:
http://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
http://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/Critical/SITES/UKI-NORTHGRID-SHEF-HEP?start_date=2019-01-01&end_date=2019-03-31

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2019
Reported by | Matt Doidge
Current Site Status Data
Site | Service Nodes | Worker Nodes | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours)
Lancaster | umd4 | umd4 | 10Gb/s | 10Gb/s | DPM |  | Site | 2019-10-01 | 2019-11-01 | 2019-12-01 | Total |  | Site | 2019-10-01 | 2019-11-01 | 2019-12-01 | Total
Liverpool | Umd4 | umd4 | 10Gb/s | 5Gb/s | DPM |  | Lancaster | 29705470 | 36765455 | 23406030 | 89876955 |  | Lancaster | 40294855 | 44362178 | 34699349 | 119356382
Manchester | Emi-3 | Emi-3 | 10Gb/s | 10Gb/s | DPM |  | Liverpool | 16034921 | 16623983 | 16271961 | 48930865 |  | Liverpool | 17608934 | 18992372 | 20194334 | 56795640
Sheffield | Emi-3 | Emi-3 | 10Gb/s | 5Gb/s | DPM |  | Manchester | 57310553 | 54726398 | 41836319 | 153873270 |  | Manchester | 62561848 | 64463719 | 64644051 | 191669618
[7 empty] | Sheffield | 0 | 0 | 0 | 0 |  | Sheffield | 0 | 0 | 0 | 0
[7 empty] | Total CPU hrs | 103050944 | 108115836 | 81514310 | 292681090 |  | Total | 120465637 | 127818269 | 119537734 | 367821640
Current Resources Available | [12 empty] | https://accounting-next.egi.eu/egi/country/United%20Kingdom/normelap_processors/SITE/DATE/2018/1/2018/3/all/onlyinfrajobs/
Used normalised sum elapsed*number of processors
| Total available to GridPP |  | Promised (GridPP MoU 2017) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
Lancaster | 48640 | 4500 | 20332 | 1368 | 239.2% | 328.9% | 36.52% | 33.49% | 89876955 | 30.71% | 2208 | 107397120 | 83.69% | 111.1%
Liverpool | 18161 | 1584 | 10169 | 927 | 178.6% | 170.9% | 13.64% | 11.79% | 48930865 | 16.72% | 2208 | 40099488 | 122% | 141.6%
Manchester | 55829 | 6820 | 20685 | 1597 | 269.9% | 427.1% | 41.92% | 50.76% | 153873270 | 52.57% | 2208 | 123270432 | 124.8% | 155.5%
Sheffield | 10560 | 531 | 5024 | 345 | 210.2% | 153.9% | 7.929% | 3.952% | 0 | 0% | 2208 | 23316480 | 0% | 0%
Totals | 133190 | 13435 | 56210 | 4237 | 237% | 317.1% | 100% | 100% | 292681090 | 100% | 2208 | 294083520 | 99.52% | 125.1%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | gstat2 |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
Lancaster | 4000 | 60800 | 5088 | NA | Lancaster
Liverpool | 1776 | 18161 | 1585 | NA | Liverpool
Manchester | 5384 | 55829 | 7207 | NA | Manchester
Sheffield | 1024 | 12493 | 531 | NA | Sheffield
Totals | 12184 | 147283 | 14411 | 0
|  |  |  | 0 | USED REBUS FOR THESE FIGURES, SO NO SI2K
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2019
Reported by | Matt Doidge
Vos Supported
Supported VOs
Site | alice | atlas |  | biomed | calice | camont | cdf | cepc | cernatschool | cms | dteam | dune | dzero | esr | epic | fusion | Fermilab (microboone) | Fermilab (g-2) | geant4 | gridpp | hyperk.org | hone | Icecube | ilc | lhcb | LSST | LZ | mice | magic | moedal | na48 | na62 | neiss | ops | pheno | planck | vo.skatelescope.eu | snoplus | solidexperiment.org | vo.cta.in2p3.fr | vo.sixt.cern.ch | northgrid | superb | supernemo | t2k.org | zeus | Total
Lancaster |  | 1 |  |  |  |  | 0 | 1 |  | 0 | 1 | 1 |  | 0 | 0 | 0 | 1 | 1 |  | 1 | 1 |  |  | 0 | 1 | 1 | 1 |  | 0 |  | 0 | 1 | 0 | 1 | 0 |  | 1 | 1 |  | 1 |  | 1 |  |  | 1 |  | 18
Liverpool | 1 | 1 |  | 1 | 1 |  | 0 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 36
Manchester | 1 | 1 |  | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 | 0 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 |  | 23
Sheffield | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | 1 | 1 | [6 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 1 | 1 | 0 |  |  |  |  | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 0 | 1 |  | 18
Total | 3 | 4 |  | 3 | 1 | 1 | 0 |  |  | 3 | 4 | 1 | 1 | 1 | 1 | 1 |  |  | 2 | 4 | 2 | 2 |  | 2 | 4 | 1 |  | 2 | 1 | 1 | 1 | 1 |  | 4 | 3 |  | 3 | 4 |  |  | 1 | 4 | 2 | 2 | 4 |  | 95
Storage resource in use per VO (TB)
Site | lhcb | atlas | biomed | t2k | common | Total | Site Percentage of T2 Disk used | Site percentage non LHC
Lancaster | 0 | 1800 | 0 | 17 | 1 | 1818 | 0.9351% | 0.9901%
Liverpool | 0.18 | 571.45 | 0.2 | 61 | 2.68 | 635.51 | 9.599% | 10.02%
Manchester | 108 | 1108.79 | 0.09 | 72 | 3.254 | 1292.134 | 5.572% | 5.831%
Sheffield | 0 | 490 | 0.28 | 29 | 1.536 | 520.816 | 5.568% | 5.917%
Total | 108.18 | 3970.24 | 0.57 | 179 | 8.47 | 4266.46 | 4.196% | 4.407%
Reported only VOs occupying more than 50GB

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | Tier 2
Quarter | Q4 2019
Reported by | Matt Doidge
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Lancaster | A.Wharton | GridPP Funded Month 1: 0,2; GridPP Funded Month 2: 0.2; GridPP Funded Month 3: 0.2
| E. Bouhova-Thacker | GridPP Funded Month 1: 0.8; GridPP Funded Month 2: 0.8; GridPP Funded Month 3: 0.8
M. Doidge | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| P. Love | Unfunded Month 1: 0.3; Unfunded Month 2: 0.3; Unfunded Month 3: 0.3
Liverpool | S. Jones | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
| R. Fay | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| J. Bland | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
Manchester | A. Forti | bar: GridPP Funded Month 1 to GridPP Funded Month 3
R. Frank | bar: GridPP Funded Month 1 to GridPP Funded Month 3
| A. McNab | Unfunded Month 1: 0.5; Unfunded Month 2: 0.5; Unfunded Month 3: 0.5
Sheffield | E. Korolkova | GridPP Funded Month 1: 0.25; GridPP Funded Month 2: 0.25; GridPP Funded Month 3: 0.25
| Mitchell Perry | Unfunded Month 1: 0.15; Unfunded Month 2: 0.15; Unfunded Month 3: 0.15
Total |  | 4.55 | 4.75 | 4.75 | 1.2 | 1.2 | 1.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Manchester | A. McNab | EGI Funded Month 1: 0.5; EGI Funded Month 2: 0.5; EGI Funded Month 3: 0.5
Manchester | A. Forti | bar: Unfunded Month 1 to Unfunded Month 3

## Lancaster
GridPP Quarterly Report
Area | NorthGrid
Quarter | 19Q4
Reported by | Matt Doidge
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Lancaster | Engage with user groups, get them working. Procure new kit. | LSST, g-2, cepc working well New kit orders put in. |  |  | A lot of debugging required to get storage working well for new users.
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Lancaster | Hitting some issues working within the paradigm of a shared cluster |  |  | Root access and participation in planning and deployment.
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | New kit procured, Fixed several problems with LSST running |  |  |  |  | More kit on its way.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Lancaster | Get new kit online. Overhaul infrastructure. |  |  |  |  | More kit. Better able to meet needs for user groups new and old.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG

## Liverpool
GridPP Quarterly Report
Area | NorthGrid
Quarter | 19Q4
Reported by | Ste Jones
Progress over last Quarter
Site | Work area | Successes |  |  | Problems/Issues
Liverpool | New VOs Support to other sites HTCCE or ARC Task forces | Incorporating MU3e (UK), UI, CVMFS, SW Support, Storage. Incorporated G-2 at liv site. Support to Shef to get ARC/BDII Support RPMs for HTCondorCE APEL. Support to RHUL to implement HTCCE. support to Centro Brasileiro de Pesquisas Físicas (HTCCE ) Participated in Info Sys and Accounting task force meetings. |  |  | None to speak of. Dozens of small things, really…
Note:To get multiple lines per box use Alt-Return
Insitute or area specific risks
Site | Risk |  |  | Mitigating Action
Liverpool | We’re operating on 0.5 FTE. |  |  | Be efficient!
Objectives and Deliverables for Last Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | We’re down to .5 FTE. As far as I can recall, we did the things we should have done and didn’t do anything we should not have done. The site is still running so it’s going to be OK. Making progress with Mu3E, HTCCE, + task force work (InfoSys and Accountng) |  |  | 6/9/2019 |  | Site survives downsize… we’re still here. Remove BDII everywhere…. it’ll take a while.
Objectives and Deliverables for Next Quarter
Site | Objective/Deliverable |  |  | Due Date |  | Metric/Output
Liverpool | Usability tests for Tom Whyntie’s user guide. Put it back online. Get the JSON Schemas accepted and start validating them rigourously. Dump BDII everywhere in the world. Get MU3e VO well set up. |  |  | 31 Mar 2020 31 Mar 2020 31 Mar 2020 |  | Usability demonstrated, document back online. Reduction in weird JSONs being passed around. MU3E production runs.
EVAL Notes
Publications |  |  | Date |  | Notes
Collaborations |  |  | Date |  | Notes
Further Funding (eg external grants) |  |  | Date |  | Notes
Destination of ex staff and recruitment issues |  |  | Date |  | Notes
Dissemmination events |  |  | Date |  | Notes
Intellectual Property |  |  | Date |  | Notes
Spin out companies |  |  | Date |  | Notes
Roles held on committees and boards |  |  | Date |  | Notes
Matt joined the NGI Security Team in September
Other outputs and Knowledge |  |  | Date |  | Notes
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG