## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q419 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 192% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 501% | 256%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 45% | 92% | 96% | 44% | 91% | 88% | 99% | 97% | 99% | [9 empty] | 100% | 83% | 94.33% | RDF and EDDIE unexpected downtimes in September/October due to power outage and repeated scheduler lockups.
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 48% | 92% | 96% | 44% | 91% | 88% | 99% | 97% | 99% | [9 empty] | 100% | 83% | 94.33%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 72% | 81% | 93.76% | 54% | 113% | 131.5% | 67% | 49% | 46.78% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 84% | 86% | 73.95% | Lower utilisation due to portion of cluster moved to DC and used for new Ceph batch farm testing, this resource is not fully utilised.
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 73% | 82% | 95.04% | 51% | 102% | 107.4% | 56% | 39% | 40.06% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 73% | 74% | 66.72%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q419
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | Site | 2019-10-01 | 2019-11-01 | 2019-12-01 | Total |  | Site | 2019-10-01 | 2019-11-01 | 2019-12-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 28818091 | 35071767 | 31716683 | 95606541 |  | DURHAM | 28418633 | 34591486 | 31304146 | 94314265
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 7088463 | 9163273 | 7459514 | 23711250 |  | ECDF | 9653771 | 9615365 | 9776059 | 29045195
[8 empty] | GLASGOW | 16632344 | 20114044 | 19550630 | 56297018 |  | GLASGOW | 20308791 | 21733692 | 23688920 | 65731403
[8 empty] | ECDF-CS [1,2] | 231290 | 5060713 |  | 5060713 |  | ECDF-CS [1,2] | 242000 | 5294000 |  | 5536000
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 52770188 | 69409797 | 58726827 | 180906812 |  | Total | 58623195 | 71234543 | 64769125 | 194626863
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 38.22% | 6.223% | 95606541 | 54.44% | 2208 | 100596480 | 95.04% | 93.76%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 8.389% | 24.13% | 23711250 | 13.5% | 2208 | 22080000 | 107.4% | 131.5%
GLASGOW | 63643 | 3882 | 22034 | 1987 | 288.8% | 195.4% | 53.39% | 69.64% | 56297018 | 32.06% | 2208 | 140523744 | 40.06% | 46.78%
Totals | 119203 | 5574.239 | 46556 | 2696 | 256% | 206.8% | 100% | 100% | 175614809 | 100% | 2208 | 263200224 | 66.72% | 73.95%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 63643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q419
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q419
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | R. Currie | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | T. Li | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | J. Perry (EPCC) | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | W. Yuan | 1 | 1 | 1 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | E. SImili | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 5 | 5 | 5 | 0.2 | 0.2 | 0.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q419
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Failures
DURHAM | Fixed some DPM issues with broken directory sizes. Tweaked the process and connection counts on the SE. Redesigned the Grid network ready for new equipment and growth. |  | Various failed disks in the DPM Pool Servers.
ECDF | Both main and RDF DPM storage migrated to DOME. Deployed new CE, and migrated both CE to new UNIVA scheduler. Fixed long standing (multi-year) NFS server performance issues. Hired new member of team to contribute sysadmin work. |  | Still coping with downtimes from old scheduler being poorly supported.
GLASGOW | New Data Centre complete and handed over. Ceph & VAC successfully migrated to DC. New CE and Batch farm comissioned at DC. |  | Delays in ordered equipment have mean migration is lower. Difficulties in testing Ceph with ATLAS have meant new batch farm (approx 900 cores) located at the DC is unused.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: New UNIVA Scheduler which may pose challenges in keeping jobs reliably running on non-managed opportunistic resources. Time required to train on new technologies. Long term site storage uncertainty. |  | Regular meetings with University Research Services to understand UNIVA scheduler in more detail. Documenting corner cases. Training and passing on knowledge. More heavily use automation to reduce future work and supplement documentation.
Glasgow: Air Condition/power issues leading to damaged equipment |  | New Data Centre commences construction, completion scheduled July 2019
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Tested new CEPH Storage |  | 2020-01-01 |  | All testing is complete omitting writeback from ATLAS production jobs
Glasgow: New monitoring for New DC site |  | 2020-01-01 |  | Prometheus and temperature monitoring created and passed to main site monitoing
Glasgow: Batch Farm Migration Complete |  | 2020-01-01 |  | 960 cores commissioned and awaiting testing by ATLAS
ECDF: Build up ELK stack with the old storage kits |  | 2020-01-01 |  | Ongoing. Hardware was set up. Now migrating old data
ECDF: Upgrade main DPM Storage |  | 2020-01-01 |  | Done. Decided not to upgrade OS based on testing, shared experiences with storage group.
ECDF: Deploy new CE/migrate to UNIVA from SGE |  | 2020-01-01 |  | New CE has been deployed and will broker jobs to Opportunistic compute resources at ECDF.
ECDF: Migrate main storage to DOME |  | 2020-01-01 |  | Done. now running latest DPM+DOME on main managed storage and RDF
ECDF: Evaluate migrating RDF to use DOME |  | 2020-01-01 |  | RDF was migrated to use DOME.
ECDF: Share automated deployment tools once finished |  | 2020-01-01 |  | Partlty done, have shared ansible playbooks with Durham via github, should do this for all GridPP
ECDF: Build a new playbook for deploying prometheus monitoring stack via ansible+docker |  | 2020-01-01 |  | Not finsihed.
Durham: Shared Fail2Ban Production Ready |  | 2020-01-01 |  | Nearly production ready; some implementation/documentation issues to resolve.
Durham: Remove all reliance on the scourge that is commercial closed source hypervisor vmware. |  | 2020-01-01 |  | Awaiting new hardware.
Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  | 2020-01-01 |  | Awaiting time manipulation abilities to be able to fit more into a day.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Shared Fail2Ban Production Ready |  | 2020-04-01 |  | We will have a none-ippp system feeding into the shared fail2ban system.
Durham: Remove all reliance on the scourge that is commercial closed source hypervisor vmware. |  | 2020-04-01
Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  | 2020-04-01
Durham: Improve and Upgrade the internal networking. |  | 2020-04-01 |  | New Grid Network is online and in use
Durham: Purchase and Install new PerfSonar |  | 2020-04-01 |  | New Perfsonar is online
Durham: Frontier Cache |  | 2020-04-01 |  | Durham will have their own Frontier cache.
ECDF: Build and publish XCache monitoring dashboard to GridPP based on the new ELK stack. |  | 2020-04-01
ECDF: Improve monitoring |  | 2020-04-01 |  | Docker based ansible playbook which can be used to deploy monitoring across the site in a better way
ECDF: Evaluate CentOS8 upgrade for grid software |  | 2020-04-01 |  | Determine if we can use CentOS8 or what the plan for site hardware will be for the next 2-3 years
ECDF: Purchase new PerfSonar |  | 2020-04-01 |  | new PerfSonar box to replace other boxes at ACF
ECDF: Purchase new NFS server |  | 2020-04-01 |  | new NFS server with increased performance/capacity for Tier2/Tier3 use with EDDIE compute and Grid-UI
Glasgow: Put CEPH storage into production |  | 2020-04-01 |  | ATLAS running production workloads against CEPH
Glasgow: Install and bring online Trance-II and IRIS HW |  | 2020-04-01 |  | All new HW installed in DC, comissioned and operational
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via Ganga/DIRAC
HyperK |  | Ongoing |  | ECDF aiding in moving workloads to the Grid.
DUNE |  | Ongoing |  | Provided effort into DUNE Rucio Prototype Evaluation
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
WLCG SoC |  | 2019-12-01 |  | Paul Clark and Adam Boutcher visited Nikhef and updated the WLCG SoC Group on the developments for the Shared Fail2Ban system.
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Member of WLCG DOMA-Access WG |  | Present |  | Teng Li
Member of LHCb RTA |  | Present |  | Robert Currie
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A