## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | Scotgrid | [5 empty] | Close to target
Quarter | Q120 | [5 empty] | Not OK
Reported by | Gareth Roy | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | DURHAM |  |  | ECDF |  |  | GLASGOW |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 221% | 221% | 221% | 244% | 244% | 243.7% | 195% | 195% | 195.4% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 192% | 207% | 206.8%
.x.2 | % of promised (by that time) CPU available | 100% | 271% | 271% | 270.6% | 130% | 130% | 130.1% | 559% | 559% | 559% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 501% | 256% | 234.6%
.x.3 | Average NAGIOS (SLL page) availability performance over the last quarter | 95% averaged over sites in Tier-2 | 92% | 96% | 91.5% | 91% | 88% | 92.6% | 97% | 99% | 99.96% | [9 empty] | 100% | 83% | 94.69% | Downtime for upgrading site HV cost ~4days of site availability, addressing future problems. Also Q1 2020 had to migrate from SGE->UNIVA on site cluster.
.x.4 | Average NAGIOS (SLL page) reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 92% | 96% | 95.01% | 91% | 88% | 99.89% | 97% | 99% | 99.96% | [9 empty] | 100% | 83% | 98.29%
.x.7 | Approx. CPU utilisation (wall clock time) | 50% | 81% | 94% | 89.8% | 113% | 132% | 98.69% | 49% | 47% | 54.14% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 84% | 86% | 73.1%
.x.8 | Approx. CPU utilisation (CPU time) | 50% | 82% | 95% | 91.54% | 102% | 107% | 84.97% | 39% | 40% | 46.25% |  |  | #N/A |  |  | #N/A |  |  | #N/A | 73% | 74% | 68.69%
.x.3/.4 | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | Scotgrid
Quarter | Q120
Reported by | Gareth Roy
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time * number Processors HS06 hours)
DURHAM | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | Site | 2020-01-01 | 2020-02-01 | 2020-03-01 | Total |  | Site | 2020-01-01 | 2020-02-01 | 2020-03-01 | Total
ECDF | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | DURHAM | 34183658 | 21736964 | 34159378 | 90080000 |  | DURHAM | 33416204 | 21299664 | 33660089 | 88375957
GLASGOW | EMI3 | EMI3 |  | 10Gb/s | 10Gb/s | DPM |  | ECDF | 8112332 | 4457264 | 5782863 | 18352459 |  | ECDF | 9609824 | 5235313 | 6471315 | 21316452
[8 empty] | GLASGOW | 18078430 | 14809653 | 20703763 | 53591846 |  | GLASGOW | 21368638 | 18339333 | 23025556 | 62733527
[8 empty] | ECDF-CS [1,2] | 0 | 0 | 0 | 0 |  | ECDF-CS [1,2] | 0 | 0 | 0 | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0 |  | 0 |  |  |  | 0
[12 empty] | 0 | [5 empty] | 0
[8 empty] | Total CPU hrs | 60374420 | 41003881 | 60646004 | 162024305 |  | Total | 64394666 | 44874310 | 63156960 | 172425936
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2018) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours
DURHAM | 45560 | 346.9 | 16836 | 157 | 270.6% | 221% | 41.72% | 6.223% | 90080000 | 55.6% | 2160 | 98409600 | 91.54% | 89.8%
ECDF | 10000 | 1345.339 | 7686 | 552 | 130.1% | 243.7% | 9.157% | 24.13% | 18352459 | 11.33% | 2160 | 21600000 | 84.97% | 98.69%
GLASGOW | 53643 | 3882 | 22034 | 1987 | 243.5% | 195.4% | 49.12% | 69.64% | 53591846 | 33.08% | 2160 | 115868880 | 46.25% | 54.14%
Totals | 109203 | 5574.239 | 46556 | 2696 | 234.6% | 206.8% | 100% | 100% | 162024305 | 100% | 2160 | 235878480 | 68.69% | 73.1%
Please check the figures in the Yellow
| MoU figures taken from 2017 spreadsheet | [8 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
Site | Rebus |  |  | Read the SI2K from gstat | [5 empty] | Q3 | 2208
| cpu cores | HS06 | TB | SI2K | [5 empty] | Q4 | 2208
DURHAM | 423 | 45560 | 346.9 | 2419200 | DURHAM
ECDF | 568 | 10000 | 1345.339 | 10812256 | ECDF
GLASGOW | 573 | 53643 | 3882 | 8469816 | GLASGOW
Totals
Colour coding is green for within 10% and orange within 20%
Gstat currently shows KSI2k so this is converted to HS06 above
[1] New Cloud scheduler service run on ECDF openstack (~400 cores). In future this will be integrated into a single ECDF resource.
[2] Values are not available in EGI accounting at present. CPU and walltime data are available at https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CondorHeprcAccounting and https://wiki.heprc.uvic.ca/twiki/bin/view/HEPrc/CernAccounting

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q120
Reported by | Gareth Roy
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cms | dteam | dzero | epic | enmr.eu | euindia | fusion | geant4 | gridpp | hone | LZ | lsst | ilc | lhcb | mice | magic | minos | na48 | ngs | ops | pheno | planck | ralpp | sixt | southgrid | superb | supernemo | t2k | totalep | na62 | zeus | Total
DURHAM | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13
ECDF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
GLASGOW | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 12
0
0
0
0
0
Total | 0 | 3 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 3 | 0 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 34
Site | atlas | biomed | camont | cdf | cms | compchem | dames.org.uk | dteam | dzero | enmr.eu | enroller.org.uk | gridpp | hone | ilc | ildg | lhcb | LZ | mice | monitoring.ngs.ac.uk | na62 | ngs.ac.uk | ops | pheno | planck | sixt | supernemo.vo.eu-egee.org | totalep | ukqcd.vo.gridpp.ac.uk | vo.nanocmos.ac.uk | vo.optics.ac.uk | vo.panda.gsi.de | vo.scotgrid.ac.uk | vo.ssp.ac.uk | zeus | any VO | total | fraction used | Site percentage non LHC
DURHAM | 240 | 0.1 |  |  |  | 0 | [16 empty] | 7.67 | [12 empty] | 247.77 | 4.512% | 3.136%
ECDF | 1071 | [33 empty] | 274.339 | 1345.339 | 24.5% | 20.39%
GLASGOW | 3882 | 1.2 | 0 | 0 | 1.01 |  | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 6.91 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 3898.428 | 70.99% | 0.3955%
Total | 5193 | 1.3 | 0 | 0 | 1.01 | 0 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0.002 | 0 | 0 | 0 | 1.39 | 0 | 1.52 | 0 | 0.002 | 14.58 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 0 | 5491.537 | 100% | 5.418%

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | ScotGrid
Quarter | Q120
Reported by | Gareth Roy
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
Durham | Paul Clark | 0 | 0 | 0 | 0 | 0 | 0
Edinburgh | R. Currie | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | T. Li | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | J. Perry (EPCC) | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Edinburgh | W. Yuan | 1 | 1 | 1 | 0 | 0 | 0
Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
Glasgow | E. Simili | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | S. Skipsey | 0 | 0 | 0 | 0 | 0 | 0
Glasgow | G. Roy | 1 | 1 | 1 | 0 | 0 | 0
Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
Total |  | 5 | 5 | 5 | 0.2 | 0.2 | 0.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | ScotGrid
Quarter | Q120
Reported by | Gareth Roy
Progress over last Quarter
Site/area | Successes |  | Failures
DURHAM | Migrated from VMWare to Proxmox onto new hardware. Tendered, purchased and deployed PerfSonar. Deployed small docker swarm for monitoring system. Installed and deployed a new ELK instance. installed and deployed Elastiflow. Tendered and purchased GridPP HW - deployed new storage array, waiting on other hardware. |  | Nothing; Durham doesn't tolerate failure. Various disk server wobbles - Paul identified issues with DOME/DPM meaning the migration to DOME was not smooth, we're still currently dependant on legacy DPM services. Solved a local issue where CE3 and CE4 had failed to send accounding data and had crashed various ARC services; a reboot solved this. Submission still worked, just no accounting data was being sent. Added some timeouts to internal monitoring scripts that utilise netcat/nc to as nc will on occasion fail and just hang, therefore adding wait io load on systems. Still seeing issues with IPv6 locally, this is due to Stateful and Stateless (SLACC) configurations not being correct, working with campus IT to resolve but IPv6 is not a priority for them.
ECDF | Re-Deployed site HV on upgraded hardware which makes scaling easier/more-reliable. Deployed new PS box and have it fully in production. Enhanced site monitoring to allow us to pick up more opportunistic compute. Added better (on-server) firewall and ssh logging across site. |  | Lack of documentation, ranging from minimal to none for how some services were historically deployed is still an ongoing issue. Will be addressed in Q2. Local issues with UNIVA allocating resources via vmem in a 64bit era causes nothing but headaches. Had to apply some local modifications to job descriptions from VOs to allocate resources on the cluster so jobs aren't killed for no valid reason. Now we're limited to <=500 ATLAS cores at the site at any one time, but LHCb seems to be able to scale up/down without problem. Lack of centralised monitoring makes checking for security problems and updates error prone. Lack of monitoring of some components of site makes detecting VO specific errors difficult. Problems with jobs running on CS means resource is marked as offline due to storage related issues, despite rest of site working correctly. Investigations ongoing.
GLASGOW | Installation of all Tranche and IRIS HW went smoothly within new data centre. All WN now online and integrated intp new batch farm. 3.2TB of Storage now online with CEPH and ongoing work to enable grid interfaces continues. Deployment of new central logging infrastructure based on Loki. |  | Reduction in SIte HEPSPEC due to unavailable equipment in the Data Centre and portion still associated with CentOS6 queue which is mainly idle. Site operations are complicated by being split across 3 sites, with 3 seperate generations of MIddleware. HW failures (in particular Storage servers) have led to poor site performance. CEPH deployment stalled by poorly behaving Grid Interfaces, requireing a redeisgn of front end services.
0
0
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Staff loss. Loss of expertise. |  | Documentation for each site, including install and maintenance methods.
Institute or area specific risks
Risk |  | Mitigating Action
ECDF: New UNIVA Scheduler which may pose challenges in keeping jobs reliably running on non-managed opportunistic resources. Time required to train on new technologies. Long term site storage uncertainty. |  | Regular meetings with University Research Services to understand UNIVA scheduler in more detail. Documenting corner cases. Training and passing on knowledge. More heavily use automation to reduce future work and supplement documentation.
Glasgow: Air Condition/power issues leading to damaged equipment |  | Migration ongoing to new DC, delayed due to comissioning of new strage system
Durham: Only a single system admin with Grid knowledge. |  | Training up other admin.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Durham: Shared Fail2Ban Production Ready |  | 2020-04-01 |  | Bring Forward - Basically Production Ready just lacking documentation.
Durham: Remove all reliance on the scourge that is commercial closed source hypervisor vmware. |  | 2020-04-01 |  | Completed - Utilising a 4 node Proxmox VE Cluster and CEPH for shared storage.
Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  | 2020-04-01 |  | 90% Complete - Need to re-write the "self build" portion and migrate Nagios into a container.
Durham: Improve and Upgrade the internal networking. |  | 2020-04-01 |  | Completed - Now running on a redundant 40Gb/s Internal network with a redundant 10Gb/s uplink to the campus network.
Durham: Purchase and Install new PerfSonar |  | 2020-04-01 |  | Completed - New PS is installed, some minor perfornace issues but this could be the network and not PS.
Durham: Frontier Cache |  | 2020-04-01 |  | Bring Forward - Hardware has been identified.
ECDF: Build and publish XCache monitoring dashboard to GridPP based on the new ELK stack. |  | 2020-04-01 |  | Dashboard are being published, still need for anonymous dashboard to access monitoring remotely.
ECDF: Improve monitoring |  | 2020-04-01 |  | Site monitoring has now been put behind firewall rules, plan to use docker-compose to de-deploy stack using DNS + nginx-proxies. Have expanded additional monitoring to reflect changes in site SGE cluster.
ECDF: Evaluate CentOS8 upgrade for grid software |  | 2020-04-01 |  | CentOS8 determined not appropriate for most Tier2 software as a host but ideal for deploying HV and non-grid components.
ECDF: Purchase new PerfSonar |  | 2020-04-01 |  | Purchased new PS and put into production. Working well.
ECDF: Purchase new NFS server |  | 2020-04-01 |  | Purchased new NFS server, delay in putting into production due to pending CE/ARGUS upgrades.
Glasgow: Put CEPH storage into production |  | 2020-04-01 |  | Delay due to lack of physical access.
Glasgow: Install and bring online Trance-II and IRIS HW |  | 2020-04-01 |  | All HW add and online
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Glasgow: Decomission CentOS6 queue and reclaim resource |  | 2020-07-01 |  | All WN decomissioned.
Glasgow: Production Deployment of CEPH Storage |  | 2020-07-01 |  | Atlas running production workloads.
ECDF: Deploy new NFS server |  | 2020-07-01 |  | New NFS backing compute and extra storage for T3 use.
ECDF: Enable anonymous access to monitoring at site |  | 2020-07-01 |  | Public facing anonymous montoring dashboards exposed for GridPP/small-VO monitoring at site
ECDF: ARC6 |  | 2020-07-01 |  | Site has migrated to ARC6 to still run jobs
ECDF: Migrate services to CentOS7 |  | 2020-07-01 |  | Migrate DPM head-node and site BDII to CentOS7 (ARGUS to follow after July)
ECDF: Set up centralised logging |  | 2020-07-01 |  | Setup and configure centralised logging based on Loki
Durham: Frontier Cache |  | 2020-07-01 |  | Working frontier cache.
Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  | 2020-07-01 |  | Migrate the rest of the monitoring platform/stack - eg Nagios and Self Build ability. Finish performance tweaks.
Durham: Shared Fail2Ban Production Ready |  | 2020-07-01 |  | Finalised Documentation/Installation guide.
Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  | 2020-07-01 |  | Working production CentOS8 Dome Head Node.
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
LSST |  | Ongoing |  | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via DIRAC
LZ |  | Ongoing |  | ECDF aiding in moving some workloads to the Grid.
DUNE |  | Ongoing |  | Provided effort into DUNE RUCIO deployment and data management
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
N/A
Roles held on committees and boards |  | Date |  | Notes
UK Members of DPM Collaboration |  | Present |  | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group |  | Present |  | S. Skipsey
Member of Tier-2 Evolution Working Group |  | Present |  | S.Skipsey
WLCG Sytem Performance and Cost Modelling WG |  | Present |  | Gareth Roy
Member of WLCG DOMA-Access WG |  | Present |  | Teng Li
Member of LHCb RTA |  | Present |  | Robert Currie
Other outputs and Knowledge |  | Date |  | Notes
N/A
N/A