## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Tier-1 |  |  | Close to target
Quarter | Q1 2020 |  |  | Not OK
Reported by | Darren Moore |  |  | Not yet able to be measured
Suspended
GridPP no. | Tier-1 no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Q418 | Q119 | Q219 | Q319 | Q419 | Q120 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comment Q318 | Comments Q418 | Comments Q119 | Comments Q219 | Comments Q319 | Comments Q419 | Comments Q120
1.1.1 | 1.2.7 | Fraction of WLCG MoU commitment for CPU 100 % |  | Darren Moore | 100% | 142.7% |  | 107% | 107.3% | 96% | 91.33% | 109% | 119% | >100% | 117% | 120% | >100% | 115% | [8 empty] | Metrics recording process failed for this quarter
1.1.2 | 1.6.3 | % met of GRIDPP T1-RB allocation for CPU 100 % |  | Darren Moore | 100% | 144.3% | 106.7% | 105.3% | 101% | 98% | 86.33% | 93.73% | 118% | >100% | 106% | 106% | >100% | >100% | [8 empty] | Metrics recording process failed for this quarter
1.1.3 |  | Availability of CE service 99 % |  | Darren Moore | 99%
1.1.4 |  | Number of Security Incidents 2 per year |  | David Crook | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [8 empty] | Security Challenge Accepted
1.1.5 |  | # level 3 incidents(newly entered or active) in disaster management system 0 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Escalated problem LHCb had with Castor while running stipping/merging campain. Led to reverting LHCb Castor SRM upgrade.
1.1.6 |  | # level 4 incidents (newly entered or active) in disaster management system 0 |  | Andrew Sansum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7 |  | Percentage of GRIDPP4 Staff in Post 93 % |  | Andrew Sansum | 93% | 90% | 86% | 83% | 87% | 80% | 95% | 98.5% | 99% | 91.88% | 100% | 95.17% | 97.93% | 93.1%
1.2.1 | 1.2.8 | Fraction of WLCG MoU commitment for Disk 100 % |  | Darren Moore | 100% | 202.7% |  | 140% | 152% | 158% | 155% | 150% | 155% | 155% | 126% | 100% | 100% | 100% | [8 empty] | Metrics recording process failed for this quarter
1.2.2 | 1.2.9 | Fraction of WLCG MoU commitment for Tape 100 % |  | Darren Moore | 100% | 100% | 100% | 100% | 100% | 100% | 95% | 100% | 95% | 100% | 100% | 100% | 100% | 100% |  |  |  |  | There was a temporary shortage of tape during this quarter while we were sorting out a procurement of more tape media. During this time the free tape pool reduced and Atlas & CMS deleted some files off tape for us to help. |  |  |  | Metrics recording process failed for this quarter
1.2.3 | 1.6.1 | % met of GRIDPP T1RB Allocation for Tape 100 % |  | Darren Moore | 100% | 104% | 100% | 100% | 98% | 100% | 84% | 89% | 100% | 100%% | 100%% | 100% | 100% | 100% |  |  |  |  | See comment above for metric 1.2.2. |  |  |  | Metrics recording process failed for this quarter
1.2.4 | 1.6.2 | % met of GRIDPP T1RB Allocation for Disk 100 % |  | Darren Moore | 100% | 113.7% |  | 115% | 115% | 112.3% | 96.33% | 116% | 98% | >100% | 107% | 100% | 100% | 100% |  |  |  |  | There has been some delay getting storage into Echo. |  |  |  | Metrics recording process failed for this quarter
1.2.5 | 7.1.3 | # Storage node failures leading to filesystem loss or damage |  | Kashif Hafeez | 2 | 0 | 0 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0
1.2.6 | 7.1.4 | % Lost disk server hours due to hardware problems over deployed base |  | Kashif Hafeez | 1% | 0.29% | 0.3% | 0.1533% | 0.2567% | 0.3767% | 0.26% | 0.41% | <1% | <1% | <1% | < 1% | <1% | <1% | [7 empty] | Difficult to estimate. No disk servers were out in Echo, but an increasing number are having problems in Castor.
1.2.7 | 7.3.1 | Damaged tapes/month, leading to data loss |  | Tim Folkes | 1 | 0 | 0 | 0.33333 | 0 | 0 | 0 | 0.33 | 0 | 1 | 1 | 0 | 0% | 0% | [6 empty] | 6 ATLAS files lost
1.2.8 | 5.1.2 | CASTOR SAM tests: ATLAS VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 92.33% | 92.33% | 98% | 99.33% | 97% | 99.33% | 100% | 99.3% | 98.3% | >99% | 100% | 99.3% | 99.66% | There were several spells of poor test results for Talas. The first (early Feb) coincided with a tape recall exercise and tests time out. There were then two further spells of test failures (late Feb, early March). We identified that the Atlas Test was not specifying a space token on write and then (depending on what else was going on) the file was not found in later stages of the SRM test. | There was a problem around to 30th April/1st May when one of the Atlas disks filled up and we failed tests consistently. There were also intermittent test failures before the Castor Atlas 2.1.16 upgrade which was done on the 25th May. | In first part of quarter there were problems that appeared in the SRMs that were thought to be due to Castor performance issues. The merging of the small AtlasScratchDisk pool into a larger disk pool alleviated these. (See Narrative). |  | Problem with Atlas Castor instance in January. There was a high rate of deletion requests. The back end stager database struggled to keep up with the total load. Found one of the tables in the Atlas stager Castor database was badly fragmented. During an overnight outage this table and the associated indexes was rebuilt and preformance restored.
1.2.9 | 5.1.1 | CASTOR SAM tests: ALICE VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 95.67% | 100% | 100% | 100% | 99.67% | 99.67% | 100% | 100%% | 99% | >99% | 98.07% | 100%% | 100% | Missing ALICE-specific xroot component after Castor 2.1.15 upgrade led to several days of test failure (inlcuing a weekend).
1.2.10 | 5.1.3 | CASTOR SAM tests: CMS VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 97.67% | 89.67% | 94% | 98% | 99.33% | 98% | 92% | 97.3% | 97.3% | 97.3% | 98.72% | 97% | 99.72% | There have been sporadic failures of the CMS SAM tests against the SRMs (timeouts) throught this period. Effort was directed at Castor upgrades (SRM and then Castor itself to improve this). | During this period we had a high level of failure of the CMS SRM SAM tests with timeout errors. There was also some specific test failures on top of this: 9/10/11th April - Problems with CMS Castor (transfermanager); 3rd May: glexec problem; 14/15 May - problems writing into Castor CMS. 24/25 June - test ailing with CMSDisk full. | At the start of the quarter there was a high rate of SRM tests failures (timeouts) but in the middle of the quarter this improved - although we do not know why. (See narrative). The September figure was brought down by CMSDisk becoming full causing a very high rate of SRM test failures for a couple fo days. | Availability brought down by CMSDisk in Castor becoming full over the 5/6 October.
1.2.11 | 5.1.4 | CASTOR SAM tests: LHCb VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 97.33% | 97% | 95.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99.92% | 100% | 100% | Sporadic SRM test failures through the quarter. Some specific problems with the SRM led to more test failures on one or two days. | Test failures dominated by problems in first part of quarter The causes are as detailed in the narrative section. (These led to the reversion of a previous SRM update and a problem with TURLs returned after the Castor upgrade.) | Figure dominated by September availability at 88%. Problem with two disk servers added into Castor gave problems for SAM tests although LHCb did did not report problems. Also noted in Narrative section.
1.2.12 | 7.3.4 | Reliability of tape robot 99 % |  | Tim Folkes | 99% | 100% | 100% | 99.72% | 99.72% | 99.95% | 99.95% | 100% | 100%% | 96% | 96% | 100% | 100% | 100%
1.3.1 | 1.2.2 | WLCG Service Availability Target (set lower by WLCG than MoU, taken from OPS availability) 97 % |  | Darren Moore | 97% | 99.67% | 98.67% | 99.57% | 99.77% | 99.23% | 84.23% | 99.53% | 99%% | [9 empty] | The OPS tests were failing in May and June because of the problems with the Castor Information Provider ("CIP")
1.3.2 | 1.2.11 | WLCG Service Availability for Alice 97 % |  | Darren Moore | 97% | 95.67% | 100% | 100% | 100% | 99.67% | 99.67% | 100% | 98.7% | 99% | 98.7% | 99% | 99% | 99.3% | See comment for metric 1.2.9.
1.3.3 | 1.2.12 | WLCG Service Availability for ATLAS 97 % |  | Darren Moore | 97% | 92.33% | 92.33% | 98% | 99.33% | 97% | 99.33% | 99.67% | 99.3% | 99.3% | 98.7% | 99% | 98% | 100% | See comment for metric 1.2.8. | See comment for metric 1.2.8. | See comment for metric 1.2.8. |  | See comment for metric 1.2.8.
1.3.4 | 1.2.13 | WLCG Service Availability for CMS 97 % |  | Darren Moore | 97% | 97.67% | 89.67% | 94% | 98% | 99.33% | 98% | 91.67% | 97.3% | 97.3% | 96.3% | 97% | 98% | 99.3% | See comment for metric 1.2.10 above. Plus in March CMS CE tests suffered from aa problem with argus plus another when a Hyperviosor failed affecting a number of virtual machines. This in turn affected CMS CE tests. | See comment for metric 1.2.10 | See comment for metric 1.2.10 | See comment for metric 1.2.10
1.3.5 | 1.2.14 | WLCG Service Availability for LHCB 97 % |  | Darren Moore | 97% | 97.33% | 97% | 95.67% | 100% | 100% | 100% | 100% | 100% | 98.6% | 98.6% | 97% | 99% | 100% | See comment for metric 1.2.11. | See comment for metric 1.2.11 | See comment for metric 1.2.11
1.3.6 | 1.2.4 & 1.2.5 | Respond to pager within 2 hours 95 % |  | Darren Moore | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.3.7 | 4.1.2 | Number of GGUS Tickets not responded to within two hours . |  | Darren Moore | 3 per month | 0.33333 | 0.33333 | 2.3333 | 0.33333 | 1.3333 | 0.33333 | 2 | 0 | 1 | 0 | 3 | 0 | 0
1.3.8 | 1.6.4 | Job Efficiency (CPU/Wall) 70 % |  | Darren Moore | 70% | 78.33% | 77.33% | 87.33% | 85% | 84.33% | 84.33% | 87.43% | 82.3% | 76.4% | > 70% | 71.8% | 67.5% | < 70% | [8 empty] | Metrics recording process failed for this quarter |  |  |  | Not clear if the monitoring is accurate. Job efficiency has been poor for numerous reasons. Problems for ALICE when starting to use Echo.
1.3.9 | 1.6.5 | Farm Occupancy 70 % |  | Darren Moore | 70% | 94.33% | 95% | 90.67% | 93% | 93.67% | 92.33% | 94.43% | 97.1% | 75.45% | >70% | 82.08% | 49.34% | 98% | [8 empty] | Metrics recording process failed for this quarter |  |  | We are not convinced this value is valid for Q419
1.3.10 | 1.6.6 | Percentage of available T1 Disk 1 used in quarter 20 % |  | Darren Moore | 20% | 77.33% |  | 46.67% | 53% | 47% | 40.33% | 35.5% | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | Metrics recording process failed for this quarter
1.3.11 | 7.3.5 | Used tape capacity (TB) |  | Tim Folkes | 5416 | 22450 | 23400 | 26433.3333 | 30966.6667 | 34233.3333 | 36543.3333 | 38500 | 41034 | 43100 | 45500 | 48849 | 48780 | 56712.67
NGI
3.4.1 |  | UK CPU and storage delivered to EGI |  | Ian Collier
3.4.2 |  | Monthly timesheets complete by 10th of each month |  | Ian Collier
3.4.3 |  | GridPP staff PM delivered as required |  | Ian Collier
3.4.4 |  | GOCDB Availability |  | Ian Collier | >99% |  |  | 100% | 100% | 99.99% |  | 100% | 100% | 100% | 100% | 100% |  | 99% | Waiting on EGI to publish their stats. A quick look at Nagios over the quarter shows no availability issues. |  |  |  | Source: http://argo.egi.eu/lavoisier/opsmon_reports?accept=html
3.4.5 |  | APEL Availability |  | Adrian Coveney | >99% | 100% | 99% | 100% | 100% | 99% | 100% | 100% | 100% | 100% | 100% | 100% |  | 99.2%

## Milestones
GridPP Quarterly Report |  |  |  | Complete |  | Proposed to be Rescheduled
Area | Tier-1 |  |  | Overdue |  | Likely to be late
Quarter | Q1 2020 |  |  | Not yet due |  | Proposed Milestone change
Reported by | Darren Moore |  |  | Suspended |  | Query
Based on Milestones 1.3d-2
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.4.1 | Produce the purchasing plan | Andrew Sansum | 2016-06-01 |  |  | A purchasing plan swas produced but changes in the amount of money available require the plan to be re-visited.
1.4.2 | FY16 Capacity order placed | Andrew Sansum | 2016-11-01 | 2017-02-01 |  | Order for CPU & disk storage received by vendor mid-Feb.
1.4.3 | FY16 Purchase in production | Andrew Sansum | 2017-04-01 |  |  | CPU in use. Storage in Echo
1.4.4 | Tier-1 WLCG MoU commitments met | Alastair Dewhurst | 2017-05-01 |  |  | As shown in metrics.
1.4.5 | Produce the purchasing plan | Alastair Dewhurst | 2017-06-01 |  |  | Planning completed so that tenders could be issued.
1.4.6 | FY17 Capacity order placed | Alastair Dewhurst | 2017-11-01 |  |  | Tenders issued at end of November. Orders placed January 2018. - technically outside this quarter - but it is now done.
1.4.7 | FY17 Purchase in production | Alastair Dewhurst | 2018-04-01 | 2018-09-01 |  | 50% of CPU in production by June. XMA CPU and all storage still behind.
1.4.8 | Tier-1 WLCG MoU commitments met | Alastair Dewhurst | 2018-05-01 | 2018-09-01 |  | Waiting on CPU delivery, storage is being ramped up slowly.
1.4.9 | Produce the purchasing plan | Alastair Dewhurst | 2018-06-01 | 2018-08-01 |  | Unclear finance situation, new hardware is not in production, so hard to make predictions about what we will need.
1.4.10 | FY18 Capacity order placed | Alastair Dewhurst | 2018-11-01 | 2018-12-01 |  | Disk Tender runs until 7th December. CPU direct award placed in December.
1.4.11 | FY18 Purchase in production | Alastair Dewhurst | 2019-04-01 | 2019-03-01 |  | CPU in production in March. Disk is ready for deployment although it will be phased in slowly as we have plenty of spare capacity currently.
1.4.12 | Tier-1 WLCG MoU commitments met | Alastair Dewhurst | 2019-05-01 | 2019-03-01 |  | Plenty of spare capacity in Echo (even before 18 generation was added). LHCb migrated to Echo in March. ALICE still using Castor.
1.4.13 | Produce the purchasing plan | Alastair Dewhurst | 2019-06-01 | 2019-06-01 |  | Initial plan circulated 4th June 2019.
1.4.14 | FY19 Capacity order placed | Alastair Dewhurst | 2019-11-01 | 2019-11-01 |  | Disk and CPU tenders ended on 25th October. Orders placed in November fro delivery in Janaury 2020.
1.4.15 | FY19 Purchase in production | Alastair Dewhurst | 2020-04-01 | 2020-03-01 |  | Disk delivered in January. CPU delivered in February and entered production in March.
1.4.16 | Tier-1 WLCG MoU commitments met | Alastair Dewhurst | 2020-05-01 | 2020-03-01 |  | Very little change in MoU commitments during long shutdown. Additional disk had been provided to VOs last year. CPU was installed in March.

## Manpower Q419
GridPP Quarterly Report
Area | Tier-1
Quarter | Q1 2020
Reported by | Alastair Dewhurst
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Folkes, Hafeez, Harper, Summers, Lisseev, Hancock, Furnell | 4.71
Tier-1 | Grid | Caballero, Adams, Collier | 2.7
Tier-1 | CASTOR/Tape/CEPH | Appleyard, Johnson, Patargias, McComb, Byrne | 3.1
Tier-1 | Database | Lopez, Packer, Contractor | 1
Tier-1 | Management | Dewhurst | 1
Tier-1 | Production | Moore, Davies | 1.7
Total |  |  | 14.21 |  |  | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL, GOCDB | Coveney, Corbett, Ryall, Nielson | 0.75 | 0.75 | 0.75
Total |  |  | 0.75 | 0.75 | 0.75 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE

## Manpower Q120
GridPP Quarterly Report
Area | Tier-1
Quarter | Q1 2020
Reported by | Alastair Dewhurst
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Folkes, Harper, Summers, Lisseev, Hancock | 4
Tier-1 | Grid | Caballero, Adams, Collier | 2.7
Tier-1 | CASTOR/Tape/CEPH | Appleyard, Johnson, Patargias, McComb, Byrne | 3.1
Tier-1 | Database | Lopez, Hafeez, Packer, Contractor | 1
Tier-1 | Management | Dewhurst | 1
Tier-1 | Production | Moore, Davies | 1.7
Total |  |  | 13.5 |  |  | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL, GOCDB | Coveney, Corbett, Ryall, Nielson | 0.75 | 0.75 | 0.75
Total |  |  | 0.75 | 0.75 | 0.75 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE

## Narrative Q419
GridPP Quarterly Report
Area | Tier-1
Quarter | Q1 2020
Reported by | Darren Moore
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | Tier-1 is currently running " business as usual". No major outages/issues during this period. This has been helped in part by the fact the LHC are not collecting data but this should not distract from the fact RAL Tier-1 is running as it should do.
Management
CPU
Disk
CASTOR | ALICE has been successfully migrated to Echo
ECHO
Grid Deployment
Core Services
Production Team
Network | Major network outage - Friday 13th October impacted Tier-1 services |  | Network outage resolved after discovery of faulty router managed by JANET.
Machine Room Operations
Database team
APEL | No major problems encountered. Service ran smoothly during this period. Response time for GGUS tickets within OLA.
GOCDB
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource.This may prove to be impossible or require more effort than available. |  | Close engagement with UKT0 project.
Insitute or area specific risks
Risk |  | Mitigating Action
CERN will stop support for Castor. |  | CERN have announces a replacement for Castor (for tape). An evaluation of the best way forward for future tape storage is being made.
CEPH ECHO will not deliver storage reliably or be able to deliver the necessary access bandwidth. |  | Tight management of the ECHO project is carefuly monitoring progress. There has been one notable data loss incident. However, experience so far corroborates that expected from the risk register. Atlas and CMS have now switched to using Echo and it is delivering sufficient bandwidth. Any bandwidth limitations are in the gateways and here we are providing gateways on each of our worker nodes as well as the general usage ones. This risk is diminishing as operational experience builds.
Oracle withdraw support for existing Tape infrastructure. |  | No indication from Oracle that existing tape infrastructure will end of life. Maintain close links with Oracle in order to identify any future issues.
GridPP5 Staffing plan requires Tier-1 to reduce staff effort to 14.5 FTE in FY18. Potential impact on Tier-1 operation. |  | Attempt to maintain average staff level closer to 100%. Identify further mitigations to improve STFC recruitment and retention. Seek financial reprofile of FY17 underspend. Cut costs where feasible through terminating services and reducing costs.
Staffing recruitment and retention remains very problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level. Recent departures, coupled with difficulties recruiting make this risk more acute.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
1.4.11 FY18 Purchases in production |  | Apr '19 |  | CPU in production in March. Disk is ready for deployment although it will be phased in slowly as we have plenty of spare capacity currently.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
1.4.12 Tier-1 WLCG MoU commitments met |  | May '19
1.4.13 Produce the purchasing plan |  | June '19
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q120
GridPP Quarterly Report
Area | Tier-1
Quarter | Q1 2020
Reported by | Darren Moore
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | With regards remote working at end of Q1 2020 this has proved Tier-1 as resiliant and adaptable. Tier-1 is currently running " business as usual". No major outages/issues during this period.
Management |  |  | Keeping in line with government guide lines regards COVID-19 the Tier-1 is now working in a remote configuaration.
CPU
Disk
CASTOR
ECHO
Grid Deployment
Core Services
Production Team | As part of business continuity Tier-1 ran Operation "Home Guard". A two day exercise whereby Tier-1 adopted a remote working posture to ensure the technically feasibility of Tier-1 to operate successfully whilst geographcally distributed. The findings and results of this exercise were implement again "for real" at the end of March 2020.
Network
Machine Room Operations
Database team
APEL | No major problems encountered. Service ran smoothly during this period. Response time for GGUS tickets within OLA.
GOCDB
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource.This may prove to be impossible or require more effort than available. |  | Close engagement with UKT0 project.
Insitute or area specific risks
Risk |  | Mitigating Action
CERN will stop support for Castor. |  | CERN have announces a replacement for Castor (for tape). An evaluation of the best way forward for future tape storage is being made.
CEPH ECHO will not deliver storage reliably or be able to deliver the necessary access bandwidth. |  | Tight management of the ECHO project is carefuly monitoring progress. There has been one notable data loss incident. However, experience so far corroborates that expected from the risk register. Atlas and CMS have now switched to using Echo and it is delivering sufficient bandwidth. Any bandwidth limitations are in the gateways and here we are providing gateways on each of our worker nodes as well as the general usage ones. This risk is diminishing as operational experience builds.
Oracle withdraw support for existing Tape infrastructure. |  | No indication from Oracle that existing tape infrastructure will end of life. Maintain close links with Oracle in order to identify any future issues.
GridPP5 Staffing plan requires Tier-1 to reduce staff effort to 14.5 FTE in FY18. Potential impact on Tier-1 operation. |  | Attempt to maintain average staff level closer to 100%. Identify further mitigations to improve STFC recruitment and retention. Seek financial reprofile of FY17 underspend. Cut costs where feasible through terminating services and reducing costs.
Staffing recruitment and retention remains very problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level. Recent departures, coupled with difficulties recruiting make this risk more acute.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
1.4.11 FY18 Purchases in production |  | Apr '19 |  | CPU in production in March. Disk is ready for deployment although it will be phased in slowly as we have plenty of spare capacity currently.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
1.4.12 Tier-1 WLCG MoU commitments met |  | May '19
1.4.13 Produce the purchasing plan |  | June '19
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes