## Metrics
GridPP Tier-2 Quarterly Report | [6 empty] | OK
Tier-2 | SouthGrid | [5 empty] | Close to target
Quarter | Q1 2020 | [5 empty] | Not OK
Reported by | Pete Gronbech | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Target | Birmingham |  |  | Bristol |  |  | Cambridge |  |  | Oxford |  |  | RALPP |  |  | Sussex |  |  | Overall |  |  | Comments
|  |  | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current | Q-2 | Q-1 | Current
.x.1 | % of promised (by that time) disk available to GridPP | 100% | 140.4% | 140.4% | 140.4% | 186% | 186% | 368.8% | 144% | 144% | 144% | 172.8% | 169.1% | 169.1% | 171.7% | 171.7% | 171.7% | 179.5% | 179.5% | 179.5% | 165% | 164.4% | 181.1%
.x.2 | % of promised (by that time) CPU available | 100% | 274% | 274% | 274% | 215.6% | 215.6% | 215.6% | 176.3% | 176.3% | 176.3% | 215.1% | 197.6% | 197.6% | 213.2% | 213.2% | 213.2% | 181.9% | 181.9% | 181.9% | 216.7% | 211.8% | 211.8%
.x.3 | Average SAM availability performance over the last quarter | 95% averaged over sites in Tier-2 | 42% | % | % | 100% | 97.9% | 97.9% | 100% |  |  | 100% | 87.49% | 100% | 93% | 96.9% | 100% | 99% | 23.21% | 0% | 89% | 76.38% | 74.48% | Bham decommisiioning …
.x.4 | Average SAM reliability performance over the last quarter | 95% averaged over sites in Tier-2 | 42% |  |  | 100% | 99.39% | 99.39% | 100% |  |  | 100% | 89.21% | 100% | 93% | 98.5% | 100% | 99% | 23.21% | 0% | 89% | 77.58% | 74.85% | Bham, Cam no data Sussex no data from Nov & Dec.
.x.5 | Approx. CPU utilisation (wall clock time) | 50% | 59.2% | 70.7% | 63.53% | 58.68% | 73.94% | 67.37% | 112.5% | 113% | 79.78% | 83.99% | 86.06% | 90.9% | 100.8% | 96.04% | 104.3% | 35.18% | 0% | 0% | 83.12% | 83.98% | 84.05%
.x.6 | Approx. CPU utilisation (CPU time) | 50% | 48.88% | 64.87% | 50.83% | 42.5% | 59.39% | 54.1% | 78.62% | 83.77% | 50.88% | 77.49% | 76.45% | 79.29% | 80.41% | 72.42% | 77.42% | 25.96% | 0% | 0% | 68.16% | 68.47% | 65.95%
https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES
.x.3/.4 | http://argo.egi.eu/lavoisier/site_reports?accept=html
summarised here | http://pprc.qmul.ac.uk/~lloyd/gridpp/argo.html

## Resources
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2020
Reported by | Pete Gronbech
Current Site Status Data
Site | Service Nodes | Worker Nodes |  | Local Network Connectivity | Site Connectivity | SRM |  | CPU hours (HEPSPEC06 ) | [5 empty] | Wall clock hours (Normalised elapsed time HS06 hours*no of processors)
[8 empty] | Site | 2020-01-01 | 2020-02-01 | 2020-03-01 | Total |  | Site | 2020-01-01 | 2020-02-01 | 2020-03-01 | Total
Birmingham | UMD4 | VAC |  | 10Gb/s | 10Gb/s | DPM 1.8
Bristol | UMD4 | EMI 3+UMD4 |  | 10Gb/s | 5Gb/s | NO SRM |  | Birmingham | 8430542.0804 | 8080423.7321 | 5918389.28 | 22429355.0925 |  | Birmingham | 10352995.5274 | 9710042.1111 | 7970847.7529 | 28033885.3914
Cambridge | UMD 4/C7 | VAC/CS7 |  | 10Gb/s | 2*20Gb/s | No SE |  | Bristol | 4979559.5951 | 6626403.1929 | 5813186.4133 | 17419149.2013 |  | Bristol | 5641891.5948 | 8530849.5639 | 7521292.0781 | 21694033.2368
Oxford | UMD 4 | UMD 4 |  | 10Gb/s | 2*20Gb/s | DPM 1.9.2 |  | Cambridge | 3979990.9631 | 4704717.6563 | 1180106.6524 | 9864815.2718 |  | Cambridge | 6915318.4726 | 6591821.7209 | 1962617.6607 | 15469757.8542
RALPP | UMD4 | UMD3 |  | 2X10Gb/s | 100Gb/s | Dcache 3.2.41 |  | Oxford | 20190427.5406 | 18490875.9643 | 19908898.2508 | 58590201.7557 |  | Oxford | 23205308.6066 | 21246066.0767 | 22718118.175 | 67169492.8583
Sussex | UMD4/EMI3 | UMD4 |  | 40Gb/s | 2x10Gb/s | Storm /Lustre |  | RALPP | 24157056.3461 | 23532727.7247 | 30601481.3699 | 78291265.4407 |  | RALPP | 34227073.554 | 30578386.2645 | 40638239.3967 | 105443699.2152
[8 empty] | Sussex | 0 | 0 | 0 | 0 |  | Sussex | 0 | 0 | 0 | 0
[8 empty] | Total CPU hrs | 61737576.5253 | 61435148.2703 | 63422061.9664 | 186594786.762 |  | Total | 80342587.7554 | 76657165.7371 | 80811115.0634 | 237810868.5559
Current Resources Available
| Total available to GridPP |  | Promised (GridPP MoU 2019) |  | CPU calculations
Site | HEPSPEC06 | Storage (TB) | CPU (HS06) | Storage (TB) | % of MoU CPU | % of MoU Disk | % CPU of Tier-2 | % Storage of Tier-2 | HS06 CPU hours from accounting | % of T2 CPU hours provided for the quarter | No of hours per quarter approx | Multiplied by HS06 at site | Utilisation of site CPU hours | Utilisation of site Wall clock hours | job efficiency
Birmingham | 20206 | 1000 | 7375 | 712 | 274% | 140.4% | 15.6% | 16.74% | 22429355.0925 | 12.02% | 2184 | 44129904 | 50.83% | 63.53% | 80.01%
Bristol | 14744 | 1110 | 6839 | 301 | 215.6% | 368.8% | 11.38% | 18.58% | 17419149.2013 | 9.335% | 2184 | 32200896 | 54.1% | 67.37% | 80.29%
Cambridge | 8878 | 265 | 5035 | 184 | 176.3% | 144% | 6.853% | 4.435% | 9864815.2718 | 5.287% | 2184 | 19389552 | 50.88% | 79.78% | 63.77%
Oxford | 33834 | 920 | 17126 | 544 | 197.6% | 169.1% | 26.12% | 15.4% | 58590201.7557 | 31.4% | 2184 | 73893456 | 79.29% | 90.9% | 87.23%
RALPP | 46300 | 2610 | 21712 | 1520 | 213.2% | 171.7% | 35.74% | 43.68% | 78291265.4407 | 41.96% | 2184 | 101119200 | 77.42% | 104.3% | 74.25%
Sussex | 5584 | 70 | 3069 | 39 | 181.9% | 179.5% | 4.31% | 1.172% | 0 | 0% | 2184 | 12195456 | 0% | 0% | #DIV/0!
Totals | 129546 | 5975 | 61156 | 3300 | 211.8% | 181.1% | 100% | 100% | 186594786.762 | 100% | 2184 | 282928464 | 65.95% | 84.05% | 78.46%
[10 empty] | Q1 | 2160/2184 (if leap year)
[10 empty] | Q2 | 2184
[6 empty] | REBUS CPU HS06 | REBUS DISK |  |  | Q3 | 2208
[10 empty] | Q4 | 2208
[5 empty] | Birmingham | 22433 | 980
[5 empty] | Bristol | 9607 | 0
[5 empty] | Cambridge | 5940 | 293
[5 empty] | Oxford | 26240 | 940
[5 empty] | RALPP | 42840 | 3079
[5 empty] | Sussex | 2006 | 83
Note on F15: Windows User: Active Passive
Note on F17: gronbech: HPC capped at 5Gbit/s
Note on D30: gronbech: Sussex may have promised 2000 by email.?

## VOs
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2020
Reported by | Pete Gronbech
Vos Supported
Supported VOs
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cern@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total
Birmingham | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 |  | 1 | 0 | 0 | 1 | 0 | 1 | 1 |  | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 21
Bristol | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1 | 14
Cambridge | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Oxford | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 23
RALPP | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 |  | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 |  | 1 | 0 | 1 | 0 | 0 | 1 | 31
Sussex |  | 1 | [8 empty] | 1 | [21 empty] | 1 |  |  |  |  | 0 | 1 | 1 | [7 empty] | 5
[47 empty] | 0 | 0
[47 empty] | 0 | 0
Total | 4 | 6 | 0 | 2 | 2 | 2 | 1 | 1 | 2 | 4 | 6 | 3 | 2 | 2 | 0 | 3 | 1 | 5 | 2 | 1 | 4 | 1 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 4 | 1 | 1 | 6 | 3 | 1 | 0 | 0 | 1 | 3 | 6 | 1 | 1 | 0 | 2 | 0 | 0 | 4 | 102
Storage resource in use per VO (TB)
Site | alice | atlas | babar | biomed | calice | camont | cdf | cedar | cer@school | cms | dteam | dune | dzero | esr | euindia | fusion | geant4 | gridpp | hone | hyperk | ilc | Landslides | lhcb | lsst | LZ | mice | magic | minos | na48 | na62 | neurogrid | ngs | ops | pheno | planck | ralpp | sixt | skatelescope.eu | snoplus | southgrid | solid | superb | supernemo | t2k | total | totalep | zeus | Total | Percentage SouthGrid Disk used | Site percentage non LHC
Birmingham | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 19.83% | 0%
Bristol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.1 | 0.007 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0.002 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 384.109 | 7.626% | 0.001822%
Cambridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Oxford | 0 | 677 | 0 | 0 | 0 | 0.024 | 0 | 0 | 0 | 1.01 | 0.04 |  | 0.049 | 0.59 | 0 | 0.049 | 0 | 0.0035 | 0.036 |  | 0.004 | 0 | 0.0038 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.033 | 0 | 0 | 0 | 0 | 2.61 | 0.018 |  | 0.016 | 1.5 | 33.6 | 0 | 0 | 0.02285 | 716.6091 | 14.23% | 5.386%
RALPP | 0 | 672 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1743 | 0.25 | 0 | 0 | 0.14 | 0 | 0.08 | 0 | 0 | 0.03 |  | 1.6 | 0 | 371 |  | 48 | 44 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.03 | 0.7 | 1 | 0 | 0 | 0.65 | 2886.06 | 57.3% | 3.467%
Sussex |  | 50 | [8 empty] | 0.01 | [5 empty] | 0 | [14 empty] | 0 |  |  |  |  | 1 | [10 empty] | 51.01 | 1.013% | 1.98%
Total | 999 | 1399 | 2 | 1 | 0 | 0.024 | 0 | 0 | 0 | 2128.11 | 0.307 | 0 | 0.049 | 0.73 | 0 | 0.129 | 0 | 0.0035 | 0.066 | 0 | 1.604 | 0 | 371.0058 | 0 | 48 | 44 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063 | 0 | 0 | 1 | 0 | 2.61 | 0.018 | 0 | 0.046 | 2.2 | 34.6 | 0 | 0 | 0.67285 | 5036.7882 | 100% | 2.773%
red is old data

## Manpower
GridPP Tier-2 Quarterly Report
Tier-2 | SouthGrid
Quarter | Q1 2020
Reported by | Pete Gronbech
Effort (FTE)
|  | GridPP Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Birmingham | Mark Slater | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
Bristol | Winnie Lacesso | Unfunded Month 1: 0.2; Unfunded Month 2: 0.2; Unfunded Month 3: 0.2
| Luke Kreczko | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Cambridge
| John Hill | 0 | 0 | 0 | 0 | 0 | 0
Oxford
| Vip Davda | GridPP Funded Month 1: 0.7; GridPP Funded Month 2: 0.7; GridPP Funded Month 3: 0.7
| Mike Leech | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
RALPP | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
| Chris Brew | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3
Sussex | [7 empty] | red text last quarters figures
| J Maris | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
| Leo Rojas | Unfunded Month 1: 0.1; Unfunded Month 2: 0.1; Unfunded Month 3: 0.1
Total |  | 2.2 | 2.2 | 2.2 | 1.2 | 1.2 | 1.2
EGI Funded Posts (FTE)
|  | EGI Funded |  |  | Unfunded
Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3

## Narrative
GridPP Quarterly Report
Area | SouthGrid
Quarter | Q1 2020
Reported by | Pete Gronbech
Progress over last Quarter
Site/area | Successes |  | Problems/Issues
Birmingham | Completed work on XCache setup for Atlas with two storage nodes. Continued move of Tier 3 resources to different server room to allow all workers to be run and provide more space for equipment purchases currently being made.
Bristol | The 19 new WN with 4 x 14TB disk each added net 532TB to Bristol HDFS Storage! |  | OS load+config fine & storage fine, but htcondor-8.8 does not work on them. (explain below)
Cambridge
Oxford | Retired a pool node so the disks can be used for spares. Purchased: 7 x PowerEdge R6525 - Compute nodes 1 x PowerEdge R6515 - perfSoNAR server. Still awaiting delivery of Compute Nodes. Upgraded ARC CE to 6. |  | Old storage pool nodes disks are becoming more unreliable. Cache battery failing on 6 pool nodes. Upgrading storage pool nodes from SL6 to CentOS 7? -- may have to go diskless site and retire all storage.
RALPP | New Worker Nodes: 2 Quads, 8 nodes, 128 4GB slots per node New disk servers: 2 Nodes, 2 100TB Pools per node |  | Old disk servers becoming more unreliable – may need to retire storage
Sussex |  |  | We are still migrating to centOS7 and ARC CE6. I had to scrap the legacy cluster with Cream CE/Argus etc and SL6 when the hard deadline happened for the centOS7 update (about one month after starting the job at Sussex). I currently only have the ARC CE6 and two worker nodes in our new HPC cluster which are successfully running pilot test jobs then lock-down happened and I haven't been able to move the legacy nodes or install the new GridPP worker nodes, the aggregation network switch and the PerfSonar box. This week I have finally been granted access to the data centre and have started installing the new kit and moving legacy nodes so hopefully in a few weeks time I should be able to install and provision all the GridPP equipment.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Shortage of manpower at some sites |  | Regular ops meetings and SouthGrid help, dispite streched staff at all sites.
Insitute or area specific risks
Risk |  | Mitigating Action
Lack of GridPP funded staff at Bristol and Sussex a continues to be a concern.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Bristol: (not in 19Q4 report) Last of 2019 funding spent (instead of +1WN) on replacing 2 x 64GB-RAM HDFS NameNodes with new 2 x 192GB-RAM hardware. |  | 2020-03-31 |  | Nodes arrived, racked. Not by 31/03/2020 OS-load or configure. IT Admin mandatory Change Control re configure = convoluted pain.
Bristol: Further work on replacement of dmlite SE with xrootd-only SE |  | 2020-03-31 |  | A small amount of progress was made but everyone was too low on time to work much on it :[ (We expect MUCH more progress by end of 20Q2)
Bristol: Replacement of 7-OS IPv6 perfsonar BW+LAT with GridPP provided hardware |  | 2020-03-31 |  | The hardware from RAL may have been delivered late 03 or early 04 but due to C19 (building closure) at the moment its location is unknown :[
Bristol: Get new WN into production |  | 2020-03-31 |  | Output = 532TB added HDFS Storage in production! But not compute: htcondor 8.6 works on one of the new WN, but all htcondor 8.8 WN do not work. Dr Kreczko was low on time to debug. In the meantime there was no big pressing need for new WN cores.
Oxford: Buy CPU from GridPP Hardware grant |  | 03/31/2019 |  | Purchased but not yet delivered from Oxford warehouse.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
RALPP: Upgrade site-bdii to C7 |  | 2018-12-31 |  | On hold - awaiting clarity on the future of the BDII
Bristol: bring HTCondor-8.8 CE lcgce02 into testing & then production. Dr Kreczko says our htcondor-8.8 WN don't work due to old ARC-CE version on lcgce01. Rather than argue with that he wants to abandon ARC-CE & try 7-OS HTCondor CE lcgce02 (now that Dr Steve Jones has got the Accounting part working). ) |  | 2020-09-30 |  | 7-OS HTContor-8.8 CE lcgce02 prod, retire 6-OS ARC-CE lcgce01
Bristol: upgrade all WN to 7-OS HTCondor 8.8 |  | 2020-11-30 |  | Once htcondor-8.8 CE is working, the new HTCondor-8.8 WN should work. Then start rebuilding all 6-OS htcondor-8.6 WN as 7-OS htcondor-8.8 WN.
Bristol: hardware upgrades to current Bristol GridFTP server io02 |  | 2020-06-30 |  | io02 will have +1CPU & +128GB RAM = total 384GB RAM. *Assuming* humans are by that date allowed in building eg Dell Engineer to do install.
Bristol: Further work on replacement of dmlite SE with xrootd-only SE |  | 2020-09-30 |  | Asymptotically approach status of lcgse01 retired & io02 becomes The Bristol xrootd-only sort-of SE! (Dr Skipsey says tecchnically it's not an SE but it will be the only storage service node at Bristol.)
Bristol: Completion of replacing existing HDFS NameNodes |  | 2020-06-30 |  | Old 6-OS nn+jt retire replaced by production 7-OS nn00+01
EVAL Notes
Publications |  | Date |  | Notes
Collaborations |  | Date |  | Notes
Further Funding (eg external grants) |  | Date |  | Notes
Destination of ex staff and recruitment issues |  | Date |  | Notes
Dissemmination events |  | Date |  | Notes
Intellectual Property |  | Date |  | Notes
Spin out companies |  | Date |  | Notes
Roles held on committees and boards |  | Date |  | Notes
Pete Gronbech |  | Current |  | Chairman HEPSYSMAN
Pete Gronbech |  | Current |  | Member of HEPiX Board
Other outputs and Knowledge |  | Date |  | Notes