## Resource & Narrative
Year | 2020 | Area | LondonGrid
Quarter | Q4 | Reporter | DR
Narrative
Area | Successes |  |  | Problems
Brunel | Tender started to buy - network update . update switches out of warranty . bring in fabric capable of doing 100G both internally and externally - storage . preparation to move out of DOME |  |  | Significant network problems. From 19 Dec to 10 Jan, only ~20% of worker nodes in production.
Imperial
QMUL | We ran a tender for new compute (Dell won with intel 6248R CPUs). After Christmas we have reinstalled all GridPP servers and started up the compute service. Only the main StoRM frontend is running on SL6 now. |  |  | We were well in to the process of migrating to CentOS7 from SL6. However a firmware bug in the SSDs of our PROXMOX cluster (running the ceph journal) caused both the running and backup images of all VMS on the cluster, including the DNS, DHCP, deployment server, arcce, argus, bdii, and development nodes to fail. We were able to re commission part the old (SL6) deployment server and reinstall the PROXMOX VM cluster rebuild the DNS and dhcp servers to get the storage up and running before Christmas ( The StoRM SEs are on real servers). We also had an extended power down in December due to overrunning essential engineering works! To take advantage of a planned weekend power down in the building hosting the cluster it was decided to replace the power distribution boards in preparation for major upgrades due in 2021 for the data centre hosting the GridPP cluster. These were planned to take a week but were extended to replace all power wiring in the data centre when the existing infrastructure was found to have aged badly. More disruption expected for 2021 as they refurnish the data centre but that should leave us in a good position for the next 10 years.
RHUL | Migration to C7 almost done. Still some remaining services. |  |  | Some intermittent problems with switches. Production records affected by sbdii migration and a problem with a very early stage of Hadoop. However, production itself wasn’t affected but our reliability/availability levels dropped a bit.
Risks
Type | Risk |  |  | Mitigation
Brunel
Imperial
QMUL
RHUL | WAN connection to Janet is insufficient for site to operate effectively as non-storage site
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 1 | 100% | 5% | 324.3% | MOK | % of WLCG Pledged CPU Available - LondonGrid |  |  | Metric OK | MOK
1b | 5 | 100% | 5% | 224.6% | MOK | % of WLCG Pledged Disk Available - LondonGrid |  |  | Metric Clost to Target | MCT
1b | 9 | 50% | 5% | 72.29% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid | Brunel only 27% utilisation due to network problems |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 89.37% | MFL | Average Argo Availability - LondonGrid | QMUL power down in December |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 90.77% | MCT | Average Argo Reliability - LondonGrid | QMUL power down in December

## Resources
Please fill in all fields highlighed in
Capacities | Brunel | Imperial | QMUL | RHUL | Total | Notes
CPU Available (HS06) | 52831 | 113946 | 85000 | 56000 | 307777 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 19770 | 22156 | 26991 | 25984 | 94901
% of Pledge | 267.2% | 514.3% | 314.9% | 215.5% | 324.3%
Storage Available (TB) | 1500 | 8129 | 5000 | 1300 | 15929
Storage Pledged (TB) | 918 | 2794 | 3379 | 685 | 7091
% of Pledge | 163.4% | 290.9% | 148% | 189.8% | 224.6%
Availability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 98.52 | 100 | 100 | 99.97 | 99.62% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 87.86 | 100 | 98.98 | 72.22 | 89.77% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 18.13 | 96.81 | 78.73%
% Tier-2 Averge | 95.46 | 100 | 72.37 | 89.6667 | 89.37%
Reliability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 98.52 | 100 | 100 | 99.97 | 99.62% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 95.41 | 100 | 98.98 | 73.66 | 92.01% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 100 | 100 | 23.43 | 99.22 | 80.66%
% Tier-2 Total | 97.9767 | 100 | 74.1367 | 90.95 | 90.77%
CPU Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 116650848 | 251592768 | 187680000 | 123648000 | 679571616 | https://accounting.egi.eu/tier2/federation/London Tier 2/normcpu/SITE/DATE/2020/10/2020/12/all/localinfrajobs/
Hours per quarter:
Month 1 | 9190802.6382 | 60827430.4554 | 48557204.297 | 30340983.15 | 148916420.5406 | Q1: 2160/2184 (if leap year)
Month 2 | 6830522.9401 | 61593069.2861 | 68515861.61 | 33437736.2027 | 170377190.0389 | Q2: 2184
Month 3 | 6817405.8236 | 60253839.8161 | 11805449.0156 | 31652933.5804 | 110529628.2357 | Q3: 2208
Total: | 22838731.4019 | 182674339.5576 | 128878514.9226 | 95431652.9331 | 429823238.8152 | Q4: 2208
% Utilisation | 19.58% | 72.61% | 68.67% | 77.18% | 63.25%
WallClock Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 116650848 | 251592768 | 187680000 | 123648000 | 679571616 | https://accounting.egi.eu/tier2/federation/London Tier 2/normelap_processors/SITE/DATE/2020/10/2020/12/all/localinfrajobs/
Hours per quarter:
Month 1 | 12110146.0359 | 77058650.7417 | 46369465.7499 | 35057553.6388 | 170595816.1663 | Q1: 2160/2184 (if leap year)
Month 2 | 9676987.0407 | 76396918.2362 | 63842817.9428 | 34797282.9193 | 184714006.139 | Q2: 2184
Month 3 | 9426349.6653 | 77447686.3119 | 11185913.7533 | 37895473.9167 | 135955423.6472 | Q3: 2208
Total: | 31213483 | 230903255 | 121398197 | 107750310 | 491265245.9525 | Q4: 2208
% Utilisation | 26.76% | 91.78% | 64.68% | 87.14% | 72.29%
Storage LHC & IRIS: AVAILABLE (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 32.98 | 0 | 4450 | 1055 | 5537.98 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 1429 | 4058.129 | 1 | 2.2 | 5490.329 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 710 | 300 | 0 | 1010
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 1204 | 0 | 0 | 1204
Storage LHC & IRIS: USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 29.68 | 0 | 7322 | 781 | 8132.68 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 893 | 3486.319 | 0.5 | 1.57 | 4381.389 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 3.2314e-08 | 487 | 255 | 0 | 742
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 718.8 | 0 | 0 | 718.8
Storage - Other : USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
biomed | 0.357 | 0 | 0.5 | 0 | 0.857 | Active VOs at you site can be assesed from the following link:
comet.j-parc.jp | 0 | 39.4 | 0 | 0 | 39.4 | https://accounting.egi.eu/tier2/federation/London Tier 2/njobs/VO/DATE/2020/10/2020/12/all/localinfrajobs/
dune | 0 | 248.8 | 5 | 0 | 253.8 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
gridpp | 0.5 | 0 | 10 | 0 | 10.5 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
ilc | 0 | 0 | 0 | 0 | 0
lsst | 0 | 77.8 | 5 | 0 | 82.8
lz | 0 | 810.49 | 0.5 | 0 | 810.99
na62.vo.gridpp.ac.uk | 0 | 0 | 0 | 0 | 0
pheno | 0.008 | 0 | 0.5 | 0 | 0.508
skatelescope.eu | 0 | 0 | 10 | 0 | 10
snoplus.snolab.ca | 0 | 0 | 10 | 0 | 10
solidexperiment.org | 0 | 467.9 | 0 | 0 | 467.9
t2k.org | 0 | 59.11 | 125 | 0 | 184.11
vo.complex-systems.eu | 0 | 0 | 0 | 0 | 0
vo.cta.in2p3.fr | 0 | 0 | 0 | 0 | 0
supernemo | 0 | 0 | 0 | 0 | 0
mice | 9.6 | 0 | 0 | 0 | 9.6
vo.moedal.org | 0 | 0 | 5 | 0 | 5
fusion | 0 | 0 | 0 | 0 | 0
cernatschool.org | 0 | 0 | 0.5 | 0 | 0.5
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes