## Resource & Narrative
Year | 2020 | Area | LondonGrid
Quarter | Q3 | Reporter | DR
Narrative
Area | Successes |  |  | Problems
Brunel | We do have some 20-30% extra of new CPU cores and 200 TB of disk ready to be installed. |  |  | Unable to access machine room (DC2).
Imperial
QMUL | New cooling installed in data centre replacing old units that broke at start of lockdown. Easing of lock down rules allowed more than one person in room. As a result we were finally were able to install and commission Lenovo worker nodes. Completed the migration to new Lustre file system (2.8 -> 2.12) and new storage hardware. No reported issues from VOs Commissioned new DNS and DHCP servers, Added IPv6 to worker nodes. Decommissioned old Dell R510 and C6100 nodes Started tender process for next batch of Compute and Storage. (will physically replace the R510 and C6100s) |  |  | SL6 mitigation Have replacement of most world facing nodes using CentOS7 ready to deploy New version of StoRM is out supporting CentOS7 and TPT, we are working to deploy this.
RHUL |  |  |  | Problems with APEL accounting still going on. Some intermittent problems with our network. Didn’t affect much production. C6 to C7 migration of some services still on going.
Risks
Type | Risk |  |  | Mitigation
Brunel
Imperial
QMUL
RHUL
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 1 | 100% | 5% | 293.8% | MOK | % of WLCG Pledged CPU Available - LondonGrid |  |  | Metric OK | MOK
1b | 5 | 100% | 5% | 229.2% | MOK | % of WLCG Pledged Disk Available - LondonGrid |  |  | Metric Clost to Target | MCT
1b | 9 | 50% | 5% | 60.07% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 96.65% | MOK | Average Argo Availability - LondonGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 98.82% | MOK | Average Argo Reliability - LondonGrid

## Resources
Please fill in all fields highlighed in
Capacities | Brunel | Imperial | QMUL | RHUL | Total | Notes
CPU Available (HS06) | 52831 | 84975 | 85000 | 56000 | 278806 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 19770 | 22156 | 26991 | 25984 | 94901
% of Pledge | 267.2% | 383.5% | 314.9% | 215.5% | 293.8%
Storage Available (TB) | 1800 | 8150 | 5000 | 1300 | 16250
Storage Pledged (TB) | 918 | 2794 | 3379 | 685 | 7091
% of Pledge | 196.1% | 291.7% | 148% | 189.8% | 229.2%
Availability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 99.91 | 99.97 | 98.21 | 100 | 99.52% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 98.25 | 100 | 99.93 | 99.82 | 99.5% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.78 | 99.41 | 64.47 | 100 | 90.91%
% Tier-2 Averge | 99.3133 | 99.7933 | 87.5367 | 99.94 | 96.65%
Reliability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 99.91 | 99.97 | 98.21 | 100 | 99.52% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 98.25 | 100 | 99.93 | 99.82 | 99.5% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.78 | 99.41 | 90.51 | 100 | 97.42%
% Tier-2 Total | 99.3133 | 99.7933 | 96.2167 | 99.94 | 98.82%
CPU Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 116650848 | 187624800 | 187680000 | 123648000 | 615603648 | https://accounting.egi.eu/tier2/federation/London Tier 2/normcpu/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 10749516.0729 | 50062769.2894 | 29215738.2307 | 38505182.4917 | 128533206.0847 | Q1: 2160/2184 (if leap year)
Month 2 | 2422.1569 | 48611444.3748 | 26319585.7544 | 35783402.6527 | 110716854.9388 | Q2: 2184
Month 3 | 0 | 47742599.697 | 15297046.5558 | 32921359.3334 | 95961005.5862 | Q3: 2208
Total: | 10751938.2298 | 146416813.3612 | 70832370.5409 | 107209944.4778 | 335211066.6097 | Q4: 2208
% Utilisation | 9.217% | 78.04% | 37.74% | 86.71% | 54.45%
WallClock Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 116650848 | 187624800 | 187680000 | 123648000 | 615603648 | https://accounting.egi.eu/tier2/federation/London Tier 2/normelap_processors/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 14115689.9939 | 59565794.3746 | 23650701.0928 | 40226377.0223 | 137558562.4836 | Q1: 2160/2184 (if leap year)
Month 2 | 2616.3347 | 58319414.9809 | 24871305.6224 | 39629092.1583 | 122822429.0963 | Q2: 2184
Month 3 | 0 | 57164550.9108 | 14362513.0957 | 37867625.175 | 109394689.1815 | Q3: 2208
Total: | 14118306.3286 | 175049760.2663 | 62884519.8109 | 117723094.3556 | 369775680.7614 | Q4: 2208
% Utilisation | 12.1% | 93.3% | 33.51% | 95.21% | 60.07%
Storage LHC & IRIS: AVAILABLE (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 33 | 0 | 4250 | 1055 | 5338 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 1429 | 4071.572 | 1 | 0 | 5501.572 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 710 | 300 | 0 | 1010
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 1204 | 0 | 0 | 1204
Storage LHC & IRIS: USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 30 | 0 | 3655 | 752.3 | 4437.3 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 884 | 3631.272 | 3.5 | 1.7 | 4520.472 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 3.2314e-08 | 480 | 250 | 0 | 730
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 678.6 | 0 | 0 | 678.6
Storage - Other : USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
biomed | 0.36 | 0 | 0.5 | 0 | 0.86 | Active VOs at you site can be assesed from the following link:
comet.j-parc.jp | 0 | 39.35 | 0 | 0 | 39.35 | https://accounting.egi.eu/tier2/federation/London Tier 2/njobs/VO/DATE/2020/7/2020/9/all/localinfrajobs/
dune | 0 | 249 | 0 | 0 | 249 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
gridpp | 0.5 | 0 | 10 | 0 | 10.5 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
ilc | 0 | 0 | 0 | 0 | 0
lsst | 0 | 77.8 | 0.18 | 0 | 77.98
lz | 0 | 771 | 0 | 0 | 771
na62.vo.gridpp.ac.uk | 0 | 0 | 0 | 0 | 0
pheno | 0.008 | 0 | 0.5 | 0.02 | 0.528
skatelescope.eu | 0 | 0.05 | 0.18 | 0 | 0.23
snoplus.snolab.ca | 0 | 0 | 10 | 0 | 10
solidexperiment.org | 0 | 410.47 | 0 | 0 | 410.47
t2k.org | 0 | 59.11 | 200 | 0 | 259.11
vo.complex-systems.eu | 0 | 0 | 0 | 0 | 0
vo.cta.in2p3.fr | 0 | 0 | 0 | 0 | 0
supernemo | 0.25 | 0 | 0 | 0 | 0.25
mice | 9.6 | 0 | 0 | 0 | 9.6
vo.moedal.org | 0 | 0 | 5 | 0 | 5
fusion | 0 | 0 | 0 | 0.01 | 0.01
cernatschool.org | 0 | 0 | 0.5 | 0 | 0.5
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes