## Resource & Narrative
Year | 2020 | Area | LondonGrid
Quarter | Q2 | Reporter | DR
Narrative
Area | Successes |  |  | Problems
Brunel | Received delivery of GPU, compute nodes and 500 TB disk. |  |  | All waiting for lockdown permission, scheduled to be racked in early August.
Imperial
QMUL | April - June 2020 With limited access to Computing centre due to COVID-19 we have be cautious in Cluster operations. We have run at reduced computing power to prioritise the reliability of the site especially the storage. We have also delayed a major recableing of the network to move to the new 100Gb capable core switch. 60KW of cooling broke permanently at the start of March. Research ITS now has obtained funding for about 60KW of new cooling to replace broken units in the data centre hosting three GridPP cluster. Research ITS has also obtained funding for a project to design and cost a full renewal of the data centre hosting the GridPP cluster. Working to be able to deploy CentOS7 GridPP service nodes (xrootd/bdii/argus/storm) before November. Working to replace SL6 cluster service nodes with CemtOS7/8 alternatives (NIS/NFS/syslog/ntp/backup/ local repo mirror) before November. Lustre mitigation to latest LTS support release waiting on completion of RSYNC of data from existing Lustre system to new system (70% done). Designing and building new Network Weathermap (https://www.network-weathermap.com/) for cluster to monitor throughput/performance for internal and external links. Updated Kea DHCP from 1.3 beta release to 1.6.3 production release. Full review and, where necessary, rewriting of cluster documentation. Completed building bandwidth + latency DUNE perfSONAR meshes. Updated our provisioning system to deploy CentOS 8.2 and 7.9 hosts - now running CentOS 8.x hosts for non-grid related duties (DNS, DHCP, etc, etc).
RHUL | LHCb support added to HTC CE. Storage migration SL6 to Centos7 finished. |  |  | Problems with APEL accounting still going on. June data completely missing from accounting.egi.eu portal: https://ggus.eu/index.php?mode=ticket_info&ticket_id=147738 New machines (13kHS06, AMD Epyc 7502) delivered in April have not yet been installed due to COVID-19 restrictions.
Risks
Type | Risk |  |  | Mitigation
Brunel
Imperial
QMUL
RHUL
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 1 | 100% | 5% | 244.9% | MOK | % of WLCG Pledged CPU Available - LondonGrid |  |  | Metric OK | MOK
1b | 5 | 100% | 5% | 231.9% | MOK | % of WLCG Pledged Disk Available - LondonGrid |  |  | Metric Clost to Target | MCT
1b | 9 | 50% | 5% | 79.51% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 91% | MCT | Average Argo Availability - LondonGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 92.62% | MCT | Average Argo Reliability - LondonGrid

## Resources
Please fill in all fields highlighed in
Capacities | Brunel | Imperial | QMUL | RHUL | Total | Notes
CPU Available (HS06) | 42000 | 93396 | 41000 | 56000 | 232396 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 19770 | 22156 | 26991 | 25984 | 94901
% of Pledge | 212.4% | 421.5% | 151.9% | 215.5% | 244.9%
Storage Available (TB) | 1800 | 8346 | 5000 | 1300 | 16446
Storage Pledged (TB) | 918 | 2794 | 3379 | 685 | 7091
% of Pledge | 196.1% | 298.7% | 148% | 189.8% | 231.9%
Availability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 99.66 | 96.09 | 57.69 | 100 | 88.36% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 83.87 | 58.42 | 99.75 | 85.51% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.87 | 99.05 | 97.57 | 100 | 99.12%
% Tier-2 Averge | 99.8433 | 93.0033 | 71.2267 | 99.9167 | 91%
Reliability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 99.66 | 99.4 | 57.69 | 100 | 89.19% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 100 | 58.42 | 99.75 | 89.54% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.87 | 99.05 | 97.57 | 100 | 99.12%
% Tier-2 Total | 99.8433 | 99.4833 | 71.2267 | 99.9167 | 92.62%
CPU Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 91728000 | 203976864 | 89544000 | 122304000 | 507552864 | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normcpu/SITE/DATE/2020/4/2020/6/all/localinfrajobs/
Hours per quarter:
Month 1 | 14408115.5752 | 44191096.5656 | 32842416.6962 | 31047447.4804 | 122489076.3174 | Q1: 2160/2184 (if leap year)
Month 2 | 17611365.9383 | 41579320.0614 | 26361263.6904 | 32942772.0945 | 118494721.7846 | Q2: 2184
Month 3 | 15262410.5839 | 47144628.0498 | 27076262.7363 | 33138564.1416 | 122621865.5116 | Q3: 2208
Total: | 47281892.0974 | 132915044.6768 | 86279943.1229 | 97128783.7165 | 363605663.6136 | Q4: 2208
% Utilisation | 51.55% | 65.16% | 96.35% | 79.42% | 71.64%
WallClock Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 91728000 | 203976864 | 89544000 | 122304000 | 507552864 | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/normelap_processors/SITE/DATE/2020/4/2020/6/all/localinfrajobs/
Hours per quarter:
Month 1 | 20561902.4632 | 53725948.7195 | 31369878.0367 | 35129044.9194 | 140786774.1388 | Q1: 2160/2184 (if leap year)
Month 2 | 22230762.1417 | 51807977.44 | 21049829.7648 | 34211099.8473 | 129299669.1938 | Q2: 2184
Month 3 | 19813447.5603 | 58108984.5723 | 18762534.9393 | 36777288.4361 | 133462255.508 | Q3: 2208
Total: | 62606112.1652 | 163642910.7318 | 71182242.7408 | 106117433.2028 | 403548698.8406 | Q4: 2208
% Utilisation | 68.25% | 80.23% | 79.49% | 86.77% | 79.51%
Storage LHC & IRIS: AVAILABLE (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 32.9853 | 0 | 4100 | 1133 | 5265.9853 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 1429.3651 | 4071.473 | 1 | 2.1 | 5503.9381 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0.053687 | 710.1 | 300 | 0 | 1010.1537
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 1204 | 0 | 0 | 1204
Storage LHC & IRIS: USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 28.7327 | 0 | 3100 | 816 | 3944.7327 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 875.9661 | 3325.251 | 0.5 | 1.7 | 4203.4171 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 3.2314e-08 | 214.305 | 227 | 0 | 441.305
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 749.4 | 0 | 0 | 749.4
Storage - Other : USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
biomed | 0.357 | 0 | 0.936 | 0 | 1.293 | Active VOs at you site can be assesed from the following link:
comet.j-parc.jp | 0 | 39.355 | 0 | 0 | 39.355 | https://accounting.egi.eu/tier2/federation/UK-London-Tier2/njobs/VO/DATE/2020/4/2020/6/all/localinfrajobs/
dune | 0 | 248.833 | 0 | 0 | 248.833 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
gridpp | 0.511 | 0 | 0.069 | 0.1 | 0.68 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
ilc | 0 | 0 | 0 | 0 | 0
lsst | 0 | 77.811 | 0.169 | 0 | 77.98
lz | 0 | 716.663 | 0 | 0 | 716.663
na62.vo.gridpp.ac.uk | 0 | 0 | 0 | 0 | 0
pheno | 0.008 | 0 | 0.023 | 0.05 | 0.081
skatelescope.eu | 0 | 0.0538 | 0.16 | 0 | 0.2138
snoplus.snolab.ca | 0 | 20 | 11 | 0 | 31
solidexperiment.org | 0 | 628 | 0 | 0 | 628
t2k.org | 0 | 47.8 | 217 | 0 | 264.8
vo.complex-systems.eu | 0 | 0 | 0 | 0 | 0
vo.cta.in2p3.fr | 0 | 0 | 0 | 0 | 0
supernemo | 0.25 | 0 | 0 | 0 | 0.25
mice | 9.63 | 0 | 0 | 0 | 9.63
vo.moedal.org | 0 | 0 | 1.4 | 0 | 1.4
fusion | 0 | 0 | 0 | 0.1 | 0.1
cernatschool.org | 0 | 0 | 0.073 | 0 | 0.073
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes