## Resource & Narrative
Year | 2020 | Area | NorthGrid
Quarter | Q3 | Reporter | MD
Narrative
Area | Successes |  |  | Problems
Lancaster | ARC6 CE Installed, up and running. Majority of servers moved off of SL6 Access to machine room somewhat restored. New kit all brought online. |  |  | DPM is still recovering due to long rebuild time on disk servers disk servers, still awaiting disks. Lost disk server due to number of factors. Access to machine room requires many hoops to jump through. New disk servers can’t be easily leveraged due to fear of DPM hostspotting – easing up the amount of available disk.
Liverpool | ARC CE had to be partially reinstalled to increase scalability and clear out broken job databases. New nodes benchmarked and put online. DPM upgraded to 1.14. Many RAID arrays rebuilt and rebooted. Mu3e.org VO enabled on SE and ARC CE. We hope to have better throughput and production IPv6 on DPM by the end of the quarter. New Perfsonar system installed and configured. University WAN and firewall have been upgraded. We are working with university network team to remove bottlenecks and filtering issues. |  |  | No progress on grid FTE issue. Effort is probably the same (as soon as we finish one thing another comes along to replace it!) Lots of storage still running on out of warranty and problematic servers.
Manchester
Sheffield
Risks
Type | Risk |  |  | Mitigation
Lancaster | DPM continues to be a pressure point Machine room access is hard to arrange in a timely manner ARC Publishing problems. |  |  | Start planning on Xcache “shims” to alleviate pressure. Heavily plan all physical work. Fix and republish.
Liverpool | Staffing issues continue. Storage running on problematic servers.
Manchester | ARC Publishing is way off, greatly underreporting CPU time. |  |  | Fixed in V3 of this report.
Sheffield | Low amount of available effort |  |  | Support from other sites.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-09-01 | Liverpool and Lancaster Online new kit |  |  | Increased delivery metrics (particularly Liverpool).
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-12-20 | Lancs: fix arc publishing Lancs: Preliminary investigation of xcache “dpm shim” All – complete any SL6 migration |  |  | Sensical job reporting Plan to increase DPM stability Keep ahead of SL6 EOL

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 2 | 100% | 5% | 221.7% | MOK | % of WLCG Pledged CPU Available - NorthGrid |  |  | Metric OK | MOK
1b | 6 | 100% | 5% | 185.8% | MOK | % of WLCG Pledged Disk Available - NorthGrid |  |  | Metric Clost to Target | MCT
1b | 10 | 50% | 5% | 111% | MOK | % CPU Utilisation (Wall Clock) - NorthGrid |  |  | Metric not OK | MFL
1b | 16 | 95% | 5% | 69.83% | MFL | Average Argo Availability - NorthGrid |  |  | Metric with no Target | MNO
1b | 17 | 95% | 5% | 74.17% | MFL | Average Argo Reliability - NorthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
CPU Available (HS06) | 79845 | 34873 | 55829 | 11918 | 170547 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 23955 | 14171 | 29463 | 9326 | 76915
% of Pledge | 333.3% | 246.1% | 189.5% | 127.8% | 221.7% | Capacity figures are as reported by the site directly.
Storage Available (TB) | 3400 | 1577 | 6820 | 0 | 11797 | Liverpool accidentially underreported their CPU figures last quarter.
Storage Pledged (TB) | 1645 | 724 | 3979 | 29 | 6348
% of Pledge | 206.7% | 217.8% | 171.4% | 0% | 185.8%
Availability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 96 | 58 | 97 | 13 | 66% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 99 | 87 | 100 | 2 | 72% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 91 | 95 | 100 | 0 | 71.5%
% Tier-2 Averge | 95.3333 | 80 | 99 | 5 | 69.83%
Reliability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 96 | 97 | 97 | 13 | 75.75% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 99 | 100 | 100 | 2 | 75.25% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 91 | 95 | 100 | 0 | 71.5%
% Tier-2 Total | 95.3333 | 97.3333 | 99 | 5 | 74.17%
CPU Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 176297760 | 76999584 | 123270432 | 26314944 | 402882720 | https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 33794023 | 17869501 | 54375457 | 0 | 106038981 | Q1: 2160/2184 (if leap year)
Month 2 | 70392442 | 14634171 | 42508588 | 0 | 127535201 | Q2: 2184
Month 3 | 59429185 | 11923516 | 41762890 | 0 | 113115591 | Q3: 2208
Total: | 163615650 | 44427188 | 138646935 | 0 | 346689773 | Q4: 2208
% Utilisation | 92.81% | 57.7% | 112.5% | 0% | 86.05% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
WallClock Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 176297760 | 76999584 | 123270432 | 26314944 | 402882720 | https://accounting.egi.eu/tier2/federation/NorthGrid/normelap_processors/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 48501395 | 18451980 | 65305457 | 0 | 132258832 | Q1: 2160/2184 (if leap year)
Month 2 | 82745604 | 15399243 | 64824233 | 0 | 162969080 | Q2: 2184
Month 3 | 74149999 | 13309455 | 64569980 | 0 | 152029434 | Q3: 2208
Total: | 205396998 | 47160678 | 194699670 | 0 | 447257346 | Q4: 2208
% Utilisation | 116.5% | 61.25% | 157.9% | 0% | 111%
Storage LHC & IRIS: AVAILABLE (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 3400 | 1000 | 0 | 0 | 4400 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 313 | 0 | 0 | 313
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 1060 | 0 | 0 | 0 | 1060
Storage LHC & IRIS: USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 2700 | 761 | 0 | 0 | 3461 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 221 | 0 | 0 | 221
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 286 | 0 | 0 | 0 | 286
Storage - Other : USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
t2k.org | 18 | 0.882 | 0 |  | 18.882 | Active VOs at you site can be assesed from the following link:
snoplus.snolab.ca | 0.5 | 0.286 | 0 |  | 0.786 | https://accounting.egi.eu/tier2/federation/NorthGrid/njobs/VO/DATE/2020/7/2020/9/all/localinfrajobs/
na62.vo.gridpp.ac.uk | 0 | 2.47 | 0 |  | 2.47 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
cernatschool.org | 0 | 0.03 | 0 |  | 0.03 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dteam | 0.01 | 0.04 | 0 |  | 0.05
esr | 0 | 0.07 | 0 |  | 0.07
gridpp | 0.001 | 0 | 0 |  | 0.001
lsst | 0 | 0.978 | 0 |  | 0.978
dune | 0 | 0.59 | 0 |  | 0.59
mu3e.org | 0 | 9.96 | 0 |  | 9.96
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
lsst (iris) | 91 | 0 | 0 |  | 91
dune (iris) | 122 | 0 | 0 |  | 122
vo.cta.in2p3.fr (iris) | 74 | 0 | 0 |  | 74
ska.telescope.eu (iris) | 0.03 | 0 | 0 |  | 0.03
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes