## Resource & Narrative
Year | 2020 | Area | NorthGrid
Quarter | Q2 | Reporter | MD
Narrative
Area | Successes |  |  | Problems
Lancaster | Commissioned New Kit, planned new services. |  |  | COVID, aging disk servers, pending SL6 deadlines. Some aging hardware. COVID restrictions meant putting online some kit harder then it should be, some delayed until next quarter.
Liverpool | Work on supporting new Vos |  |  | COVID, being an admin down, aging disk servers
Manchester
Sheffield | Working towards getting a working site again. |  |  | COVID, tiny fraction of unfunded effort available for grid work at the same time the site was needing to be practically rebuilt. This has led to low figures.
Risks
Type | Risk |  |  | Mitigation
Lancaster | Aging Disk Servers are our biggest risk, particularly with machine room access being scarce. Some services still on SL6 DPM inflexibilities compound disk problems, putting stress on newer disks. |  |  | Decommissioning most at risk servers and cannabalising for parts.
Liverpool | Being an Admin down local admins are trying hard to keep things going. A/R figures for next quarter “at risk” due to HTCCE not being properly monitored and accounted for yet. |  |  | Help from the community. Awareness so we can request recalculations.
Manchester
Sheffield | Tiny fraction of effort available at the site. |  |  | Minimise service, reach out for support from the community.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-05-31 | Lancaster – deploy as much of new kits as possible Adjust to working from home regime |  |  | Increased capacity. As close to business as usual as possible.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-09-01 | Lancaster – deploy last of new kit (perfsonar) Lancaster – remove last few SL6 nodes |  |  | All new kit deployed Decommissioned ahead of SL6 EOL date

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 2 | 100% | 5% | 200% | MOK | % of WLCG Pledged CPU Available - NorthGrid |  |  | Metric OK | MOK
1b | 6 | 100% | 5% | 184.6% | MOK | % of WLCG Pledged Disk Available - NorthGrid |  |  | Metric Clost to Target | MCT
1b | 10 | 50% | 5% | 94.95% | MOK | % CPU Utilisation (Wall Clock) - NorthGrid |  |  | Metric not OK | MFL
1b | 16 | 95% | 5% | 72.42% | MFL | Average Argo Availability - NorthGrid |  |  | Metric with no Target | MNO
1b | 17 | 95% | 5% | 72.42% | MFL | Average Argo Reliability - NorthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
CPU Available (HS06) | 79845 | 18161 | 55829 | 11918 | 153835 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 23955 | 14171 | 29463 | 9326 | 76915
% of Pledge | 333.3% | 128.2% | 189.5% | 127.8% | 200% | Capacity figures are as reported by the site directly.
Storage Available (TB) | 3400 | 1497 | 6820 | 0 | 11717
Storage Pledged (TB) | 1645 | 724 | 3979 | 29 | 6348
% of Pledge | 206.7% | 206.8% | 171.4% | 0% | 184.6%
Availability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 100 | 82 | 100 | 1 | 70.75% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 99 | 100 | 0 | 74.75% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 92 | 95 | 100 | 0 | 71.75%
% Tier-2 Averge | 97.3333 | 92 | 100 | 0.33333 | 72.42%
Reliability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 100 | 82 | 100 | 1 | 70.75% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 100 | 99 | 100 | 0 | 74.75% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 92 | 95 | 100 | 0 | 71.75%
% Tier-2 Total | 97.3333 | 92 | 100 | 0.33333 | 72.42%
CPU Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 174381480 | 39663624 | 121930536 | 26028912 | 362004552 | https://accounting.egi.eu/tier2/federation/UK-NorthGrid/normcpu/SITE/DATE/2020/4/2020/6/all/localinfrajobs/
Hours per quarter:
Month 1 | 29119117 | 14570098 | 50837731 |  | 94526946 | Q1: 2160/2184 (if leap year)
Month 2 | 31832955 | 16519795 | 54659962 | 0 | 103012712 | Q2: 2184
Month 3 | 29769893 | 16249532 | 45239531 | 0 | 91258956 | Q3: 2208
Total: | 90721965 | 47339425 | 150737224 | 0 | 288798614 | Q4: 2208
% Utilisation | 52.03% | 119.4% | 123.6% | 0% | 79.78% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
WallClock Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 174381480 | 39663624 | 121930536 | 26028912 | 362004552 | https://accounting.egi.eu/tier2/federation/UK-NorthGrid/normelap_processors/SITE/DATE/2020/4/2020/6/all/localinfrajobs/
Hours per quarter:
Month 1 | 37321359 | 17523784 | 61721722 | 0 | 116566865 | Q1: 2160/2184 (if leap year)
Month 2 | 38287494 | 17282783 | 61829365 | 0 | 117399642 | Q2: 2184
Month 3 | 37336317 | 17216281 | 55213809 | 0 | 109766407 | Q3: 2208
Total: | 112945170 | 52022848 | 178764896 | 0 | 343732914 | Q4: 2208
% Utilisation | 64.77% | 131.2% | 146.6% | 0% | 94.95% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normelap_processors/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
Storage LHC & IRIS: AVAILABLE (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 3400 | 0 | 0 | 0 | 3400 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 0 | 0
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 1060 | 0 | 0 | 0 | 1060
Storage LHC & IRIS: USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 2900 | 761 | 1108 | 0 | 4769 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 221 | 108 | 0 | 329
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 286 | 0 | 0 | 0 | 286
Storage - Other : USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
t2k.org | 18 | 27 | 72 |  | 117 | Active VOs at you site can be assesed from the following link:
snoplus.snolab.ca | 0.5 | 0.285 | 0 |  | 0.785 | https://accounting.egi.eu/tier2/federation/UK-NorthGrid/njobs/VO/DATE/2020/4/2020/6/all/localinfrajobs/
na62.vo.gridpp.ac.uk | 0 | 2.5 | 0 |  | 2.5 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
cernatschool.org | 0 | 0.03 | 0 |  | 0.03 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dteam | 0.01 | 0.04 | 0 |  | 0.05
esr | 0 | 0.07 | 0 |  | 0.07
gridpp | 0.001 | 0.07 | 0 |  | 0.071
lsst | 0 | 1 | 0 |  | 1
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
lsst (iris) | 90 | 0 | 0 |  | 90
dune (iris) | 122 | 0 | 0 |  | 122
vo.cta.in2p3.fr (iris) | 74 | 0 | 0 |  | 74
ska.telescope.eu (iris) | 0.03 | 0 | 0 |  | 0.03
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes