## Resource & Narrative
Year | 2020 | Area | ScotGrid
Quarter | Q3 | Reporter | GR
Narrative
Area | Successes |  |  | Problems
Durham | Didn't catch COVID. Written an API for the Shared Fail2Ban. |  |  | Disk Server failures - Failed HDDS in RAID array. DPM/Xroot corrupt libs.
Edinburgh | Migrated all storage to CentOS7 and rebuilt using experience/expertise to remove storage performance issues. Had positive feedback from both DOMA-QoS and ATLAS to ECDF becoming a demonstrator site for opportunistic storage to show if it can work or not in principle. |  |  | Having to pick-up/maintain services with loss of manpower/expertise. Storage problems highlighted due to problems with WLCG approved software which has led to several bug reports being made upstream to developers.
Glasgow | More Equipment moved to new DC. CLAS12 successfully moved to run jobs on the new DC batch farm. Comissioning of new 40Gb enabled CEPH cache node. Comissioning of new PerfSonar |  |  | More failed disks in aging DPM pool node led to lost files.
Risks
Type | Risk |  |  | Mitigation
Durham | COVID restrictions in the North East England means 2 man working is advised against, University Policies restrict this too.Some issues may not be resolved if it requires a 2 man team. General access is also restricted and so issues may take longer to resolve.
Edinburgh | Additional loss of expertise due to staff leaving (again). A/R risks due to not controlling all services relating to Tier2. Aging storage at the site. |  |  | More documentation needed across the site to avoid missing knowledge gaps building up. Have comissioned additional services to supplement this to avoid A/R falling too low. Working with ATLAS/DOMA-QoS to determine best use of storage.
Glasgow | COVID and other delays mean migration to new DC is delayed. |  |  | Focus on running both batch farms and storage pools for as long as possible.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-10-01 | Durham: Frontier Cache |  |  | Stable Frontier Squid
2020-10-01 | Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  |  | Stability required, Auto build Required.
2020-10-01 | Durham: Shared Fail2Ban Production Ready |  |  | Final Documentation
2020-10-01 | Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  |  | C8 SE Maybe?
2020-10-01 | Glasgow: Production Deployment of CEPH Storage |  |  | Active usage by Atlas for both Storage and CPU writeback
2020-10-01 | Glasgow: Migration of select HW to new Data Centre |  |  | Additional CPU capacity deployed to new DC
2020-10-01 | ECDF: Explore turning off legacy components of DPM |  |  | Still haven't been able to fully evaluate this but have discovered and fixed multiple issues to do with storage over last quarter.
2020-10-01 | ECDF: commission additional ARGUS servers |  |  | Not yet started due to length of time taken to re-build and fix storage problems with DPM being broken
2020-10-01 | ECDF: Deploy new NFS server |  |  | This has started but has been delayed as deploying the new NFS is expected to be done in parallel with re-building the site ARGUS so that the downtimes are kept to a minimum.
2020-10-01 | ECDF: Work with ATLAS/DOMA-QoS to best use site storage |  |  | Edinburgh has formally agreed to be an "Opportunistic Storage Demonstrator". Still early days
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Jan/Feb-21 | Durham: Frontier Cache |  |  | Stable Frontier Squid
Jan/Feb-21 | Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  |  | Stability required, Auto build Required.
Jan/Feb-21 | Durham: Shared Fail2Ban Production Ready |  |  | Github is up to date, documentation is very technically light and expects people to know fail2ban already. Looking to deploy at another site.
Jan/Feb-21 | Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  |  | C8 SE Maybe?
Jan/Feb-21 | ECDF: Better ARGUS setup |  |  | Commission 2 parallel ARGUS to better exploit local resources. This effectively removes one of the last bottlenecks in the T2 stack at the site for doing more work.
Jan/Feb-21 | ECDF: New NFS server |  |  | This should be relatively easy, but will be done in parallel with new ARGUS setup
Jan/Feb-21 | ECDF: Re-Setup XCache-s |  |  | Kick the tiers of the XCache@ECDF again and try to put back into production
Jan/Feb-21 | ECDF: XCache monitoring |  |  | Give the XCache monitoring a swift sharp kick and aim to get proof of concept summary plots working again with 2/3 sites soon
Jan/Feb-21 | Glasgow: HV migrated to new DC |  |  | All VMs on the production Hypervisors running in new DC
Jan/Feb-21 | Glasgow: Production frontier squid migrated to new DC |  |  | Frontier squid moved to new DC and special routing rules removed from workernodes

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 3 | 100% | 5% | 205.2% | MOK | % of WLCG Pledged CPU Available - ScotGrid |  |  | Metric OK | MOK
1b | 7 | 100% | 5% | 121.3% | MOK | % of WLCG Pledged Disk Available - ScotGrid |  |  | Metric Clost to Target | MCT
1b | 11 | 50% | 5% | 112.3% | MOK | % CPU Utilisation (Wall Clock) - ScotGrid |  |  | Metric not OK | MFL
1b | 17 | 95% | 5% | 96% | MOK | Average Argo Availability - ScotGrid |  |  | Metric with no Target | MNO
1b | 18 | 95% | 5% | 96% | MOK | Average Argo Reliability - ScotGrid

## Resources
Please fill in all fields highlighed in
Capacities | Durham | Edinburgh | Glasgow | Total | Notes
CPU Available (HS06) | 45560 | 10000 | 44333 | 99893 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 18310 | 5396 | 24977 | 48683
% of Pledge | 248.8% | 185.3% | 177.5% | 205.2%
Storage Available (TB) | 346 | 1044 | 3882 | 5272
Storage Pledged (TB) | 33 | 474 | 3838 | 4345
% of Pledge | 1048% | 220.3% | 101.1% | 121.3%
Availability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 76.85 | 98.91 | 99.87 | 91.88% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 99.15 | 90.18 | 100 | 96.44% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.69 | 99.69 | 99.69 | 99.69%
% Tier-2 Averge | 91.8967 | 96.26 | 99.8533 | 96%
Reliability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 76.85 | 98.91 | 99.87 | 91.88% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 99.15 | 90.18 | 100 | 96.44% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.69 | 99.69 | 99.69 | 99.69%
% Tier-2 Total | 91.8967 | 96.26 | 99.8533 | 96%
CPU Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 100596480 | 22080000 | 97887264 | 220563744 | https://accounting.egi.eu/tier2/federation/ScotGrid/normcpu/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 36438504 | 15317429 | 16784300 | 68540233 | Q1: 2160/2184 (if leap year)
Month 2 | 41242679 | 19188728 | 20900668 | 81332075 | Q2: 2184
Month 3 | 38882021 | 29659684 | 19787522 | 88329227 | Q3: 2208
Total: | 116563204 | 64165841 | 57472490 | 238201535 | Q4: 2208
% Utilisation | 115.9% | 290.6% | 58.71% | 108% | ECDF cloud: https://accounting.egi.eu/cloud/site/UKI-SCOTGRID-ECDF/sum_elap_processors/VO/DATE/2020/7/2020/9/all/localinfrajobs/ * 21.0 HEPSPEC (average from historical data and using non-HT CPU)
WallClock Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 100596480 | 22080000 | 97887264 | 220563744 | https://accounting.egi.eu/tier2/federation/ScotGrid/normelap_processors/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 35520571 | 17181389.196 | 19043862 | 71745822.196 | Q1: 2160/2184 (if leap year)
Month 2 | 41573776 | 20634989.58 | 22576061 | 84784826.58 | Q2: 2184
Month 3 | 37772997 | 31122536.61 | 22251862 | 91147395.61 | Q3: 2208
Total: | 114867344 | 68938915.386 | 63871785 | 247678044.386 | Q4: 2208
% Utilisation | 114.2% | 312.2% | 65.25% | 112.3% | ECDF cloud wallclock = (1.046 * CPU hours based on historical performance)
Storage LHC & IRIS: AVAILABLE (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 265 | 1000 | 4200 | 5465 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 300 | 300
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 235 | 679.08 | 1580 | 2494.08 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 1 | 1 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 72 | 72
Alice | 0 | 0 | 0 | 0 | ECDF site ATLAS use at low point as storage servers are being re-balanced to migrate to CentOS7 will increase to ~900T in next quarter
IRIS | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
biomed | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
cernatschool.org | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/ScotGrid/njobs/VO/DATE/2020/7/2020/9/all/localinfrajobs/
clas12 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
comet.j-parc.jp | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dune | 0 | 0 | 0 | 0
gridpp | 0 | 1 | 2 | 3
hyperk.org | 0 | 0 | 0 | 0
ilc | 0 | 0 | 0 | 0
iris.ac.uk | 0 | 0 | 0 | 0
lhcb | 0 | 0 | 0 | 0
lsst | 0 | 0 | 0 | 0
lz | 0 | 0 | 0 | 0
magrid | 0 | 0 | 0 | 0
mice | 0 | 0 | 1.9 | 1.9
na62.vo.gridpp.ac.uk | 0 | 0 | 3.8 | 3.8
ops | 0 | 0 | 0 | 0
pheno | 66 | 0 | 7.5 | 73.5
skatelescope.eu | 0 | 0 | 0 | 0
snoplus.snolab.ca | 0 | 0 | 0 | 0
solidexperiment.org | 0 | 0 | 0 | 0
t2k.org | 0 | 0 | 0 | 0
vo.moedal.org | 0 | 0 | 0 | 0
vo.northgrid.ac.uk | 0 | 0 | 0 | 0
vo.scotgrid.ac.uk | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Ongoing | LSST | Rob assisting James with LSST job submission via DIRAC
Ongoing | LZ | ECDF aiding in moving some workloads to the Grid.
Ongoing | DUNE | Provided effort into DUNE RUCIO deployment and data management
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Present | UK Members of DPM Collaboration | UK Data Storage (S. Skipsey)
Present | HTTP Deployment Working Group | S. Skipsey
Present | Member of Tier-2 Evolution Working Group | S.Skipsey
Present | WLCG Sytem Performance and Cost Modelling WG | Gareth Roy
Present | Member of WLCG DOMA-Access WG | Teng Li
Present | Member of LHCb RTA | Robert Currie
Present | Member of the WLCG DOMA-QoS WG | Robert Currie
Date | Other Outputs and Knowledge Exchange | Notes