## Resource & Narrative
Year | 2020 | Area | ScotGrid
Quarter | Q4 | Reporter | GR
Narrative
Area | Successes |  |  | Problems
Durham | Things stayed on over christmas. |  |  | Weirdness with RAID Card on Disk02 caused us to mark it as read only / drain. Various nodes are offline. COVID.
Edinburgh | CE is stable and requires little effort. Fixed(mitigated) several DPM issues (bugs) which occured just from leaving it alone. |  |  | Exposed to problems due to provisioning our HV on CentOS8... Thanks IBM. Plan to use scotgrid DNS records (GLASGOW) to register secondary site BDII for better A/R numbers in-case of ACF downtime. DPM is bad.
Glasgow | All WN within DC now fully operation. Production CEPH now being heavily used. DPM decomissioning ongoing |  |  | Due to COVID restrictions migration to the DC is stalled.
Risks
Type | Risk |  |  | Mitigation
Durham | COVID restrictions in the North East England means 2 man working is advised against, University Policies restrict this too.Some issues may not be resolved if it requires a 2 man team. General access is also restricted and so issues may take longer to resolve.
Edinburgh | Additional loss of expertise due to staff leaving (again). A/R risks due to not controlling all services relating to Tier2. Aging storage at the site. |  |  | More documentation needed across the site to avoid missing knowledge gaps building up. Have comissioned additional services to supplement this to avoid A/R falling too low. Working with ATLAS/DOMA-QoS to determine best use of storage.
Glasgow | COVID and other delays mean migration to new DC is delayed. |  |  | Focus on running both batch farms and storage pools for as long as possible.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Jan/Feb-21 | Durham: Frontier Cache |  |  | No progress yet.
Jan/Feb-21 | Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  |  | No progress yet.
Jan/Feb-21 | Durham: Shared Fail2Ban Production Ready |  |  | No progress yet.
Jan/Feb-21 | Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  |  | No progress yet.
Jan/Feb-21 | ECDF: Better ARGUS setup |  |  | Completed, effectively lifting ceiling of jobs queued+running at the site to 4k per VO from 2k. Also increased number of accounts available to DUNE VO
Jan/Feb-21 | ECDF: New NFS server |  |  | No progress, re-evaluating HV status due to them being provisioned on CentOS8.
Jan/Feb-21 | ECDF: Re-Setup XCache-s |  |  | Have proven XCache can work reliably and reduce some load on the backend site storage.
Jan/Feb-21 | ECDF: XCache monitoring |  |  | Built new prototype XCache monitoring framework based on lessons from first attempt.
Jan/Feb-21 | Glasgow: HV migrated to new DC |  |  | Move completed Succesfully
Jan/Feb-21 | Glasgow: Production frontier squid migrated to new DC |  |  | Move completed Succesfully
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-04-01 | Durham: Frontier Cache
2021-04-01 | Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools.
2021-04-01 | Durham: Shared Fail2Ban Production Ready
2021-04-01 | Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build
2021-04-01 | ECDF: Finalise new XCache framework |  |  | New XCache framework based on messaging queues which can be presented at vCHEP
2021-04-01 | ECDF: Provision new NFS server for Tier2 |  |  | New NFS server for Tier2. Likely will provision new SLOG+ZIL device before deployment.
2021-04-01 | ECDF: Ressurect more old equipment for Tier3 use in JCMB |  |  | Expand the existing Tier3 at Edinburgh by 33% by bringing old working equipment into production.
2021-04-01 | ECDF: Bring out of warranty storage into production for DOMA |  |  | 2nd SE at the site for DOMA testing of unreliable out of warranty storage
2021-04-01 | Glasgow: Cable and bring online migrated WN with in DC |  |  | Additional Capacity available to experiments
2021-04-01 | Glasgow: Add 400TB of storage to CEPH |  |  | Additional Capacity available to experiments

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 3 | 100% | 5% | 205.2% | MOK | % of WLCG Pledged CPU Available - ScotGrid |  |  | Metric OK | MOK
1b | 7 | 100% | 5% | 121.3% | MOK | % of WLCG Pledged Disk Available - ScotGrid |  |  | Metric Clost to Target | MCT
1b | 11 | 50% | 5% | 126.6% | MOK | % CPU Utilisation (Wall Clock) - ScotGrid |  |  | Metric not OK | MFL
1b | 17 | 95% | 5% | 95.24% | MOK | Average Argo Availability - ScotGrid |  |  | Metric with no Target | MNO
1b | 18 | 95% | 5% | 97.02% | MOK | Average Argo Reliability - ScotGrid

## Resources
Please fill in all fields highlighed in
Capacities | Durham | Edinburgh | Glasgow | Total | Notes
CPU Available (HS06) | 45560 | 10000 | 44333 | 99893 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 18310 | 5396 | 24977 | 48683
% of Pledge | 248.8% | 185.3% | 177.5% | 205.2%
Storage Available (TB) | 346 | 1044 | 3882 | 5272
Storage Pledged (TB) | 33 | 474 | 3838 | 4345
% of Pledge | 1048% | 220.3% | 101.1% | 121.3%
Availability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 97.56 | 99.82 | 100 | 99.13% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 98.96 | 94.66 | 88.84 | 94.15% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.71 | 92.45 | 85.18 | 92.45%
% Tier-2 Averge | 98.7433 | 95.6433 | 91.34 | 95.24%
Reliability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 97.56 | 99.82 | 100 | 99.13% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 98.96 | 99.37 | 89.85 | 96.06% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.99 | 92.45 | 95.18 | 95.87%
% Tier-2 Total | 98.8367 | 97.2133 | 95.01 | 97.02%
CPU Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 100596480 | 22080000 | 97887264 | 220563744 | https://accounting.egi.eu/tier2/federation/ScotGrid/normcpu/SITE/DATE/2020/10/2020/12/all/localinfrajobs/
Hours per quarter:
Month 1 | 38528289 | 25604860 | 18756115 | 82889264 | Q1: 2160/2184 (if leap year)
Month 2 | 41155509 | 18251518 | 23949298 | 83356325 | Q2: 2184
Month 3 | 44584550 | 18196430 | 42730190 | 105511170 | Q3: 2208
Total: | 124268348 | 62052808 | 85435603 | 271756759 | Q4: 2208
% Utilisation | 123.5% | 281% | 87.28% | 123.2% | ECDF cloud: https://accounting-next.egi.eu/tier2/cloud/federation/ScotGrid/sum_elap/SITE/DATE/2020/10/2020/12/lhc/onlyinfrajobs/ * 21.0 HEPSPEC (average from historical data and using non-HT CPU)
WallClock Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 100596480 | 22080000 | 97887264 | 220563744 | https://accounting.egi.eu/tier2/federation/ScotGrid/normelap_processors/SITE/DATE/2020/10/2020/12/all/localinfrajobs/
Hours per quarter:
Month 1 | 37759787 | 26961146.574 | 21443533 | 86164466.574 | Q1: 2160/2184 (if leap year)
Month 2 | 39992899 | 19717553.56 | 24918020 | 84628472.56 | Q2: 2184
Month 3 | 43277323 | 19964092.122 | 45099649 | 108341064.122 | Q3: 2208
Total: | 121030009 | 66642792.256 | 91461202 | 279134003.256 | Q4: 2208
% Utilisation | 120.3% | 301.8% | 93.44% | 126.6% | ECDF cloud wallclock = (1.046 * CPU hours based on historical performance)
Storage LHC & IRIS: AVAILABLE (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 265 | 700 | 4200 | 5165 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 300 | 300
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 235 | 679.08 | 1760 | 2674.08 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 1 | 1 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 72 | 72
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
biomed | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
cernatschool.org | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/ScotGrid/njobs/VO/DATE/2020/10/2020/12/all/localinfrajobs/
clas12 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
comet.j-parc.jp | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dune | 0 | 0 | 0 | 0
gridpp | 0 | 1 | 2 | 3
hyperk.org | 0 | 0 | 0 | 0
ilc | 0 | 0 | 0 | 0
iris.ac.uk | 0 | 0 | 0 | 0
lhcb | 0 | 0 | 0 | 0
lsst | 0 | 0 | 0 | 0
lz | 0 | 0 | 0 | 0
magrid | 0 | 0 | 0 | 0
mice | 0 | 0 | 1.9 | 1.9
na62.vo.gridpp.ac.uk | 0 | 0 | 3.8 | 3.8
ops | 0 | 0 | 0 | 0
pheno | 66 | 0 | 7.5 | 73.5
skatelescope.eu | 0 | 0 | 0 | 0
snoplus.snolab.ca | 0 | 0 | 0 | 0
solidexperiment.org | 0 | 0 | 0 | 0
t2k.org | 0 | 0 | 0 | 0
vo.moedal.org | 0 | 0 | 0 | 0
vo.northgrid.ac.uk | 0 | 0 | 0 | 0
vo.scotgrid.ac.uk | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Ongoing | LSST | Rob assisting James with LSST job submission via DIRAC
Ongoing | LZ | ECDF aiding in moving some workloads to the Grid.
Ongoing | DUNE | Provided effort into DUNE RUCIO deployment and data management
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Present | UK Members of DPM Collaboration | UK Data Storage (S. Skipsey)
Present | HTTP Deployment Working Group | S. Skipsey
Present | Member of Tier-2 Evolution Working Group | S.Skipsey
Present | WLCG Sytem Performance and Cost Modelling WG | Gareth Roy
Present | Member of LHCb RTA | Robert Currie
Present | Member of the WLCG DOMA-QoS WG | Robert Currie
Date | Other Outputs and Knowledge Exchange | Notes