## Resource & Narrative
Year | 2020 | Area | ScotGrid
Quarter | Q2 | Reporter | GR
Narrative
Area | Successes |  |  | Problems
Durham | Migrated all CE's to ARC6. Upgraded to DOME. Installed some new equipment. Installed Proxmox to new hardware in a 4node cluster and CEPH; now with HIGH availability. |  |  | Disk Array continues to crash/KP. dur to SATA SMR Drives being rubbish. DOME/XROOT/DMLITE issues; poor documentation and poor packaging. Failed heat exchanger cause the datacentre to go offline due to high temps.
Edinburgh | Anonymous access to XCache and Rucio monitoring enabled. Migrated to ARC6 on all CE. Correctly Re-Evaluated site HEPSPEC. Comissioned new Tier3 Added new experimental logging infrastructure. Upgraded BDII to CentOS7. Upgraded DPM head node and most of storage to CentOS7. |  |  | DPM 1.13 continues to have (none site-specific) problems. These are being worked through but are a significant time-sink. Suffered on site A/R numbers due to services we don't directly control being down for numerous reasons (security/power/scalabiltity).
Glasgow | CEPH comissioning contines, with active ATLAS jobs running against new CEPH pool. Additional monitoring infrastructure set with initial deployment of ElastiFlow for network monitoring. |  |  | Due to delays in migration to new DC, some resources (CPU & Disk) are unavailable for consumption by WLCG experiments. Problems with xrootd and writing back to CEPH has stalled comissioning of production CEPH cluster.
Risks
Type | Risk |  |  | Mitigation
Durham
Edinburgh | Potential loss of expertise due to staff leaving. A/R risks due to not controlling all services relating to Tier2. Aging storage at the site. |  |  | More documentation needed across the site to avoid missing knowledge gaps building up. Have comissioned additional services to supplement this to avoid A/R falling too low. Working with ATLAS/DOMA-QoS to determine best use of storage.
Glasgow | COVID and other delays mean migration to new DC is delayed. |  |  | Focus on running both batch farms and storage pools for as long as possible.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-07-01 | Glasgow: Decomission CentOS6 queue and reclaim resource |  |  | Queue Decomissioned, resources waiting to be removed post COVID restrictions
2020-07-01 | Glasgow: Production Deployment of CEPH Storage |  |  | Issues with xroot have meant this is still ongoing, as a fall back GridFTP is now being set up.
2020-07-01 | ECDF: Deploy new NFS server |  |  | WIP delayed due to ARC6/CentOS7 migration
2020-07-01 | ECDF: Enable anonymous access to monitoring at site |  |  | Anoymous readonly access is done.
2020-07-01 | ECDF: ARC6 |  |  | Deployed and working across site, bug in HTCondor+ARC6 reported
2020-07-01 | ECDF: Migrate services to CentOS7 |  |  | BDII done, SE 50% done, ARGUS pending, T3 working
2020-07-01 | ECDF: Set up centralised logging |  |  | Ongoing. Loki and Promtail depolyed, but dashboards need to be set up
2020-07-01 | Durham: Frontier Cache |  |  | Ongoing - Works but unstable to to storage issues.
2020-07-01 | Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  |  | Ongoing - ELK/Elastiflow works, LibreNMS, works, Smokeping, Oxidized Works, Grafana, Graphite and Promethus works - Issues with Ganglia and storage.
2020-07-01 | Durham: Shared Fail2Ban Production Ready |  |  | Ongoing - Need to finalise documentation.
2020-07-01 | Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  |  | Ongoing - Currently on a CentOS7 VM working OK; might hold off C8 migration for now.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-10-01 | Durham: Frontier Cache |  |  | Stable Frontier Squid
2020-10-01 | Durham: In a vain attempt to split some monitoring systems away from traditional installs enabling us to update some of the monitoring tools. |  |  | Stability required, Auto build Required.
2020-10-01 | Durham: Shared Fail2Ban Production Ready |  |  | Final Documentation
2020-10-01 | Durham: Investigate DPM/Dome Head Node issues; finalising on a C8 Build |  |  | C8 SE Maybe?
2020-10-01 | Glasgow: Production Deployment of CEPH Storage |  |  | Active usage by Atlas for both Storage and CPU writeback
2020-10-01 | Glasgow: Migration of select HW to new Data Centre |  |  | Additional CPU capacity deployed to new DC
2020-10-01 | ECDF: Explore turning off legacy components of DPM |  |  | We're one of the few sites still running legacy DPM components (for various reasons). We should try to join everyone else who has turned these off as they're unsupported
2020-10-01 | ECDF: commission additional ARGUS servers |  |  | We have a site limit of 2k jobs per-DN. If we commission multiple ARGUS we can potentially work around this. At least we need to migrate to ARGUS on CentOS7.
2020-10-01 | ECDF: Deploy new NFS server |  |  | Comission new better performing NFS server for cluster use.
2020-10-01 | ECDF: Work with ATLAS/DOMA-QoS to best use site storage |  |  | Work with ATLAS to understand how to best make use of site storage through GridPP6

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 3 | 100% | 5% | 205.2% | MOK | % of WLCG Pledged CPU Available - ScotGrid |  |  | Metric OK | MOK
1b | 7 | 100% | 5% | 121.3% | MOK | % of WLCG Pledged Disk Available - ScotGrid |  |  | Metric Clost to Target | MCT
1b | 11 | 50% | 5% | 92.54% | MOK | % CPU Utilisation (Wall Clock) - ScotGrid |  |  | Metric not OK | MFL
1b | 17 | 95% | 5% | 92.01% | MCT | Average Argo Availability - ScotGrid | Due to airconditioning and storage problems at Durham in June Tier-2 average is down. Power problems and GPFS problems in Edinburgh also brought down the average. |  | Metric with no Target | MNO
1b | 18 | 95% | 5% | 92.01% | MCT | Average Argo Reliability - ScotGrid | Due to airconditioning and storage problems at Durham in June Tier-2 average is down. Power problems and GPFS problems in Edinburgh also brought down the average.

## Resources
Please fill in all fields highlighed in
Capacities | Durham | Edinburgh | Glasgow | Total | Notes
CPU Available (HS06) | 45560 | 10000 | 44333 | 99893 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 18310 | 5396 | 24977 | 48683
% of Pledge | 248.8% | 185.3% | 177.5% | 205.2%
Storage Available (TB) | 346 | 1044 | 3882 | 5272
Storage Pledged (TB) | 33 | 474 | 3838 | 4345
% of Pledge | 1048% | 220.3% | 101.1% | 121.3%
Availability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 99.8 | 96.4 | 100 | 98.73% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 85.55 | 85.6 | 92.6 | 87.92% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 78.1 | 90 | 100 | 89.37%
% Tier-2 Averge | 87.8167 | 90.6667 | 97.5333 | 92.01%
Reliability | Durham | Edinburgh | Glasgow | Avg | Notes
Month 1 | 99.8 | 96.4 | 100 | 98.73% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 85.55 | 85.55 | 92.6 | 87.9% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 78.14 | 90.01 | 100 | 89.38%
% Tier-2 Total | 87.83 | 90.6533 | 97.5333 | 92.01%
CPU Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 99503040 | 21840000 | 96823272 | 218166312 | https://accounting.egi.eu/tier2/federation/UK-ScotGrid/normcpu/SITE/DATE/2020/4/2020/6/all/localinfrajobs/
Hours per quarter:
Month 1 | 33906499 | 7408536 | 14595926 | 55910961 | Q1: 2160/2184 (if leap year)
Month 2 | 27476151 | 21606621 | 16298019 | 65380791 | Q2: 2184
Month 3 | 30778015 | 24674782 | 17479524 | 72932321 | Q3: 2208
Total: | 92160665 | 53689939 | 48373469 | 194224073 | Q4: 2208
% Utilisation | 92.62% | 245.8% | 49.96% | 89.03% | ECDF cloud: https://accounting.egi.eu/cloud/site/UKI-SCOTGRID-ECDF/sum_elap_processors/VO/DATE/2020/4/2020/6/all/localinfrajobs/ * 21.0 HEPSPEC (average from historical data and using non-HT CPU)
WallClock Hours (HS06) | Durham | Edinburgh | Glasgow | Total | Notes
Hours this Quarter | 2184 | 2184 | 2184 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 99503040 | 21840000 | 96823272 | 218166312 | https://accounting.egi.eu/tier2/federation/UK-ScotGrid/normelap_processors/SITE/DATE/2020/4/2020/6/all/localinfrajobs/
Hours per quarter:
Month 1 | 33015758 | 7761157.622 | 17045016 | 57821931.622 | Q1: 2160/2184 (if leap year)
Month 2 | 26693410 | 22763124.574 | 17840639 | 67297173.574 | Q2: 2184
Month 3 | 30136871 | 26512829.916 | 20117532 | 76767232.916 | Q3: 2208
Total: | 89846039 | 57037112.112 | 55003187 | 201886338.112 | Q4: 2208
% Utilisation | 90.29% | 261.2% | 56.81% | 92.54% | ECDF cloud wallclock = (1.046 * CPU hours based on historical performance)
Storage LHC & IRIS: AVAILABLE (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 265 | 1044 | 4200 | 5509 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0.1 | 0 | 300 | 300.1
Alice | 0 | 0 | 0 | 0
IRIS | 0 | 0 | 1000 | 1000
Storage LHC & IRIS: USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
Atlas | 235.86 | 723.6 | 1580 | 2539.46 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 1 | 1 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 72.36 | 72.36
Alice | 0 | 0 | 0 | 0 | ECDF site ATLAS use at low point as storage servers are being re-balanced to migrate to CentOS7 will increase to ~900T in next quarter
IRIS | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Durham | Edinburgh | Glasgow | Total | Notes
biomed | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
cernatschool.org | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/UK-ScotGrid/njobs/VO/DATE/2020/4/2020/6/all/localinfrajobs/
clas12 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
comet.j-parc.jp | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dune | 0 | 0 | 0 | 0
gridpp | 0 | 1 | 2 | 3
hyperk.org | 0 | 0 | 0 | 0
ilc | 0 | 0 | 0 | 0
iris.ac.uk | 0 | 0 | 0 | 0
lhcb | 0 | 0 | 0 | 0
lsst | 0 | 0 | 0 | 0
lz | 0 | 0 | 0 | 0
magrid | 0 | 0 | 0 | 0
mice | 0 | 0 | 1.9 | 1.9
na62.vo.gridpp.ac.uk | 0 | 0 | 3.8 | 3.8
ops | 0 | 0 | 0 | 0
pheno | 66.61 | 0 | 7.45 | 74.06
skatelescope.eu | 0 | 0 | 0 | 0
snoplus.snolab.ca | 0 | 0 | 0 | 0
solidexperiment.org | 0 | 0 | 0 | 0
t2k.org | 0 | 0 | 0 | 0
vo.moedal.org | 0 | 0 | 0 | 0
vo.northgrid.ac.uk | 0 | 0 | 0 | 0
vo.scotgrid.ac.uk | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Ongoing | LSST | Teng Li 50% LUSC DAC Team. Rob assisting James with LSST job submission via DIRAC
Ongoing | LZ | ECDF aiding in moving some workloads to the Grid.
Ongoing | DUNE | Provided effort into DUNE RUCIO deployment and data management
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Present | UK Members of DPM Collaboration | UK Data Storage (S. Skipsey)
Present | HTTP Deployment Working Group | S. Skipsey
Present | Member of Tier-2 Evolution Working Group | S.Skipsey
Present | WLCG Sytem Performance and Cost Modelling WG | Gareth Roy
Present | Member of WLCG DOMA-Access WG | Teng Li
Present | Member of LHCb RTA | Robert Currie
Present | Member of the WLCG DOMA-QoS WG | Robert Currie
Date | Other Outputs and Knowledge Exchange | Notes