## Resource & Narrative
Year | 2020 | Area | SouthGrid
Quarter | Q3 | Reporter | PG
Narrative
Area | Successes |  |  | Problems
Birmingham | Continued to keep the site going despite minimal access to the machines. Started reinstalling the last of the SL6 machines (EOS related). |  |  | Still trying to find the time and manpower to install new hardware. This will hopefully be done in the New Year. Just before Christmas an aircon unit failed so had to reduce the number of active worker nodes.
Bristol | New HTCondor-CE lcgce02 into production!! success! APEL accounting working. Perfsonar (new RAL hardware) in production & looking very good in monitoring. 7-OS u/g of lcgarg. Retired ARC-CE. |  |  | Serious network outages due to IT Networks firmware update on main LCG router - 3.5 days as they tried to fiddle/fix it before giving up & rolling back firmware. Another odd outage 16-23 Dec where lost all outgoing to VOMS servers etc. IT Networks disclaimed all knowledge of that! (We have our doubts)
Cambridge
Oxford | New monitoring server is now in production. New Cent OS 7 voms server |  |  | 12/11/2020: Accountig broke in ARC6, had to change the arc config and republish. 20/10/2020 - 27/10/2020 - Datacentre work on the power Busbar resulted on 40 worker nodes (1140 local cpus) offlined. 20/11/2020 - 24/11/2020: Offlined 40 nodes to move the rack. 16/12/2020 - replacement Cent OS7 Squid/DHCP server failed.
RAL PPD | Testing Worker Nodes on STFC Cloud Upgrade remaining non grid services from SL6 to C7 (Grid Services completed in previous Quarter) |  |  | Accounting appears to be broken for the full quarter. Have modified config and republished Atlas cannot sumbit jobs to one ArcCE, despite it being identical (as far as we can tell) to the others and working for all other VOs Reinstalled it in November, accounting before this probably lost.
Sussex | New GridPP cluster setup and running with ARC CE6 and three working nodes all on centOS 7. |  |  | Despite limited access to the data centre I have racked the legacy cluster nodes, new network switches and new worker nodes. Aiming for all 16 nodes to be online by end February 2021
Risks
Type | Risk |  |  | Mitigation
Birmingham
Bristol | Shortage of human-power |  |  | Regular Ops & Southgrid meetings helpful, despite stretched resources!
Cambridge
Oxford | Storage disks failing Storage pool nodes are still on SL6 Replacement Squid/DHCP server failed Several mother board and memory module failures. |  |  | Replace disks from decommissioned servers Go Storageless site Squid/DHCP server - reverted back to old SL6 - replace the hardware. Replaced under warranty
RAL PPD
Sussex | New GridPP cluster setup and running with ARC CE6 and three working nodes all on centOS 7. |  |  | Despite limited access to the data centre I have racked the legacy cluster nodes, new network switches and new worker nodes. Aiming for all 16 nodes to be online by end February 2021
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-12-13 | BRISTOL: replace ARC-CE lcgce01 with HTCondor-CE lcgce02 |  |  | Retire ARC-5 lcgce01 DONE; rebuild all 6-OS WN as 7-OS: ONGOING - having some build issues.
2020-11-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | can retire lcgse01 NO PROGRESS due to urgency with lcgce02 (& lack of Dr Kreczko time)
2020-11-30 | BRISTOL: replace existing lcgarg (6-OS) with 7-OS version |  |  | DONE
2020-10-30 | BRISTOL: new RAL-donated Perfsonar install/build/configure |  |  | IN PRODUCTION
2020-12-31 | BRISTOL: support for mu3e VO |  |  | DONE
2020-11-20 | OXFORD: replace SL6 VOMS server with CentOS 7 version |  |  | New VOMS VM
2020-11-20 | OXFORD: replace SL6 Squid/DHCP server with CentOS 7 version |  |  | New Squid/DHCP server
2020-11-10 | OXFORD: replace the old monitoring server |  |  | New monitoring server
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-03-31 | BRISTOL: progress on replacing lcgse01 with xrootd-only (io02) |  |  | can retire lcgse01 (and DMLite)
2021-03-31 | BRISTOL:New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future
2021-03-31 | BRISTOL:Continue cleaning up and labelling of network cables
2021-03-31 | BRISTOL:Completed all 6-OS DICE WN u/g to 7-OS |  |  | No more 6-OS WN
2021-03-31 | BRISTOL:START work on documenting DICE for IS.Security + IT-FITS-SE support |  |  | WIP
2021-03-31 | BRISTOL:START work on migrating DICE Stacki to IT-FITS-SE foreman + puppet |  |  | WIP
2021-03-31 | OXFORD: replace hardware for the new Squid/DHCP server |  |  | retire old Squid/DHCP server
2021-03-31 | OXFORD: decommision old DPM storage servers. |  |  | Storageless site.
2021-03-31 | OXFORD: test Xcache on old hardware |  |  | Xcache tested.

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 4 | 100% | 5% | 263.8% | MOK | % of WLCG Pledged CPU Available - SouthGrid |  |  | Metric OK | MOK
1b | 8 | 100% | 5% | 215.9% | MOK | % of WLCG Pledged Disk Available - SouthGrid |  |  | Metric Clost to Target | MCT
1b | 12 | 50% | 5% | 71.84% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid |  |  | Metric not OK | MFL
1b | 19 | 95% | 5% | 92.87% | MCT | Average Argo Availability - SouthGrid |  |  | Metric with no Target | MNO
1b | 20 | 95% | 5% | 93.55% | MCT | Average Argo Reliability - SouthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
CPU Available (HS06) | 22768 | 26780 | 8500 | 45682 | 55500 | 3580 | 162810 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 9466 | 7292 | 3965 | 15882 | 22851 | 2257 | 61713
% of Pledge | 240.5% | 367.3% | 214.4% | 287.6% | 242.9% | 158.6% | 263.8%
Storage Available (TB) | 1717 | 1085 |  | 910 | 3600 |  | 7312
Storage Pledged (TB) | 1040 | 0 | 0 | 301 | 2045 | 0 | 3386
% of Pledge | 165.1% | #DIV/0! | #DIV/0! | 302.3% | 176% | #DIV/0! | 215.9%
Availability | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 |  | 99.88 | 97.98 |  | 99.29% | Availability numbers from the last quarter can be found at the following link:
Month 2 |  | 89.35 |  | 99.34 | 98.95 |  | 95.88% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 88.04 |  | 99.97 | 92.1 | 63.07 | 85.8% | Birmingham and Cambridge not shown as VAC sites don't get monitored.
% Tier-2 Averge | #DIV/0! | 92.4633 | #DIV/0! | 99.73 | 96.3433 | 63.07 | 92.87%
Reliability | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 100 |  | 99.88 | 97.98 |  | 99.29% | Reliability numbers from the last quarter can be found at the following link:
Month 2 |  | 96.22 |  | 99.34 | 98.95 |  | 98.17% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 88.04 |  | 99.97 | 92.1 | 63.07 | 85.8%
% Tier-2 Total | #DIV/0! | 94.7533 | #DIV/0! | 99.73 | 96.3433 | 63.07 | 93.55%
CPU Hours (HS06) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 18768000 | 100865856 | 122544000 | 7904640 | 229035840 | https://accounting.egi.eu/tier2/federation/SouthGrid/normcpu/SITE/DATE/2020/10/2020/12/all/localinfrajobs/
Hours per quarter:
Month 1 | 7366926 | 2584183 | 6026993 | 29370610 | 27344912 |  | 72693624 | Q1: 2160/2184 (if leap year)
Month 2 | 7729540 | 8096980 | 6022823 | 21684703 | 25732694 |  | 69266740 | Q2: 2184
Month 3 | 4827991 | 7868224 | 5380087 | 20089039 | 35170763 |  | 73336104 | Q3: 2208
Total: | 19924457 | 18549387 | 17429903 | 71144352 | 88248369 | 0 | 215296468 | Q4: 2208
% Utilisation | 39.63% | 31.37% | 92.87% | 70.53% | 72.01% | 0% | 94%
WallClock Hours (HS06) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 18768000 | 100865856 | 122544000 | 7904640 | 359484480 | https://accounting.egi.eu/tier2/federation/SouthGrid/normelap_processors/SITE/DATE/2020/10/2020/12/all/localinfrajobs/
Hours per quarter:
Month 1 | 8549403 | 3959122 | 7260497 | 33573825 | 30926506 |  | 84269353 | Q1: 2160/2184 (if leap year)
Month 2 | 8956518 | 10251121 | 7126311 | 23133388 | 30991066 |  | 80458404 | Q2: 2184
Month 3 | 7624122 | 11786160 | 7310396 | 22686708 | 44133949 |  | 93541335 | Q3: 2208
Total: | 25130043 | 25996403 | 21697204 | 79393921 | 106051521 | 0 | 258269092 | Q4: 2208
% Utilisation | 49.99% | 43.96% | 115.6% | 78.71% | 86.54% | 0% | 71.84%
Storage LHC & IRIS: AVAILABLE (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 740 | 690 | 0 | 1510 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 384 | 0 | 0 | 0 | 0 | 384 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 0 | 520 | 0 | 520
Alice | 1637 | 0 | 0 | 0 | 0 | 0 | 1637
IRIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 630 | 599 | 0 | 1309 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 325 | 0 | 0 | 0 | 0 | 325 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 0 | 0 | 380 | 0 | 380 | https://monit-grafana.cern.ch/d/mHqFLAbik/wlcg-storage-space-accounting?orgId=20&var-vo=LHCb&var-tier=Tier-2&var-country=GB&var-federation=All&var-medium=Disk&var-site=All&var-service=All&var-area=All&var-groupby=site&var-binning=1d
Alice | 566.5 | 0 | 0 | 0 | 0 | 0 | 566.5
IRIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/UK-SouthGrid/njobs/VO/DATE/2020/10/2020/12/all/localinfrajobs/
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes