## Resource & Narrative
Year | 2020 | Area | SouthGrid
Quarter | Q3 | Reporter | PG
Narrative
Area | Successes |  |  | Problems
Birmingham | Have managed kept the site operating during the COVID even with restricted access to the machine rooms. |  |  | The number of jobs that need to be done are now starting to pile up (racking servers, disk replacements, major upgrades, etc.). Will hopefully gradually work through these over the next quarter now we have more access. However, putting in the larger new equipment (e.g. disk servers) is going to be difficult without more significant protective clothing.
Bristol | started getting new HTCondor-CE lcgce02 into production, initial tests seemed success! Starting to get APEL accounting working. 2 User-use HighMemory nodes in production. Retired all the oldest LCG WN = DNUK & ViglenTwins! (ca 2009!) |  |  | Turns out lcgce02 = super problems both with VOs & APEL, ggus tickets for help for both issues
Cambridge
Oxford | 7x new worker nodes installed with 896 logical cores. New perfsonar box installed and running. Planned downtime 8/7 -> 10/7 Due to ARC5 -> ARC6 upgrade. Power outage at DWB affected VMs which took out the service 21/8 -> 24/8 |  |  | Accountig broke following ARC6 upgrade, now need to fix and republish.
RAL PPD | Drained and reinstalled all remaining SL6 Disk servers SL6 BDII replaced with new C7 VM Testing of cloud worker nodes No new Disk or CPU came online in this quarter.
Sussex
Risks
Type | Risk |  |  | Mitigation
Birmingham
Bristol | Shortage of human-power |  |  | Regular Ops & Southgrid meetings helpful, despite stretched resources!
Cambridge
Oxford
RAL PPD
Sussex
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-10-31 | BRISTOL: lcgce02 in production with working accounting! |  |  | can retire ARC-5 lcgce01 & rebuild all 6-OS WN as 7-OS; this did not happen by end Q3, but did by DueDate (which is in Q4)
2020-11-30 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | NO PROGRESS due to urgency with lcgce02 (& lack of Dr Kreczko time)
2020-11-30 | BRISTOL: replace existing lcgarg (6-OS) with 7-OS version |  |  | one less 6-OS production node; NO PROGRESS due to lcgce02 (& lack of Dr Kreczko time)
2020-09-30 | BRISTOL: new RAL-donated Perfsonar install/build/configure |  |  | new perfsonar in production (finally arrived Aug 5) NO PROGRESS due to urgency with lcgce02 (& lack of DrKreczko time)
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-10-31 | BRISTOL: lcgce02 in production with working accounting! |  |  | Accounting + 'wedging' both debugged in Oct, now ce02 seems satisfyingly production
2021-01-31 | BRISTOL: retire ARC-5 CE lcgce01 |  |  | rebuild all 6-OS WN as 7-OS
2021-02-28 | BRISTOL: replace lcgse01 with xrootd-only (io02) |  |  | can retire lcgse01
2021-01-31 | BRISTOL: replace existing lcgarg (6-OS) with 7-OS version |  |  | one less 6-OS production node
2020-09-30 | BRISTOL: new RAL-donated Perfsonar install/build/configure |  |  | Already in production by 31/10/2020
2020-12-31 | BRISTOL: New DICE NFS & 'other storage' server |  |  | Initially replacing PP+Dept NFS servers, 'more ambitious' OpenCloud+Jupyter in future

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 4 | 100% | 5% | 263.8% | MOK | % of WLCG Pledged CPU Available - SouthGrid |  |  | Metric OK | MOK
1b | 8 | 100% | 5% | 192.2% | MOK | % of WLCG Pledged Disk Available - SouthGrid |  |  | Metric Clost to Target | MCT
1b | 12 | 50% | 5% | 53.2% | MOK | % CPU Utilisation (Wall Clock) - SouthGrid |  |  | Metric not OK | MFL
1b | 19 | 95% | 5% | 73.88% | MFL | Average Argo Availability - SouthGrid |  |  | Metric with no Target | MNO
1b | 20 | 95% | 5% | 74.15% | MFL | Average Argo Reliability - SouthGrid | Squewed by missing data from some smaller sites

## Resources
Please fill in all fields highlighed in
Capacities | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
CPU Available (HS06) | 22768 | 26780 | 8500 | 45682 | 55500 | 3580 | 162810 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 9466 | 7292 | 3965 | 15882 | 22851 | 2257 | 61713
% of Pledge | 240.5% | 367.3% | 214.4% | 287.6% | 242.9% | 158.6% | 263.8%
Storage Available (TB) | 1717 | 1085 |  | 910 | 3600 |  | 7312
Storage Pledged (TB) | 1040 | 400 | 0 | 301 | 2045 | 18 | 3804
% of Pledge | 165.1% | 271.2% | #DIV/0! | 302.3% | 176% | 0% | 192.2%
Availability | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 98 |  | 94.14 | 99.29 | 0 | 72.86% | Availability numbers from the last quarter can be found at the following link:
Month 2 |  | 100 |  | 99.46 | 94.03 | 3.23 | 74.18% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 99.73 |  | 99.35 | 99.32 | 0 | 74.6% | Birmingham and Cambridge not shown as VAC sites don't get monitored.
% Tier-2 Averge | #DIV/0! | 99.2433 | #DIV/0! | 97.65 | 97.5467 | 1.0767 | 73.88%
Reliability | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Avg | Notes
Month 1 |  | 98 |  | 97.37 | 99.29 | 0 | 73.67% | Reliability numbers from the last quarter can be found at the following link:
Month 2 |  | 100 |  | 99.46 | 94.03 | 3.23 | 74.18% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 |  | 99.73 |  | 99.35 | 99.32 | 0 | 74.6%
% Tier-2 Total | #DIV/0! | 99.2433 | #DIV/0! | 98.7267 | 97.5467 | 1.0767 | 74.15%
CPU Hours (HS06) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 18768000 | 100865856 | 122544000 | 7904640 | 229035840 | https://accounting.egi.eu/tier2/federation/SouthGrid/normcpu/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 7787928 | 9458714 | 3592674 | 5872741 | 35841938 |  | 62553995 | Q1: 2160/2184 (if leap year)
Month 2 | 8741007 | 13054230 | 5338290 | 1971056 | 31313433 |  | 60418016 | Q2: 2184
Month 3 | 8273902 | 12879038 | 5739203 | 2288726 | 5647951 |  | 34828820 | Q3: 2208
Total: | 24802837 | 35391982 | 14670167 | 10132523 | 72803322 | 0 | 157800831 | Q4: 2208
% Utilisation | 49.34% | 59.85% | 78.17% | 10.05% | 59.41% | 0% | 68.9%
WallClock Hours (HS06) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Hours this Quarter | 2208 | 2208 | 2208 | 2208 | 2208 | 2208 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 50271744 | 59130240 | 18768000 | 100865856 | 122544000 | 7904640 | 359484480 | https://accounting.egi.eu/tier2/federation/SouthGrid/normelap_processors/SITE/DATE/2020/7/2020/9/all/localinfrajobs/
Hours per quarter:
Month 1 | 8982190 | 11720769 | 5122312 | 6626573 | 45573178 |  | 78025022 | Q1: 2160/2184 (if leap year)
Month 2 | 10489280 | 14068236 | 6630541 | 2231996 | 37740582 |  | 71160635 | Q2: 2184
Month 3 | 9858758 | 15859822 | 7103999 | 2606409 | 6643863 |  | 42072851 | Q3: 2208
Total: | 29330228 | 41648827 | 18856852 | 11464978 | 89957623 | 0 | 191258508 | Q4: 2208
% Utilisation | 58.34% | 70.44% | 100.5% | 11.37% | 73.41% | 0% | 53.2%
Storage LHC & IRIS: AVAILABLE (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 740 | 690 | 0 | 1510 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 384 | 0 | 0 | 0 | 0 | 384 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 0 | 0 | 0 | 520 | 0 | 520
Alice | 1637 | 0 | 0 | 0 | 0 | 0 | 1637
IRIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage LHC & IRIS: USED (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
Atlas | 80 | 0 | 0 | 630 | 599 | 0 | 1309 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 325 | 0 | 0 | 0 | 0 | 325 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 0 | 0 | 0 | 380 | 0 | 380 | https://monit-grafana.cern.ch/d/mHqFLAbik/wlcg-storage-space-accounting?orgId=20&var-vo=LHCb&var-tier=Tier-2&var-country=GB&var-federation=All&var-medium=Disk&var-site=All&var-service=All&var-area=All&var-groupby=site&var-binning=1d
Alice | 566.5 | 0 | 0 | 0 | 0 | 0 | 566.5
IRIS | 0 | 0 | 0 | 0 | 0 | 0 | 0
Storage - Other : USED (TB) | Bimingham | Bristol | Cambridge | Oxford | RAL PPD | Sussex | Total | Notes
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | Active VOs at you site can be assesed from the following link:
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://accounting.egi.eu/tier2/federation/SouthGrid/njobs/VO/DATE/2020/7/2020/9/all/localinfrajobs/
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on F41: Peter Gronbech: Peter Gronbech: Just noticed that Accounting is broken on our new ARC 6 server hence gross under reporting

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes