## Resource & Narrative
Year | 2020 | Area | ATLAS
Quarter | Q2 | Reporter | JW |  | Approved | RJ
Narrative
Area | Successes |  |  | Problems
Task 1 | Studies into stage-in and stage-out timeout issues; performance with new Workernodes investigated
Task 2 | Direct-IO jobs enabled for Analysis at RAL
Risks
Type | Risk |  |  | Mitigation
General | Aging hardware (particularly disk servers) |  |  | When significant failures occur, minimise additional disruption to site by marking lost files as temporarily unavailable to relieve deletion errors.
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Ongoing | * Helping Glasgow set up and test Ceph storage for use with ATLAS. |  |  | Successful jobs running and DDM operations, Issues continue with Xrootd write back from jobs to disk
End of Quarter | To configure third-party copy for ECHO using xrootd protocol |  |  | Add xrootd third-party copy to DOMA stress tests
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Ongoing | Chair ATLAS UK Cloud support meetings and help UK Cloud Squad. |  |  | The main matters for discussion were: bringing Sussex back online, Glasgow Ceph storage and failure of one of their disk servers, and Grand Unification of PanDA queues
Ongoing | Response to operational issues at RAL-Tier1.
Ongoing | To configure Third-party-copy using http for ECHO |  |  | To run successfully in DOMA smoke and stress tests

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 1 | 95% | 5% | 90% | MOK | T1 Job success rates from ATLAS dashboard (site-only metrics) | Occasional issues with Core ATLAS services (CTA, Frontier, Hamercloud, DB updates) resulted in some loss of site efficiency. |  | Metric OK | MOK
2 | 2 | 98% | 5% | 97% | MOK | T1 Data availability from the ATLAS dashboard |  |  | Metric Clost to Target | MCT
2 | 3 | 98% | 5% | 97.9% | MOK | Data acceptance from Tier 0/Tier 1s/Tier 2s - ATLAS SAM tests | Partial period data used, as migration to new MONIT interface and decommissioning of old site. SHEF excluded from calculation as offline for upgrade in period. |  | Metric not OK | MFL
2 | 4 | 95% | 5% | 95.7% | MOK | Production job success rates (site only metrics) - from PANDA dashboard |  |  | Metric with no Target | MNO
2 | 5 | 95% | 5% | 97% | MOK | Data availability from the ATLAS dashboard; if we can automate this reliably
2 | 6 | 95% | 5% | 96.5% | MOK | Data acceptance at Tier-2s
2 | 7 | 5% | 1% | 0.1% | MOK | Data loss at Tier-2s | Significant (O(10k) files) data loss Glasgow; most data unrecoverable
2 | 8 | 95% | 5% | 90.9% | MCT | Atlas job success in production | Site storage issues general main factor impacting on job success rate
2 | 9 | 95% | 5% | 93.5% | MOK | ATLAS job success rates in user analysis
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
2020-04-01 | Stewart Martin-Haugh, Tim Adye | Stewart and Tim return to full-time ATLAS activities within RAL, PPD, ATLAS
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes