## Resource & Narrative
Year | 2020 | Area | ATLAS
Quarter | Q3 | Reporter | JW |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Task 1 | Updates to pilot code within ATLAS. Staging failure rate substantially reduced. |  |  | Direct-IO access. Low failure in file reads. Work started in implementation of vector reads at xrootd-ceph layer to mitigate issues
Task 2 | Third-party-copy with xrootd-ceph; WLCG plans focus on TPC-http, with aim for token based authorisation; tests and development work on RAL test gateway prior to |  |  | Devopment work required at xrootd-ceph and xrootd software layers necessary before TPC-http will work. Effort is underway
Risks
Type | Risk |  |  | Mitigation
General | Data loss at T2 sites. DPM storage failures at Glasgow, MAN, LANCS. Covid and associtiated restrictions contributing factor |  |  | Covid secure machine rooms. Availability of Spares for single drive failures. Long term perspective on next-gen storage solutions.
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Ongoing | * Helping Glasgow set up and test Ceph storage for use with ATLAS. |  |  | Successful jobs running and DDM operations, Issues continue with Xrootd write back from jobs to disk
End of Quarter | To configure Third-party-copy using http for ECHO |  |  | Add xrootd third-party copy to DOMA stress tests. Problems identified with TPC-http
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Ongoing | Chair ATLAS UK Cloud support meetings and help UK Cloud Squad. |  |  | The main matters for discussion were: bringing Sussex back online, Glasgow Ceph storage and failure of one of their disk servers, and Grand Unification of PanDA queues
Ongoing | Response to operational issues at RAL-Tier1.
Ongoing | To configure Third-party-copy using http for ECHO |  |  | To run successfully in DOMA smoke and stress tests

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 1 | 95% | 5% | 97.23% | MOK | T1 Job success rates from ATLAS dashboard (site-only metrics) |  |  | Metric OK | MOK
2 | 2 | 98% | 5% | 99.31% | MOK | T1 Data availability from the ATLAS dashboard (from Monit-Grafana Panda) | Data avaialbilty does not consider failed access in direct-IO analysis jobs |  | Metric Clost to Target | MCT
2 | 3 | 98% | 5% | 93.23% | MCT | Data acceptance from Tier 0/Tier 1s/Tier 2s - ATLAS SAM tests (from WLCG SiteMon) | QMUL 10 day downtime (planned + extended) brings down average |  | Metric not OK | MFL
2 | 4 | 95% | 5% | 97.15% | MOK | T1 Production job success rates (site only metrics) - from PANDA dashboard |  |  | Metric with no Target | MNO
2 | 5 | 95% | 5% | 98.15% | MOK | Data availability from the ATLAS dashboard; (from Monit-Grafana Panda)
2 | 6 | 95% | 5% | 97.38% | MOK | Data acceptance at Tier-2s (from Monit-Grafana Panda) | QMUL 10 day downtime (planned + extended) brings down average
2 | 7 | 5% | 1% | 0.6% | MOK | Data loss at Tier-2s | Significant data loss Glasgow; most data unrecoverable
2 | 8 | 95% | 5% | 93.48% | MCT | Atlas job success in production | Disk server failures at UKI-NORTHGRID-LANCS-HEP major contribution to reduced metric value
2 | 9 | 95% | 5% | 93% | MCT | ATLAS job success rates in user analysis | Disk server failures at UKI-NORTHGRID-LANCS-HEP major contribution to reduced metric value
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to ATLAS during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes