## Resource & Narrative
Year | 2020 | Area | CMS
Quarter | Q2 | Reporter | KE |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Tier 1 | Failure rate was similar to other T1s. LogCollect jobs still need fixing by CMS developers |  |  | Job efficiency was poor on average compared to other T1s. Work continues to investigate
Tier 2s | Site availability was good |  |  | Failure rate too high for both production and analysis jobs
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [8 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments |  | Colour | Description | Code
2 | 10 |  | 5% |  | AWI | Tier-1 Data Transfer Quality | 5 |  |  | Metric OK | MOK
2 | 11 | 5% or pledge | 5% |  | AWI | Timely and efficient availability and use of resources at RAL T1 (Global %) | Batch farm provision is well above pledged CPU when averaged over the quarter. 11.2% of all completed jobs from T1 sites | https://monit-grafana.cern.ch/d/000000628/cms-job-monitoring-es-agg-data-official?orgId=11&from=1585699200000&to=1593561600000&var-group_by=Country&var-Tier=All&var-CMS_WMTool=All&var-CMS_SubmissionTool=All&var-CMS_CampaignType=All&var-Site=T1_DE_KIT&var-Site=T1_ES_PIC&var-Site=T1_FR_CCIN2P3&var-Site=T1_IT_CNAF&var-Site=T1_RU_JINR&var-Site=T1_UK_RAL&var-Site=T1_US_FNAL&var-Type=All&var-CMS_JobType=All&var-CMSPrimaryDataTier=All&var-binning=1d |  | Metric Clost to Target | MCT
2 | 12 | 70% | 5% |  | AWI | Tier-1 Average CPU Efficiency | 58% (20 percentage points below other T1s, typically) | https://monit-grafana.cern.ch/d/C8ewaCrWk/hs06-report?from=1585695600000&orgId=11&to=1593557999000 |  | Metric not OK | MFL
2 | 13 | 10% | 5% |  | AWI | Tier-1 Failure Rate | 18% - however, 30-50% of these failures are LogCollect. This problem has been known for some time but the developer has no time to fix it | https://monit-grafana.cern.ch/d/C8ewaCrWk/hs06-report?from=1585695600000&orgId=11&to=1593557999000 |  | Metric with no Target | MNO
2 | 14 | 97% | 5% |  | AWI | Site availability at the Tier-1 | 98% | David estimates this from monthly reports
2 | 15 | 5% | 5% |  | AWI | Data access efficiency via AAA, measured as variance from Global Tier-1 Average | I have no idea how to determine this, although I would like to!
2 | 16 | 0% | 1% |  | AWI | Custodial Data Loss at Tier-1 | None
2 | 17 |  | 5% |  | AWI | Transfer rates to the UK Tier 2s | Looks ok for now. We will find a better metric next time. | https://cmsweb.cern.ch/phedex/prod/Activity::RatePlots?graph=quantity_rates&entity=dest&src_filter=&dest_filter=T2_UK_*&no_mss=true&period=l26w&upto=&.submit=Update
2 | 18 | 80% | 5% |  | AWI | Site availability at the Tier-2s | IC had a problem in June with SAM test failures - average ~90% for the quarter. Other T2s ~high 90s% | David estimates this from monthly reports
2 | 19 | 80% | 5% |  | AWI | Site reliability at the Tier-2s | IC had a problem in June with SAM test failures - average ~90% for the quarter. Other T2s ~high 90s% | David estimates this from monthly reports
2 | 20 | 0% | 5% |  | AWI | Unique data loss at Tier-2s | None
2 | 21 | 30% | 5% |  | AWI | Failed analysis jobs | T1 has around 20 % failures, similar to other T1s. T2s have high failure rate - around 35%
2 | 22 | 20% | 5% |  | AWI | Failed production jobs | Tier 1 in line with other T1. Typically <20%. T2s have high failre rate - around 30%
2 | 23 | 5% | 5% |  | AWI | T2 sites provide an appropriate level of resource to CMS | UK T2s did 7% of all completed jobs by T2s worldwide
2 | 24 | 80% | 5% |  | AWI | Job performance/efficiency using AAA data transfer | We have no way to measure this
Milestones | [8 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments |  | Colour | Description | Code
2 | 5 | 2020-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  |  | Milestone Achieved | MSA
2 | 6 | 2021-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  |  | Milestone Ongoing | MOG
2 | 7 | 2022-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  |  | Milestone Overdue | MOD
2 | 8 | 2023-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  |  | Milestone not due | MSU
2 | 17 | 2020-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 18 | 2021-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 19 | 2021-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 20 | 2022-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 21 | 2022-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 22 | 2023-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 23 | 2023-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 24 | 2024-04-01 | N |  | MSU | Review of CMS AAA Efficiency

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes