## Resource & Narrative
Year | 2020 | Area | CMS
Quarter | Q4 | Reporter | KE |  | Approved | DC
Narrative
Area | Successes |  |  | Problems
Tier 1 | Switch from Phedex to Rucio went smoothly |  |  | The network to the T1 batch farm is extremely poor, and probably the cause of very low efficiencies when reading data from Offsite.
Tier 2s | Switch from Phedex to Rucio went smoothly
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 10 |  | 5% |  | AWI | Tier-1 Data Transfer Quality | No major problems for site to site transfers. At the end of the quarter, the tape pledge was filled so further transfers were stopped. |  | Metric OK | MOK
2 | 11 | 5% or pledge | 5% |  | AWI | Timely and efficient availability and use of resources at RAL T1 (Global %) | Batch farm provision is above pledge for the entire quarter except nearly 2 weeks in early October when we were put into drain for Production jobs. Analysis jobs took some of the spare capacity but still left us under pledge. RAL ran 10.5% of completed T1 jobs during the quarter. |  | Metric Clost to Target | MCT
2 | 12 | 70% | 5% | 46% | MFL | Tier-1 Average CPU Efficiency | 46% - same as last quarter, again around 30 percentage points below other T1s. The increased number of analysis jobs whilest in drain, and a good period in late-Nov helped prop this number up. No progress on improving the very poor network speed reported in the last quarter. |  | Metric not OK | MFL
2 | 13 | 10% | 5% | 29% | MOK | Tier-1 Failure Rate | 29% which is 6 percentage points up on last quarter, possibly concerning. Only 14% of these are LogCollect jobs which always fail for known reasons. A large proportion appear to be User Analysis jobs in 3 isolated spikes. However, much higher than other T1s (FNAL is close, clearly had a problem in Dec). |  | Metric with no Target | MNO
2 | 14 | 97% | 5% | 99% | MOK | Site availability at the Tier-1 | "SAM 1 day availability" is 95.5%. However, using the same source as the T2s I get 99%
2 | 15 | 5% | 5% |  | AWI | Data access efficiency via AAA, measured as variance from Global Tier-1 Average | This metric was brought over from GridPP5 as interpreted from the CMS Review of metrics document, it likely was misunderstood from the T1 and T2 AAA transfer comments at the end of the report. We should discuss at the PMB if this is required or should be altered
2 | 16 | 0% | 1% | 0% | MOK | Custodial Data Loss at Tier-1 | None
2 | 17 |  | 5% |  | AWI | Transfer rates to the UK Tier 2s | Nothing particular to report
2 | 18 | 80% | 5% | 99% | MOK | Site availability at the Tier-2s | IC - 100%, Brunel 97%, RALPP 99% Estimated from https://monit-wlcg-sitemon.web.cern.ch/monit-wlcg-sitemon/reports/2020/202012/wlcg/WLCG_All_Sites_CMS_Dec2020.pdf
2 | 19 | 80% | 5% | 99% | MOK | Site reliability at the Tier-2s | IC - 100%, Brunel 97%, RALPP 99% Same source as above
2 | 20 | 0% | 5% | 0% | MOK | Unique data loss at Tier-2s | None
2 | 21 | 30% | 5% | 25% | MCT | Failed analysis jobs | T2s averaging ~20-25% failure rate for analysis jobs, which is a good improvement on the last quarter.
2 | 22 | 20% | 5% | 15% | MCT | Failed production jobs | T2s averaging ~15% failure rate for prod jobs, which is a good improvement on the last quarter.
2 | 23 | 5% | 5% | 4.7% | MCT | T2 sites provide an appropriate level of resource to CMS | UK sites completed 4.7% of all T2 jobs for CMS
2 | 24 | 80% | 5% |  | AWI | Job performance/efficiency using AAA data transfer | This metric was brought over from GridPP5 as interpreted from the CMS Review of metrics document, it likely was misunderstood from the T1 and T2 AAA transfer comments at the end of the report. We should discuss at the PMB if this is required or should be altered
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 5 | 2020-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  | Milestone Achieved | MSA
2 | 6 | 2021-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  | Milestone Ongoing | MOG
2 | 7 | 2022-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  | Milestone Overdue | MOD
2 | 8 | 2023-12-01 | N |  | MSU | Report on delivery to CMS during year |  |  | Milestone not due | MSU
2 | 17 | 2020-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 18 | 2021-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 19 | 2021-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 20 | 2022-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 21 | 2022-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 22 | 2023-04-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 23 | 2023-10-01 | N |  | MSU | Review of CMS AAA Efficiency
2 | 24 | 2024-04-01 | N |  | MSU | Review of CMS AAA Efficiency

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes