## Resource & Narrative
Year | 2020 | Area | LHCb
Quarter | Q2 | Reporter | RN |  | Approved | AmcN
Narrative
Area | Successes |  |  | Problems
Task 1 | Monte Carlo, data reprocessing, support for sites moving out of ARC v5 and Cream CE into HTCondor or ARC v6 Ces |  |  | Problems with xrootd streaming from Tier-1 ECHO storage to RAL Worker nodes. Being investigated jointly by LHCb and Tier-1
Task 2 | GEOC Shifts by Mark Slater. VO-box maintenance by Raja Nandakumar
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 25 | 90% | 5% | 74% | MFL | Tier-1 prod CPU efficiency | Note : The “prod” here refers to reprocessing productions. Simulation at the Tier-1 is not tracked here, but anyway follows lines 10 and 11 below quite closely. Most of the jobs here were merging jobs which anyway are dominated by the time for downloading input and so, low efficiency |  | Metric OK | MOK
2 | 26 | 50% | 5% | 76.9% | MOK | Tier-1 user success rate |  |  | Metric Clost to Target | MCT
2 | 27 | 70% | 5% | 62.5% | MFL | Tier-1 user CPU efficiency | Dominated by xrootd issues as commented in the narrative |  | Metric not OK | MFL
2 | 28 | 15% | 5% | 21% | MOK | UK Tier-1 work fraction |  |  | Metric with no Target | MNO
2 | 29 | 50% | 5% | 85% | MOK | Tier-2A : User success rate
2 | 30 | 70% | 5% | 94.5% | MOK | Tier-2A : User CPU efficiency
2 | 31 | 90% | 5% | 97.6% | MOK | All Tier-2: Simulation success rate
2 | 32 | 90% | 5% | 98.2% | MOK | All Tier-2: Simulation CPU efficiency
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes