## Resource & Narrative
Year | 2020 | Area | LHCb
Quarter | Q3 | Reporter | RN |  | Approved | AMcN
Narrative
Area | Successes |  |  | Problems
Task 1 | Tier-1 : We have finally identified a major issue with streaming files from ECHI@RAL and it will need development for which RAL has committed to provide. There is another possibility being investigated, currently waiting on the LHCb job test system to work properly |  |  | Tier -1 : Ongoing problems with streaming data from ECHO@RAL using CEPH. This is a major cause of job failure rate and user frustration with RAL as a site since the move to ECHO in May 2019. Some minor issues with the batch farm Ipv4 download speed issues.
Task 2 | General: VO-box maintenance by Raja GEOC shifts by Mark Slater |  |  | Tier-2 : Systematic problems with Sheffield due to lack of effort at the site. Some dirac issues causing problems with vac jobs
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 25 | 90% | 5% | 59% | MFL | Tier-1 prod CPU efficiency | The “prod” here refers to reprocessing productions. Simulation at the Tier-1 is not tracked here, but anyway follows lines 10 and 11 below quite closely. Most of the jobs here were merging jobs again which anyway are dominated by the time for downloading input and so, low efficiency |  | Metric OK | MOK
2 | 26 | 50% | 5% | 77.2% | MOK | Tier-1 user success rate |  |  | Metric Clost to Target | MCT
2 | 27 | 70% | 5% | 64.3% | MFL | Tier-1 user CPU efficiency | Dominated by xrootd issues as commented in the narrative |  | Metric not OK | MFL
2 | 28 | 15% | 5% | 23.9% | MOK | UK Tier-1 work fraction |  |  | Metric with no Target | MNO
2 | 29 | 50% | 5% | 85.9% | MOK | Tier-2A : User success rate
2 | 30 | 70% | 5% | 92.9% | MOK | Tier-2A : User CPU efficiency
2 | 31 | 90% | 5% | 98.4% | MOK | All Tier-2: Simulation success rate
2 | 32 | 90% | 5% | 98.3% | MOK | All Tier-2: Simulation CPU efficiency
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes