## Resource & Narrative
Year | 2020 | Area | LHCb
Quarter | Q3 | Reporter | RN |  | Approved | AMcN
Narrative
Area | Successes |  |  | Problems
Task 1 | Outside of the two problems listed, RAL has been remarkably stable. Appreciate quick work by RAL admins to resolve ARC GDPR issue over the christmas break |  |  | 1. Ongoing streaming from ECHO at the RAL Tier-1 : Problem identified, but no schedule for fix. Mitigation possibilities being evaluated 2. Problem with users opening files at RAL : Understood by LHCb in Jan 2021 with help of Tom Byrne. Partial fix deployed within LHCb software stack
Task 2 | Almost all issues handled by GGUS tickets, with very little need for further offline follow up. |  |  | Vac sites have slowly gone offline without much advertisement? Occasional issues with Tier-2 sites, especially networking which may be a point to keep in mind going forward
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc | Networking to various university sites |  |  | Investment in networking?
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 25 | 90% | 5% | 76.9% | MOK | Tier-1 prod CPU efficiency | Note that this is jobs not including simulation |  | Metric OK | MOK
2 | 26 | 50% | 5% | 77.5% | MOK | Tier-1 user success rate |  |  | Metric Clost to Target | MCT
2 | 27 | 70% | 5% | 59.4% | MOK | Tier-1 user CPU efficiency | Good enough I suppose, considering the ongoing ECHO streaming issue |  | Metric not OK | MFL
2 | 28 | 15% | 5% | 22.9% | MOK | UK Tier-1 work fraction | RAL has been quite reliable. |  | Metric with no Target | MNO
2 | 29 | 50% | 5% | 80.3% | MOK | Tier-2A : User success rate
2 | 30 | 70% | 5% | 96.1% | MOK | Tier-2A : User CPU efficiency | Dominated by user simulation
2 | 31 | 90% | 5% | 97.4% | MOK | All Tier-2: Simulation success rate
2 | 32 | 90% | 5% | 98.7% | MOK | All Tier-2: Simulation CPU efficiency
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
2 | 1 | 2020-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Achieved | MSA
2 | 2 | 2021-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Ongoing | MOG
2 | 3 | 2022-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone Overdue | MOD
2 | 4 | 2023-12-01 | N |  | MSU | Report on delivery to LHCb during year |  |  | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes