## Resource & Narrative
Year | 2020 | Area | Other VOs
Quarter | Q3 | Reporter | KE
Narrative
Area | Successes |  |  | Problems
Onboarding new VOs | Testing multi-VO Rucio with dteam
Supporting existing VOs through major campaigns | None
Service improvements
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 33 | 95% | 5% | 113% | MOK | UK Tier-1 work fraction for ALICE as a proportion of all Tier-1s (not CERN). Normalised to 3% for GridPP6 | https://accounting.egi.eu/tier1/elap_processors/TIER1/VO/2020/7/2020/9/all/onlyinfrajobs/ This value is clearly below the expected value. |  | Metric OK | MOK
2 | 34 | 70% | 10% | 53% | MFL | UK T1 CPU efficiency by ALICE. | https://accounting.egi.eu/tier1/cpueff/TIER1/VO/2020/7/2020/9/all/onlyinfrajobs/ Not fully using Echo, so possible reason for low efficiency, as increased number of Offsite reads |  | Metric Clost to Target | MCT
2 | 35 | 90% | 10% | 123% | MOK | UK T1 CPU usage by ALICE. Normalised against pledged HS06. | https://accounting.egi.eu/tier1/normelap_processors/TIER1/VO/2020/7/2020/9/all/onlyinfrajobs/ |  | Metric not OK | MFL
2 | 36 | 95% | 5% | 100% | MOK | UK Tier-2 work fraction for ALICE as a proportion of all Tier-2s. Normalised to 2.1% for GridPP6. | https://accounting.egi.eu/tier2/normelap_processors/COUNTRY/VO/2020/7/2020/9/custom-alice/onlyinfrajobs/ |  | Metric with no Target | MNO
2 | 37 | 70% | 10% | 91% | MOK | UK T2 CPU efficiency for Alice. | https://accounting.egi.eu/tier2/cpueff/COUNTRY/VO/2020/7/2020/9/custom-alice/onlyinfrajobs/
|  | 80% | 10% | 24% | MFL | ALICE disk usage at T1 (on last day of the quarter?) Pledge=1.32PB | 322 TB. https://s3.echo.stfc.ac.uk/srr/storagesummary_2020-09-30.json. George Patargias says RAL Echo was read-only for ALICE until mid-Sept, so this could be the reason. He also wonders if the query is using xrdfs, which will not work with Echo. Presumably this would then read zero though?
|  | 80% | 10% | 78% | MCT | ALICE tape usage at T1 (on last day of the quarter?) - 'occupied size'. Pledge=1.131PB | 887TB. http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_30092020
|  | 80% | 10% | 59% | MFL | ALICE disk usage at T2 (on last day of the quarter?) | From Mark Slater at Birmingham: capacity: 1.04PB available: 989TB (note that this is lower due to slowness in fixing problems due to COVID) used: 611TB
2 | 38 | 70% | 10% | 46% | MFL | T1 CPU Efficiency for DUNE | Worse than last quarter, which was 53% (from EGI website)
2 | 39 | 70% | 10% | 49% | MFL | T2 CPU Efficiency for DUNE | Up from 44% last quarter (from EGI website)
2 | 40 | 75% | 25% | 13% | MFL | CPU usage by DUNE in the UK relative to pledge of 2000 cores | 252 on average between both T1 (33 average cores) and T2 (219 average cores) sites. Much reduced from Q2, mainly on T1. N.B. The Tier 1 accounting for August for non-LHC VOs is missing
2 | 41 | 70% | 20% | 48% | MFL | T1 CPU Efficiency for Other (non-DUNE, non-LHC) | https://accounting.egi.eu/tier1/cpueff/TIER1/VO/2020/7/2020/9/custom-[object%20Object],ams02.cern.ch,auger,belle,biomed,clas12,dteam,enmr.eu,escape,gridpp,hyperk.org,ilc,juno,lofar,lsgrid,lsst,mpd.nica.jinr,na62.vo.gridpp.ac.uk,None,ops,pheno,projects.nl,skatelescope.eu,snoplus.snolab.ca,t2k.org,virgo,vo.cta.in2p3.fr,vo.france-grilles.fr,xenon.biggrid.nl/onlyinfrajobs/
2 | 42 | 70% | 20% | 71% | MOK | T2 CPU Efficiency for Other (non-DUNE, non-LHC) | Down from 80% last quarter
2 | 43 | 75% | 25% | 10% | MFL | T1/T2 % pledged CPU used by Other VOs (pledge is 13% of CPU used by combined LHC exps pledge in UK, which is 533922 HS06 ~ ) | T1 usage 7,587,895 HS06 hours = 3437 HS06; T2 usage 113,988,469 HS06 hours = 51625 HS06; Sum is 55062 HS06. Usage of CPU at T1 seems to be lower than expected. N.B. The Tier 1 accounting for August for non-LHC VOs is missing
Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments
|  | 2020-04-01 | N |  | MSU |  |  | Key - Milestones
|  | 2020-04-01 | N |  | MSU |  |  | Colour | Description | Code
[9 empty] | Milestone Achieved | MSA
[9 empty] | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes