## Resource & Narrative
Year | 2020 | Area | Other VOs
Quarter | Q2 | Reporter | KE
Narrative
Area | Successes |  |  | Problems
Onboarding new VOs | None |  |  | ALICE still have problems overwriting files in Echo with XRootD, so they can't effectively use all the available capacity.
Supporting existing VOs through major campaigns | There were no major campaigns this quarter. Dune were the largest non-LHC User averaging 994 core continuously across GridPP. |  |  | None
Service improvements | Development of Multi-VO Rucio was completed. |  |  | None
Risks
Type | Risk |  |  | Mitigation
General | Loss of critical expertise |  |  | Tier 1 liaisons are startin to support other VOs to spread the knowledge
Area Specifc | Service evolution moving faster than small VOs can cope with |  |  | Proactive communication from service owners to strongly encourage users to take up officially supported solutions (e.g. Rucio, DIRAC)
Area Specifc | Insufficient or inappropriate hardware resources to support other VOs |  |  | Careful monitoring of usage and support of some VOs through IRIS
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-06-30 | Establish a plan for VO support |  |  | Quarterly report created and completed, established links with VO contacts, write objectives, identify documentation
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2020-10-31 | Migrate users of Tier 1 'myproxy' off the service |  |  | Pheno is successfully using CERN myproxy or GridPP DIRAC
2020-09-30 | Test multi-VO Rucio instance |  |  | Dteam VO created and multiple people in GridPP able to use it
2020-11-30 | Migrate users away from the LFC |  |  | SNO+ using DIRAC File Catalogue

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 33 | 95% | 5% | 105% | MOK | UK Tier-1 work fraction for ALICE as a proportion of all Tier-1s (not CERN). Normalised to 3% for GridPP6 | https://accounting.egi.eu/tier1/elap_processors/TIER1/VO/2020/4/2020/6/all/onlyinfrajobs/ |  | Metric OK | MOK
2 | 34 | 70% | 10% | 63% | MCT | UK T1 CPU efficiency by ALICE. | https://accounting.egi.eu/tier1/elap_processors/TIER1/VO/2020/4/2020/6/all/onlyinfrajobs/ ALICE jobs are accessing data off site more than normal while Echo issues are resolved. |  | Metric Clost to Target | MCT
2 | 35 | 95% | 5% | 102.1% | MOK | UK T1 CPU usage by ALICE. Normalised against pledged HS06. | https://accounting.egi.eu/tier1/normelap_processors-quarter/TIER1/VO/2020/4/2020/6/all/onlyinfrajobs/ |  | Metric not OK | MFL
2 |  | 95% | 5% | 127.6% | MOK | UK Tier-2 work fraction for ALICE as a proportion of all Tier-2s. Normalised to 2.1% for GridPP6. | As a fraction of global T2 work for ALICE, 1,208,272 out of 45,166,889 = 2.68%. https://accounting.egi.eu/tier2/elap_processors/COUNTRY/VO/2020/4/2020/6/all/onlyinfrajobs/ |  | Metric with no Target | MNO
2 |  | 70% | 10% | 94% | MOK | UK T2 CPU efficiency for Alice. | 94%
[6 empty] | ALICE disk usage at T1 (on last day of the quarter?) Pledge=1.32PB | In RAL monitoring this value is only available for the last 7 days | Katy added these fields for storage - are they required?
|  |  |  | 78.43% |  | ALICE tape usage at T1 (on last day of the quarter?) - 'occupied size'. Pledge=1.131PB | http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting. 886824847278080
[6 empty] | ALICE disk usage at T2 (on last day of the quarter?) | Not sure how to access this (except by contacting each site)
2 | 36 | 70% | 5% | 53% | MFL | T1 CPU Efficiency for DUNE | 53% from EGI website
2 | 37 | 70% | 5% | 44% | MFL | T2 CPU Efficiency for DUNE | 44% from EGI website
2 | 39 | 75% | 25% | 84.25% | MOK | CPU usage by DUNE in the UK relative to pledge of 2000 cores | On average over the quarter DUNE used 1685 cores in the UK | 164,729 hours out of 303,887 hours at T1s, accorind to EGI which is incomplete. From DUNE: Proportion of total CPU hours run in the UK = 7.75%. This is dominated by User analysis at FNAL. As a proportion of Production jobs, UK runs 25% of total (38% if NERSC excluded)
2 | 40 | 70% | 5% | 72% | MOK | T1 CPU Efficiency for Other (non-DUNE, non-LHC) |  | https://accounting.egi.eu/egi/ngi/NGI_UK/cpueff/SITE/3M/2020/4/2020/6/custom-[object%20Object],bes,biomed,calice,cepc,cernatschool.org,clas12,comet.j-parc.jp,dteam,enmr.eu,fermilab,Gluex,gridpp,hyperk.org,icecube,ilc,iris.ac.uk,lsst,lz,magrid,mice,mu3e.org,na62.vo.gridpp.ac.uk,None,ops,pheno,skatelescope.eu,snoplus.snolab.ca,solidexperiment.org,t2k.org,virgo,vo.complex-systems.eu,vo.cta.in2p3.fr,vo.moedal.org,vo.northgrid.ac.uk,vo.scotgrid.ac.uk,vo.southgrid.ac.uk,zeus/onlyinfrajobs/
2 | 41 | 70% | 5% | 80% | MOK | T2 CPU Efficiency for Other (non-DUNE, non-LHC) | I am not sure how to remove T1 from this number on the accounting page. I could calculated based on T1 accounting for ~10% of total CPU hours in the UK, this would be 80%
2 | 42 | 75% | 25% | 76.92% | MOK | T1/T2 % pledged CPU used by Other VOs (pledge is 13% of CPU used by combined LHC exps pledge in UK, which is 533922 HS06 ~ ) | Total average usage is 5003 cores | https://accounting.egi.eu/egi/ngi/NGI_UK/elap_processors-quarter/SITE/3M/2020/4/2020/6/custom-[object%20Object],bes,biomed,calice,cepc,cernatschool.org,clas12,comet.j-parc.jp,dteam,enmr.eu,fermilab,Gluex,gridpp,hyperk.org,icecube,ilc,iris.ac.uk,lsst,lz,magrid,mice,mu3e.org,na62.vo.gridpp.ac.uk,None,ops,pheno,skatelescope.eu,snoplus.snolab.ca,solidexperiment.org,t2k.org,virgo,vo.complex-systems.eu,vo.cta.in2p3.fr,vo.moedal.org,vo.northgrid.ac.uk,vo.scotgrid.ac.uk,vo.southgrid.ac.uk,zeus/onlyinfrajobs/
Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments
|  | 2020-04-01 | N |  | MSU |  |  | Key - Milestones
|  | 2020-04-01 | N |  | MSU |  |  | Colour | Description | Code
[9 empty] | Milestone Achieved | MSA
[9 empty] | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Sheet1
UK-T1-RAL | 1 | ALICE | United Kingdom | 2020 | CPU | 10950
UK-SouthGrid | 2 | ALICE | United Kingdom | 2020 | CPU | 7896
UK-T1-RAL | 1 | ATLAS | United Kingdom | 2020 | CPU | 156436
UK-London-Tier2 | 2 | ATLAS | United Kingdom | 2020 | CPU | 39871
UK-NorthGrid | 2 | ATLAS | United Kingdom | 2020 | CPU | 51037
UK-ScotGrid | 2 | ATLAS | United Kingdom | 2020 | CPU | 33292
UK-SouthGrid | 2 | ATLAS | United Kingdom | 2020 | CPU | 20504
UK-T1-RAL | 1 | CMS | United Kingdom | 2020 | CPU | 52000
UK-London-Tier2 | 2 | CMS | United Kingdom | 2020 | CPU | 31993
UK-SouthGrid | 2 | CMS | United Kingdom | 2020 | CPU | 17007
UK-T1-RAL | 1 | LHCb | United Kingdom | 2020 | CPU | 81300
UK-London-Tier2 | 2 | LHCb | United Kingdom | 2020 | CPU | 6567
UK-NorthGrid | 2 | LHCb | United Kingdom | 2020 | CPU | 12529
UK-ScotGrid | 2 | LHCb | United Kingdom | 2020 | CPU | 6943
UK-SouthGrid | 2 | LHCb | United Kingdom | 2020 | CPU | 5597
[6 empty] | 533922 | 69409.86
|  |  | 0.72 | 0.1 | 0.072
|  |  | 0.79 | 0.9 | 0.711
0.79778

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes