## Resource & Narrative
Year | 2020 | Area | Other VOs
Quarter | Q2 | Reporter | Katy Ellis
Resource Alloc. | 1 |  | GridPP6 Funded |  |  | Unfunded Effort
Site | Task | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL |  | Katy Ellis | 0.15 | 0.15 | 0.15 | 0 | 0 | 0
RAL |  | Jame Walder | 0.15 | 0.15 | 0.15
RAL |  | Raja Nandakumar | 0.15 | 0.15 | 0.15
RAL | ALICE | George Patargias | 0.2 | 0.2 | 0.2
|  | Total | 0.65 | 0.65 | 0.65 | 0 | 0 | 0
|  | +/- Delivered | -0.35 | -0.35 | -0.35
Narrative
Area | Successes |  |  | Problems
Onboarding new VOs
Supporting existing VOs through major campaigns
Service improvements
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
2 | 33 | 95% | 5% | 98.6% | MOK | UK Tier-1 work fraction for ALICE as a proportion of all Tier-1s (not CERN). Normalised to 3% for GridPP6 |  |  | Metric OK | MOK
2 | 34 | 70% | 10% | 37% | MFL | UK T1 CPU efficiency by ALICE. | https://accounting.egi.eu/tier1/cpueff/TIER1/VO/2020/10/2020/12/all/onlyinfrajobs/. As previous quarter, possibly not fully using Echo, so possible reason for low efficiency, as increased number of Offsite reads? |  | Metric Clost to Target | MCT
2 | 35 | 90% | 10% | 107% | MOK | UK T1 CPU usage by ALICE. Normalised against pledged HS06. | 10950 HS06 is the 2020 pledge in CRIC |  | Metric not OK | MFL
2 | 36 | 95% | 5% | 106% | MOK | UK Tier-2 work fraction for ALICE as a proportion of all Tier-2s. Normalised to 2.1% for GridPP6. | 2.23% of Tier 2 work |  | Metric with no Target | MNO
2 | 37 | 70% | 10% | 80% | MOK | UK T2 CPU efficiency for Alice. | Slightly down from last quarter but still acceptable. https://accounting.egi.eu/tier2/cpueff/COUNTRY/VO/2020/10/2020/12/custom-alice/onlyinfrajobs/
|  | 80% | 10% | 24% |  | ALICE disk usage at T1 (on last day of the quarter?) Pledge=1.32PB | 322 TB - no change from last quarter. https://s3.echo.stfc.ac.uk/srr/storagesummary_2020-12-31.json
|  | 80% | 10% | 78% |  | ALICE tape usage at T1 (on last day of the quarter?) - 'occupied size'. Pledge=1.131PB | 887 TB - no change since Q3. http://www-public.gridpp.rl.ac.uk/tape_accounting/tape_accounting_31122020
|  | 80% | 10% |  |  | ALICE disk usage at T2 (on last day of the quarter?) | Waiting for number from Birmingham
2 | 38 | 70% | 10% | 47% | MFL | T1 CPU Efficiency for DUNE | Similar to the last quarter and consistent with other sites
2 | 39 | 70% | 10% | 50% | MFL | T2 CPU Efficiency for DUNE | Similar to the last quarter and consistent with other sites
2 | 40 | 75% | 25% | 51% | MCT | CPU usage by DUNE in the UK relative to pledge of 2000 cores | 1021 cores in total, fromT1 (average 268 cores) and T2 (average 753 cores). Much better usage than Q3.
2 | 41 | 70% | 20% | 91% | MOK | T1 CPU Efficiency for Other (non-DUNE, non-LHC) | Big improvement from 48% last quarter. However, Q3 was dominated by usage by Virgo, with low efficiency. No Virgo work ran in Q4.
2 | 42 | 70% | 20% | 79% | MOK | T2 CPU Efficiency for Other (non-DUNE, non-LHC) | Improvement from 71% in Q3.
2 | 43 | 75% | 25% | 75% | MOK | T1/T2 % pledged CPU used by Other VOs (pledge is 13% of CPU used by combined LHC exps pledge in UK, which is 533922 HS06 ~ so 13% is 69410) | T1 usage 4761922 HS06 hours = 2157 HS06; T2 usage 110465392 HS06 hours = 50030 HS06; Sum is 52187 HS06. We appear to have calculated this incorrectly last quarter.
Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments
|  | 2020-04-01 | N |  | MSU |  |  | Key - Milestones
|  | 2020-04-01 | N |  | MSU |  |  | Colour | Description | Code
[9 empty] | Milestone Achieved | MSA
[9 empty] | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes