## Resource & Narrative
Year | 2020 | Area | Security
Quarter | Q2 | Reporter | DK / DC
Narrative
Area | Successes |  |  | Problems
Operations | Good progress made on integration of IRIS operational security with the GridPP security team. HPC and Cloud experts appointed and more GridPP members too. Handling the well advertised HPC security incident in May 2020 allowed many lessons, especially in relation to communication to be learned. This work also included building closer ties to Janet CSIRT. We co-organised, chaired and spoke at the 3 half-days WISE virtual meeting in April and at the EOSC-hub virtual conference in May. WISE Community and work on SCI within that continues to make progress and is closely linked to our policy and trust work much of which is funded by IRIS. |  |  | Communication challenge in April 2020 exposed some serious problems with institutional email systems. All investigated and now fixed (we hope!)
Trust & Identity | Good progress on WLCG AuthZ working group, to which we all belong and also in the REFEDS Sirtfi working group and eduGAIN security. |  |  | Policy issues related to GDPR continues to be a challenge. We are leading activities in WLCG and EGI addressing these and look forward to the updated GEANT Code of Conduct Version 2
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1c | 15 | 95% | 5% | 85% | MFL | % of Sites responding to security communication requests | 3 sites never received the contact email because of mail issues primarily outwith the sites. This is believed to have been resolved (prior to future testing) |  | Metric OK | MOK
3 | 3 | 95% | 5% | 100% | MOK | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | N/A: No applicable Critical SVG Broadcasts in scope (2 CRITICAL but not applicable to GridPP) |  | Metric Clost to Target | MCT
3 | 4 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | N/A: No applicable incidents in scope |  | Metric not OK | MFL
[9 empty] | Metric with no Target | MNO
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
1c | 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved |  | Milestone Achieved | MSA
1c | 2 | 2022-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Ongoing | MOG
1c | 3 | 2023-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Overdue | MOD
1c | 4 | 2024-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone not due | MSU
1c | 5 | 2022-04-01 | N |  | MSU | GridPP-wide security training event
1c | 6 | 2024-04-01 | N |  | MSU | GridPP-wide security training event
1c | 7 | 2022-04-01 | N |  | MSU | Review of the role of the security team
3 | 1 | 2021-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 2 | 2022-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 3 | 2023-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 4 | 2024-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 5 | 2022-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge
3 | 6 | 2024-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes