## Resource & Narrative
Year | 2020 | Area | Security
Quarter | Q3 | Reporter | DK / DC
Narrative
Area | Successes |  |  | Problems
Operations | The usual operational security activities were carried out as required. Progress continues on the integration of IRIS operational security with the GridPP security team. Contributing to the work in IRIS on a new Procedure for Security Incident Response. Planning carried out for the next WISE virtual meeting in October and the EGI Conference in November. Attended the EGI CSIRT meeting and the NSF Cybersecurity Summit (USA) both in September. |  |  | None
Trust & Identity | Good progress on WLCG AuthZ working group and also in the REFEDS Sirtfi working group and eduGAIN security. Work on WISE SCI continues to make good progress and is closely linked to our policy and trust work funded by IRIS. We attended and spoke at the joint EUGridPMA and GN4-3 policy meeting in September. |  |  | Policy issues related to GDPR continues to be a challenge. We are leading activities in WLCG and EGI addressing these. The long-awaited updated GEANT Code of Conduct Version 2 has been delayed more and now will initially only cover data transfers within Europe.
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1c | 15 | 95% | 5% | 100% | MOK | % of Sites responding to security communication requests | N?A: No communications challenges in scope |  | Metric OK | MOK
3 | 3 | 95% | 5% | 100% | MOK | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | N/A: No applicable Critical SVG Broadcasts in scope |  | Metric Clost to Target | MCT
3 | 4 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | N/A: No applicable incidents in scope |  | Metric not OK | MFL
[9 empty] | Metric with no Target | MNO
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
1c | 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved |  | Milestone Achieved | MSA
1c | 2 | 2022-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Ongoing | MOG
1c | 3 | 2023-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Overdue | MOD
1c | 4 | 2024-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone not due | MSU
1c | 5 | 2022-04-01 | N | 2020-07-01 | MSA | GridPP-wide security training event | IRIS Security Workshop held at end of July 2020
1c | 6 | 2024-04-01 | N |  | MSU | GridPP-wide security training event
1c | 7 | 2022-04-01 | N |  | MSU | Review of the role of the security team
3 | 1 | 2021-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 2 | 2022-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 3 | 2023-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 4 | 2024-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 5 | 2022-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge
3 | 6 | 2024-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes