## Resource & Narrative
Year | 2020 | Area | Security
Quarter | Q4 | Reporter | DK / DC
Narrative
Area | Successes |  |  | Problems
Operations | Usual operational security activities were carried out as required. Progress continues on integration of IRIS operational security with GridPP security team. 2 critical vulnerabilities in storage technologies used by GridPP were handled with minimal impact to GridPP services and good communication from sites. Presented at EGI Conference. |  |  | None
Trust & Identity | Continued progress in REFEDS SIRTFI working group and eduGAIN security. IRIS Infrastructure Security Policy approved . Ongoing collaboration with policy groups in WISE, GN4-3 and IGTF. Making good progress on guidance for use of Assurance frameworks |  |  | None
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1c | 15 | 95% | 5% | 100% | MOK | % of Sites responding to security communication requests | n/a for this reporting period |  | Metric OK | MOK
3 | 3 | 95% | 5% | 95% | MOK | % Tier2 sites responding to WLCG Critical EGI SVG broadcasts | 2 applicable broadcasts. dCache: 2 applicable sites, both responded promptly to direct emails DPM: 6 sites impacted with prior knowledge of impacted versions, all bar 1 responded to general request + 1 after direct email |  | Metric Clost to Target | MCT
3 | 4 | 95% | 5% | 100% | MOK | % Tier2 sites following WLCG incident response procedures | n/a for this reporting period |  | Metric not OK | MFL
[9 empty] | Metric with no Target | MNO
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
1c | 1 | 2021-04-01 | Y | 2020-07-01 | MSA | GridPP-wide security communication challenge | GridPP-wide security communication challenge: Challenge largely successful, but highlighted some mail infrastructure issues which are believed to have been solved |  | Milestone Achieved | MSA
1c | 2 | 2022-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Ongoing | MOG
1c | 3 | 2023-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone Overdue | MOD
1c | 4 | 2024-04-01 | N |  | MSU | GridPP-wide security communication challenge |  |  | Milestone not due | MSU
1c | 5 | 2022-04-01 | N | 2020-07-01 | MSA | GridPP-wide security training event | IRIS Security Workshop held at end of July 2020
1c | 6 | 2024-04-01 | N |  | MSU | GridPP-wide security training event
1c | 7 | 2022-04-01 | N |  | MSU | Review of the role of the security team
3 | 1 | 2021-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 2 | 2022-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 3 | 2023-04-01 | N |  | MSU | Review WLCG security policy and procedure set
3 | 4 | 2024-04-01 | N |  | MSU | Review of WLCG site security operations (SOC) guidelines
3 | 5 | 2022-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge
3 | 6 | 2024-04-01 | N |  | MSU | Participation in EGI CSIRT Service Security Challenge

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
2020-11-03 | EGI Conference, "Developing a Trust and Security Framework for IRIS", D Crooks
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes