## Resource & Narrative
Year | 2020 | Area | Federal Services
Quarter | Q3 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
GOCDB | Both SL7 hosts on Tier-1 VMWare infrastructure now in production, making GOCDB highly available. GOCDB now uses a certificate that is trusted by both modern browsers and the IGTF trust bundle.
Accounting - APEL and IRIS Dashboard | Prototype version of T1 dashboard setup, needs more work to be useable.
Workflow Management - DIRAC | Preparing for upgrade (v7), including contributing bug fixes to the core DIRAC code
Data Management - Rucio and FTS | Deployed test instance with multiple VOs
CVMFS Service | Started work in preparation for the upgrade of the infrastructure to SL7
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
GOCDB: Migration to Centos 7 VM Failover at Hartree Centre, decommissioning of bare metal Red Hat 6 Failover at DL.
APEL: Migration of messaging to AMS. Decommissioning of SL6 hosts.

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
3 | 1 | 99% | 2% | 100% | MOK | GOCDB Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-GOCDB?start_date=2020-07-01&end_date=2020-09-30 |  | Metric OK | MOK
3 | 2 | 0.5 | 0.1 | 1.3 | MOK | GOCDB Usage | Average Number of Concurrent GOCDB sessions https://vande.gridpp.rl.ac.uk/next/d/gbuGiWHMk/gocdb-longer-term-host-metrics?orgId=1&from=1593558000000&to=1601506799000&viewPanel=6 |  | Metric Clost to Target | MCT
3 | 3 | 99% | 2% | 100% | MOK | APEL Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-APEL?start_date=2020-07-01&end_date=2020-09-30 |  | Metric not OK | MFL
3 | 4 | 1 | 0.2 | 1.2 | MOK | APEL Usage | Millions of messages processed in the quarter. |  | Metric with no Target | MNO
3 | 5 | 97% | 2% | 99% | MOK | Workflow Management (DIRAC) Availability
3 | 6 |  |  | 9 | MOK | Workflow Management (DIRAC) Usage | Measured as number of active VO (>2000 jobs in the quarter)
3 | 7 | 99% | 2% | 100% | MOK | Data Management (FTS + Rucio) Availability | Only measuring FTS service availability currently
3 | 8 |  |  |  | AWI | Data Management (FTS + Rucio) Usage
3 | 9 | 99% | 2% | 100% | MOK | CVMFS Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-CVMFS?start_date=2020-07-01&end_date=2020-09-30
3 | 10 |  |  | 44 | MOK | CVMFS Usage | Measured as number of active repositories
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
|  |  | N |  | MSU |  |  |  | Milestone Achieved | MSA
|  |  | N |  | MSU |  |  |  | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes