## Resource & Narrative
Year | 2020 | Area | Federal Services
Quarter | Q4 | Reporter | AD
Narrative
Area | Successes |  |  | Problems
GOCDB | Migrated failover to a CentOS 7 VM. This ensures we continue to run a secure and updated off site failover for GOCDB. To meet requirements of the EOSC-hub project, a separate “view” of GOCDB was deployed: https://gocdb.eosc-hub.eu/portal/ |  |  | Old failover lost outgoing network connectivity following central firewall work which eventually led to the failover being inaccessible by most clients, as it could not update its CRLs. Sufficient rules we (re-)added eventually by our corporate IT and access to the failover restored.
Accounting - APEL and IRIS Dashboard | Prototype version of T1 dashboard setup, needs more work to be useable.
Workflow Management - DIRAC | Successful upgrade of the major DIRAC version on the GridPP. Simon has now taken on the on the release manager role for the VMDIRAC package which DIRAC uses to deploy VMs on clouds within the DIRAC framework.
Data Management - Rucio and FTS | Deployed test instance with multiple VOs
CVMFS Service | Started work in preparation for the upgrade of the infrastructure to SL7
Risks
Type | Risk |  |  | Mitigation
General
Area Specifc
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
GOCDB: Migration to Centos 7 VM Failover at Hartree Centre, decommissioning of bare metal Red Hat 6 Failover at DL.
APEL: Migration of messaging to AMS. Decommissioning of SL6 hosts.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
3 | 1 | 99% | 2% | 99.94% | MOK | GOCDB Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-GOCDB?start_date=2020-10-01&end_date=2020-12-31 |  | Metric OK | MOK
3 | 2 | 0.5 | 0.1 | 1.53 | MOK | GOCDB Usage | Average Number of Concurrent GOCDB sessions https://vande.gridpp.rl.ac.uk/next/d/gbuGiWHMk/gocdb-longer-term-host-metrics?orgId=1&from=1593558000000&to=1601506799000&viewPanel=6 |  | Metric Clost to Target | MCT
3 | 3 | 99% | 2% | 100% | MOK | APEL Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-APEL?start_date=2020-10-01&end_date=2020-12-31 |  | Metric not OK | MFL
3 | 4 | 1 | 0.2 | 1.2 | MOK | APEL Usage | Millions of messages processed in the quarter. |  | Metric with no Target | MNO
3 | 5 | 97% | 2% | 99% | MOK | Workflow Management (DIRAC) Availability
3 | 6 |  |  | 7 | MOK | Workflow Management (DIRAC) Usage | Measured as number of active VO (>2000 jobs in the quarter)
3 | 7 | 99% | 2% | 100% | MOK | Data Management (FTS + Rucio) Availability | Only measuring FTS service availability currently
3 | 8 |  |  |  | AWI | Data Management (FTS + Rucio) Usage
3 | 9 | 99% | 2% | 99.94% | MOK | CVMFS Availability | https://egi.ui.argo.grnet.gr/egi/report-ar-dates-2/OPS-MONITOR-Critical/SITES/GRIDOPS-CVMFS?start_date=2020-10-01&end_date=2020-12-31
3 | 10 |  |  | 44 | MOK | CVMFS Usage | Measured as number of active repositories
Milestones | [7 empty] | Key - Milestones
WP | ID | Target | Started | Completed | Status | Description | Comments | Colour | Description | Code
|  |  | N |  | MSU |  |  |  | Milestone Achieved | MSA
|  |  | N |  | MSU |  |  |  | Milestone Ongoing | MOG
[9 empty] | Milestone Overdue | MOD
[9 empty] | Milestone not due | MSU

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes