## Resource & Narrative
Year | 2021 | Area | LondonGrid
Quarter | Q1 | Reporter | DR
Narrative
Area | Successes |  |  | Problems
Brunel
Imperial
QMUL | We have disposed of several racks of equipment (R510s storage and C6100 compute nodes, racks and PDUs) to make space for new equipment. We have finished the procurement of a significant amount of equipment and have taken delivery before the end of the financial year (120 compute server, 8 GPU servers, network switches and cables, racks and PDUs). We have physically installed all the equipment in new racks with new PDUs. We have upgraded Lustre to latests LTS version 2.12.6 as well as general hardware firmware updates for all equipment. We continue to Plan for DC refurbishment.
RHUL | Migration to C7 almost done. Only one service left (argus) |  |  | Some intermittent problems with switches. Power outage happened the 5th of March, so we were offline for a couple of days until the power generator was fixed.
Risks
Type | Risk |  |  | Mitigation
Brunel
Imperial
QMUL
RHUL | WAN connection to Janet is insufficient for site to operate effectively as non-storage site
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 1 | 100% | 5% | 308.5% | MOK | % of WLCG Pledged CPU Available - LondonGrid |  |  | Metric OK | MOK
1b | 5 | 100% | 5% | 226% | MOK | % of WLCG Pledged Disk Available - LondonGrid |  |  | Metric Clost to Target | MCT
1b | 9 | 50% | 5% | 77.19% | MOK | % CPU Utilisation (Wall Clock) - LondonGrid | Brunel: 27% utilisation |  | Metric not OK | MFL
1b | 15 | 95% | 5% | 96.7% | MOK | Average Argo Availability - LondonGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% | 96.89% | MOK | Average Argo Reliability - LondonGrid

## Resources
Please fill in all fields highlighed in
Capacities | Brunel | Imperial | QMUL | RHUL | Total | Notes
CPU Available (HS06) | 52831 | 113946 | 70000 | 56000 | 292777 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 19770 | 22156 | 26991 | 25984 | 94901
% of Pledge | 267.2% | 514.3% | 259.3% | 215.5% | 308.5%
Storage Available (TB) | 1500 | 8129 | 5100 | 1300 | 16029
Storage Pledged (TB) | 918 | 2794 | 3379 | 685 | 7091
% of Pledge | 163.4% | 290.9% | 150.9% | 189.8% | 226%
Availability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 100 | 99.73 | 75.43 | 100 | 93.79% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 97.4 | 100 | 93.56 | 100 | 97.74% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.42 | 100 | 97.2 | 97.67 | 98.57%
% Tier-2 Averge | 98.94 | 99.91 | 88.73 | 99.2233 | 96.7%
Reliability | Brunel | Imperial | QMUL | RHUL | Avg | Notes
Month 1 | 100 | 99.73 | 75.43 | 100 | 93.79% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 97.4 | 100 | 93.56 | 100 | 97.74% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 99.42 | 100 | 97.2 | 100 | 99.16%
% Tier-2 Total | 98.94 | 99.91 | 88.73 | 100 | 96.89%
CPU Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2160 | 2160 | 2160 | 2160 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 114114960 | 246123360 | 151200000 | 120960000 | 632398320 | https://accounting.egi.eu/tier2/federation/London Tier 2/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 6385641.2673 | 58509994.8025 | 31398455.4321 | 34189749.0308 | 130483840.5327 | Q1: 2160/2184 (if leap year)
Month 2 | 5253698.313 | 53742194.0105 | 46827890.9493 | 33353203.5027 | 139176986.7755 | Q2: 2184
Month 3 | 8165188.8269 | 59006285.2196 | 55419114.1615 | 26098883.5528 | 148689471.7608 | Q3: 2208
Total: | 19804528.4072 | 171258474.0326 | 133645460.5429 | 93641836.0863 | 418350299.069 | Q4: 2208
% Utilisation | 17.35% | 69.58% | 88.39% | 77.42% | 66.15%
WallClock Hours (HS06) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Hours this Quarter | 2160 | 2160 | 2160 | 2160 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 114114960 | 246123360 | 151200000 | 120960000 | 632398320 | https://accounting.egi.eu/tier2/federation/London Tier 2/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 9393710.4564 | 78523859.6413 | 29208344.2561 | 39878350.3251 | 157004264.6789 | Q1: 2160/2184 (if leap year)
Month 2 | 8910544.6143 | 70073969.27 | 43667143.9038 | 36447750.4862 | 159099408.2743 | Q2: 2184
Month 3 | 11973673.1726 | 75918591.094 | 53277622.3889 | 30905823.7639 | 172075710.4194 | Q3: 2208
Total: | 30277928 | 224516420 | 126153111 | 107231925 | 488179383.3726 | Q4: 2208
% Utilisation | 26.53% | 91.22% | 83.43% | 88.65% | 77.19%
Storage LHC & IRIS: AVAILABLE (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 32.98 | 0 | 4500 | 1055 | 5587.98 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 1429 | 4058.129 | 1 | 2.2 | 5490.329 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 710 | 300 | 0 | 1010
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 1204 | 0 | 0 | 1204
Storage LHC & IRIS: USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
Atlas | 27.4 | 0 | 3300 | 781 | 4108.4 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 894 | 3486.319 | 0.5 | 1.57 | 4382.389 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 3.2314e-08 | 413 | 235 | 0 | 648
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 0 | 718.8 | 0 | 0 | 718.8
Storage - Other : USED (TB) | Brunel | Imperial | QMUL | RHUL | Total | Notes
biomed | 0.357 | 0 | 0.5 | 0 | 0.857 | Active VOs at you site can be assesed from the following link:
comet.j-parc.jp | 0 | 36 | 0 | 0 | 36 | https://accounting.egi.eu/tier2/federation/London Tier 2/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
dune | 0 | 2.98 | 5 | 0 | 7.98 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
gridpp | 0.5 | 0 | 10 | 0 | 10.5 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
ilc | 0 | 0 | 0 | 0 | 0
lsst | 0 | 77.8 | 5 | 0 | 82.8
lz | 0 | 810.49 | 0.5 | 0 | 810.99
na62.vo.gridpp.ac.uk | 0 | 0 | 0 | 0 | 0
pheno | 0.008 | 0 | 0.5 | 0 | 0.508
skatelescope.eu | 0 | 0 | 10 | 0 | 10
snoplus.snolab.ca | 0 | 0 | 10 | 0 | 10
solidexperiment.org | 0 | 529 | 0 | 0 | 529
t2k.org | 0 | 46.4 | 200 | 0 | 246.4
vo.complex-systems.eu | 0 | 0 | 0 | 0 | 0
vo.cta.in2p3.fr | 0 | 0 | 0 | 0 | 0
supernemo | 0 | 0 | 0 | 0 | 0
mice | 9.6 | 0 | 0 | 0 | 9.6
vo.moedal.org | 0 | 0 | 5 | 0 | 5
fusion | 0 | 0 | 0 | 0 | 0
cernatschool.org | 0 | 0 | 0.5 | 0 | 0.5
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes