## Resource & Narrative
Year | 2021 | Area | NorthGrid
Quarter | Q1 | Reporter | MD
Narrative
Area | Successes |  |  | Problems
Lancaster | Achieved funding for a major storage and hardware refresh, as well as a starting block for future resources |  |  | A large portion of our storage has become almost unusable to due a high rate of HDD failures and lack of agility with ZFS.
Liverpool | Still just Rob and John keeping things ticking over. General node and server maintenance as site visits permit. Gradual retirement of long-out-of-warranty storage and worker nodes when it becomes necessary. ARC CE upgraded and accounting publishing fixed/updated on CEs and SE. |  |  | Still waiting on University to upgrade their hardware to support production IPv6. Storage capacity down a bit ~150TB, we've had to retire a few old servers due to age and reliability.
Manchester
Sheffield | Site has kept on running. |  |  | Some ongoing electrical work, but planned so all done within downtimes.
Risks
Type | Risk |  |  | Mitigation
Lancaster | Large portion of storage “at risk” |  |  | Temporary reduction in atlas use at the site to give space to move data, use portion of new disk to make up the short fall
Liverpool | Aging Kit |  |  | Planned retirements
Manchester
Sheffield | Low amount of available support effort |  |  | Support from the community will hopefully help.
Objectives and Deliverables Last Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-03-30 | Lancs: Maintain good job throughput and reliability despite the problems with storage Lancs: Purchase new kit using EoY funds. |  |  | Good CPU hours New kit to shore up losses and provide core for future storage
2021-03-30 | Liv: Fixed APEL problems, kept ARC updated. |  |  | Accurate accounting, up to date services.
Objectives and Deliverables This Quarter
Due Date | Objective/Deliverable |  |  | Metric/Output
2021-05-31 | Lancs: Put new compute and a portion of the new storage online and in production. |  |  | Increased/restored capacity.
2021-06-30 | Lancs: Have the base to a CEPH test instance planned out using the other disk servers obtained. |  |  | Core to future storage, progress to be reported to storage group.

## Metrics & Milestones
Metrics | [7 empty] | Key - Metrics
WP | ID | Target | Margin | Current | Status | Description | Comments | Colour | Description | Code
1b | 2 | 100% | 5% |  | AWI | % of WLCG Pledged CPU Available - NorthGrid |  |  | Metric OK | MOK
1b | 6 | 100% | 5% |  | AWI | % of WLCG Pledged Disk Available - NorthGrid |  |  | Metric Clost to Target | MCT
1b | 10 | 50% | 5% |  | AWI | % CPU Utilisation (Wall Clock) - NorthGrid |  |  | Metric not OK | MFL
1b | 15 | 95% | 5% |  | AWI | Average Argo Availability - NorthGrid |  |  | Metric with no Target | MNO
1b | 16 | 95% | 5% |  | AWI | Average Argo Reliability - NorthGrid

## Resources
Please fill in all fields highlighed in
Capacities | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
CPU Available (HS06) | 79845 | 37645 | 55829 | 11918 | 173319 | Pledge figures are given and agreed at the start of each GridPP year (April) by local PI
CPU Pledged (HS06) | 23955 | 14171 | 29463 | 9326 | 76915
% of Pledge | 333.3% | 265.6% | 189.5% | 127.8% | 225.3% | Capacity figures are as reported by the site directly.
Storage Available (TB) | 3400 | 1424 | 6820 | 0 | 11644
Storage Pledged (TB) | 1645 | 724 | 3979 | 29 | 6348
% of Pledge | 206.7% | 196.7% | 171.4% | 0% | 183.4%
Availability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 99 | 100 | 96 | 97 | 98% | Availability numbers from the last quarter can be found at the following link:
Month 2 | 95 | 99 | 98 | 87 | 94.75% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 97 | 99 | 100 | 98 | 98.5%
% Tier-2 Averge | 97 | 99.3333 | 98 | 94 | 97.08%
Reliability | Lancaster | Liverpool | Manchester | Sheffield | Avg | Notes
Month 1 | 99 | 100 | 96 | 100 | 98.75% | Reliability numbers from the last quarter can be found at the following link:
Month 2 | 95 | 99 | 98 | 90 | 95.5% | https://egi.ui.argo.grnet.gr/egi/report-ar/Critical/SITES?filter=NGI_UK
Month 3 | 97 | 99 | 100 | 98 | 98.5%
% Tier-2 Total | 97 | 99.3333 | 98 | 96 | 97.58%
CPU Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2160 | 2160 | 2160 | 2160 | Quarter | CPU time available from link below:
Max achievable HS06/hrs | 172465200 | 81313200 | 120590640 | 25742880 | 400111920 | https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 55500056 | 18871409 | 45599876 | 8043965 | 128015306 | Q1: 2160/2184 (if leap year)
Month 2 | 46313095 | 20172797 | 50831274 | 4640123 | 121957289 | Q2: 2184
Month 3 | 58079528 | 20600455 | 55437432 | 7155211 | 141272626 | Q3: 2208
Total: | 159892679 | 59644661 | 151868582 | 19839299 | 391245221 | Q4: 2208
% Utilisation | 92.71% | 73.35% | 125.9% | 77.07% | 97.78% | Used: https://accounting.egi.eu/tier2/federation/NorthGrid/normcpu/DATE/SITE/2020/4/2020/6/all/localinfrajobs/
WallClock Hours (HS06) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Hours this Quarter | 2160 | 2160 | 2160 | 2160 | Quarter | WallClock time available from link below:
Max achievable HS06/hrs | 172465200 | 81313200 | 120590640 | 25742880 | 400111920 | https://accounting.egi.eu/tier2/federation/NorthGrid/normelap_processors/SITE/DATE/2021/1/2021/3/all/localinfrajobs/
Hours per quarter:
Month 1 | 65556422 | 20730032 | 56943686 | 8492995 | 151723135 | Q1: 2160/2184 (if leap year)
Month 2 | 55488078 | 22199983 | 58088369 | 5541405 | 141317835 | Q2: 2184
Month 3 | 70584110 | 22421975 | 62940938 | 7261494 | 163208517 | Q3: 2208
Total: | 191628610 | 65351990 | 177972993 | 21295894 | 456249487 | Q4: 2208
% Utilisation | 111.1% | 80.37% | 147.6% | 82.73% | 114%
Storage LHC & IRIS: AVAILABLE (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 3400 | 970 | 0 | 0 | 4370 | Please indicate how much storage is AVAILABLE at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is available
LHCb | 0 | 313 | 0 | 0 | 313
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 1060 | 0 | 0 | 0 | 1060
Storage LHC & IRIS: USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
Atlas | 2800 | 860 | 0 | 0 | 3660 | Please indicate how much storage is USED at each site in the distributed Tier-2 for the LHC experiments
CMS | 0 | 0 | 0 | 0 | 0 | Additionally if the site has recieved and is required to provide storage for IRIS VOs please indicate how much is USED
LHCb | 0 | 211 | 0 | 0 | 211
Alice | 0 | 0 | 0 | 0 | 0
IRIS | 313 | 0 | 0 | 0 | 313
Storage - Other : USED (TB) | Lancaster | Liverpool | Manchester | Sheffield | Total | Notes
t2k.org | 18 | 23.4 | 0 |  | 41.4 | Active VOs at you site can be assesed from the following link:
snoplus.snolab.ca | 0.5 | 0.3 | 0 |  | 0.8 | https://accounting.egi.eu/tier2/federation/NorthGrid/njobs/VO/DATE/2021/1/2021/3/all/localinfrajobs/
na62.vo.gridpp.ac.uk | 0 | 2.5 | 0 |  | 2.5 | This includes all VOs that have run at least one job at the distributed Tier-2 in the last Quarter and are deemed to be supported.
cernatschool.org | 0 | 0.03 | 0 |  | 0.03 | If you have other VOs that are supported, use storage and may not have run in the last quarter please include them also.
dteam | 0.01 | 0.04 | 0 |  | 0.05
esr | 0 | 0.1 | 0 |  | 0.1
gridpp | 0.001 | 0 | 0 |  | 0.001
lsst | 0 | 1 | 0 |  | 1
dune | 0 | 0.6 | 0 |  | 0.6
mu3e.org | 0 | 13.6 | 0 |  | 13.6
hyperk.org | 0.25 | 0 | 0 |  | 0.25
| 0 | 0 | 0 |  | 0
lsst (iris) | 91 | 0 | 0 |  | 91
dune (iris) | 25 | 0 | 0 |  | 25
vo.cta.in2p3.fr (iris) | 150 | 0 | 0 |  | 150
ska.telescope.eu (iris) | 0.03 | 0 | 0 |  | 0.03
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0
| 0 | 0 | 0 |  | 0

## Outreach & Knowledge Sharing
Outreach & Knowledge Exchange - ResearchFish Inputs
Date | Publications | Notes
Date | Collaborations | Notes
Date | Further Funding (e.g. External Funding) | Notes
Date | Destination of Ex. Staff | Notes
Date | Dissemmination Events | Notes
Date | Intellectual Property | Notes
Date | Spin out companies | Notes
Date | Roles Held on Committees and Boards | Notes
Date | Other Outputs and Knowledge Exchange | Notes